## Triveniganj
MPPR OF -Triveniganj, Month -September . 2014
Sl. | DESCRIPTION OF PROGRAM | Cummalitive achievement Previous month | Cummalitive achievement in current month | Cummalative achievement
1 | No. of Panchayats | 18 | 0 | 18
2 | No of revenue villages to be covered | 36 | 0 | 36
3 | No of Village to be saturated (geographically) - certification from the VO | 22 | 0 | 22
Result-1 | Formation of self reliant and inclusive community institutions including SHGs, Village Organizations and Federations.
In-1.2 | Self managed self help groups (SHGs) established, covering at least 80% of the target households, 60% of formed SHGs into VO; and 40% of the formed VOs into BLF.
| Total SGSY groups in JEEViKA fold | 0 | 0 | 0
1.2.1 | Total No of SHG formed (C1- ……... , C2- ………., C3-……….) *** | 1372 | 40 | 1412
| TOTAL NO OF POOR MOBILISED | 16348 | 428 | 16776
| No. of SC | 4129 | 142 | 4271
| No. ST | 152 | 0 | 152
| No.EBC | 3011 | 12 | 3023
| No. OBC | 7099 | 209 | 7308
| No. Minority | 1880 | 48 | 1928
| General | 77 | 17 | 94
1.2.2 | No. of Village Organisation Formed (C1- …., C2-….., C3- ……..) *** | 82 | 0 | 82
1.2.3 | No. of 4 months old SHGs Part of Village Organisation | 860 | 0 | 860
| No. of CLF Formed | 1 | 0 | 1
| No. of one year old VO part of CLF | 15 | 0 | 15
| No. of VO Registered under Cooperative Society Act-1999 | 5 | 0 | 5
COMMUNITY CADRES - IB & CB
1.2.6 | Number of CM working | 139 | 0 | 139
1.2.7 | Number of VO Book Keepers working | 17 | 0 | 17
1.2.8 | Number of Internal CRPs - SHG Formation working | 62 | 0 | 62
1.2.9 | Number of Internal CRPs-VO formation working | 0 | 0 | 0
1.2.10 | Number of Internal CRPs -Master Trainer working | 0 | 0 | 0
| No. of TSC CRP identified/Trained | 0 | 0 | 0
In-1.3 | At least 75% of formed VOs accessed and managed project funds as per project processes at any point of time
1.3.1 | No of VOs having Bank Account | 77 | 2 | 79
1.3.2 | No of VO to manage Baalwaadi | 0 | 0 | 0
1.3.3 | No of VO to be promoted as Health & Nutrition center | 0 | 0 | 0
1.3.4 | Number of VO participating in HRF | 61 | 0 | 61
1.3.5 | No. of members benefitted in HRF | 178 | 0 | 178
1.3.6 | No of VO received funding for its Action Plan | 0 | 0 | 0
In-1.4
1.4.2 | No. of SHGs having Bank A/C | 1164 | 67 | 1231
1.4.3 | No of Bank Mitra working | 4 | 0 | 4
1.4.4 | No of eligible SHGs ( six month old SHG + following PANCHSUTRA ) financed by Banks | 800 | 50 | 850
1.4.5 | Amount Loaned by Banks to SHG | 40000000 | 2500000 | 42500000
1.4.6 | No of Groups repeat financed by Banks | 13 | 18 | 31
1.4.7 | Repeat financed Amount by Banks | 1300000 | 1800000 | 3100000
1.4.10 | No. of SHG members received bond under insurance programme. | 3495 | 0 | 3495
Result-2 | Establishment and use of Community Investment Fund for food security, social services, assets and income generation and service sector investment
2.1.1 | No of Group visited for Social plan | 0 | 0 | 0
2.1.2 | No of SHG members made signature literate | 7032 | 122 | 7154
2.1.3 | No of SHG made financial literate | 0 | 0 | 0
5 | No of SHG Member linked with RSBY - Health insurance | 1139 | 0 | 1139
2.1.5 | Sanitation Programme initiated with number of SHGs | 0 | 0 | 0
2.1.6 | No. of SHG HHs linked with Social Security Programme | 0 | 0 | 0
2.1.7 | No of Social Security Resource Person working | 0 | 0 | 0
2.1.8 | NO of Social Security community professional working | 0 | 0 | 0
2.1.9 | No of groups to complete Micro Planing exercise within 3 months of Group formation | 999 | 32 | 1031
2.1.10 | No of Group Recd ICF through BPIU | 924 | 99 | 1023
2.1.11 | No of Group Recd ICF through VO | 0 | 0 | 0
2.1.12 | Total No. of Groups received ICF through Vo/BPIU | 797 | 111 | 908
2.1.13 | No of groups/Farmers to complete Livelihoods Micro Planing exercise(SWI) | 0 | 0 | 0
2.1.14 | No of Group Revisited for Micro plan | 0 | 0 | 0
2.1.15 | No of trained CM generating Micro Plan | 0 | 0 | 0
Food security increased for 80% of target households as compared to the baseline
2.1.16 | Number of VO participating in FSF | 60 | 0 | 60
2.1.17 | No of HH linked with FS Intervention | 1563 | 0 | 1563
Result - 3 | Establishment and operationalization of Technical Assistance Fund.
In- 3.1 | At least 5 major business linkages established through public/private partnership by CBOs
3.1.1 | No of SHG members registered in VO for SRI | 2540 | 0 | 2540
3.1.2 | No of SHG members registered in VO for SWI | 460 | 0 | 460
3.1.3 | No of Acres of land will be under Agriculture Intervention-SRI | 117 | 0 | 117
3.1.4 | No of Acres of land will be under Agriculture Intervention- SWI | 0 | 0 | 0
3.1.5 | No of vermi-compost pit will be prepared | 0 | 0 | 0
3.1.6 | No of VRP will work in the Agriculture Intervention | 41 | 0 | 41
3.1.7 | No of Skilled Extension Worker will be created in Agriculture Intervention | 0 | 0 | 0
3.1.8 | No of SHG members will be registered in existing DCS | 0 | 0 | 0
3.1.9 | No of New DCS formed | 0 | 0 | 0
3.1.10 | No of SHG members will be registered in new DCS | 0 | 0 | 0
3.1.11 | No of DCS promoted as resource DCS | 0 | 0 | 0
3.1.13 | No of Kishan days will be organized | 0 | 0 | 0
3.1.14 | No of Cluster Adhibesan will be organized | 0 | 0 | 0
3.1.15 | No of VO have efficient equipment management system in place | 0 | 0 | 0
| Moong MP | 0 | 0 | 0
| No. of Katta for moong cultivation0 | 0 | 0 | 0
Atleast 5,000 Direct jobs created through Project facilitation and atleast 75% of them are getting sustained income
3.1.16 | No of youth identified - data base prepared | 2644 | 0 | 2644
3.1.17 | No of Youth Placed by direct placement | 10 | 0 | 10
3.1.18 | No of Youth Placed by service sector agency | 0 | 0 | 0
3.1.19 | No of JRP working | 3 | 0 | 3
Project Monitoring and Learning System established, including RLMIS, learning and experience sharing forums at different levels of Project management
3.1.20 | % of Cluster generating reports through MIS | 0 | 0 | 0
3.1.21 | No of SHG graded | 885 | 0 | 885
3.1.22 | No of VO rated | 74 | 0 | 74
3.1.23 | No of Case study generated ( Best Practice - Institution Program,Procurement, Financial Mgmt.) | 0 | 0 | 0
Result 4 | Project implementation procedures and agreed business standards are followed for at least 80% of project interventions at any point in time
4.2.1 | No of MOU signed between BPIU and Community Based Organisation | 70 | 0 | 70
4.2.2 | No of UC received within One month time of CIF release from CBOs | 46 | 0 | 46
4.2.3 | No of CBOs trained on Community Procurement | 2 | 0 | 2
4.2.4 | % of Community Cadre payment made in the Ist week of the month | 68 | 0 | 68
4.2.5 | No of VO submitting Receipt & payment on monthly basis | 35 | 0 | 35
4.2.6 | No of VO two months old procured establishment materials | 28 | 0 | 28
Note on B9: Anurag Kumar (MIS Exeucutive) Please mention in this field cluster wise no. of SHG.
Note on B17: Anurag Kumar (MIS Exeucutive) Please mention in this field cluster wise no. of VO.

## Basantpur
MPPR OF - Basantpur. Month - September. 2014
Sl. | DESCRIPTION OF PROGRAM | Cummalitive achievement Previous month | Cummalitive achievement in current month | Cummalative achievement
1 | No. of Panchayats | 9 | 0 | 9
2 | No of revenue villages to be covered | 45 | 0 | 45
3 | No of Village to be saturated (geographically) - certification from the VO | 27 | 0 | 27
Result-1 | Formation of self reliant and inclusive community institutions including SHGs, Village Organizations and Federations.
In-1.2 | Self managed self help groups (SHGs) established, covering at least 80% of the target households, 60% of formed SHGs into VO; and 40% of the formed VOs into BLF.
| Total SGSY groups in JEEViKA fold | 25 | 6 | 31 | Only Validate
1.2.1 | Total No of SHG formed (C1- …... , C2-…..., C3-………….) *** | 845 | 0 | 845
| TOTAL NO OF POOR MOBILISED | 10202 | 0 | 10202
| No. of SC | 3331 | 0 | 3331
| No. ST | 0 | 0 | 0
| No.EBC | 2323 | 0 | 2323
| No. OBC | 2491 | 0 | 2491
| No. Minority | 3508 | 0 | 3508
| General | 206 | 0 | 206
1.2.2 | No. of Village Organisation Formed (C1-25, C2- 22, C3- 14) *** | 60 | 0 | 60
1.2.3 | No. of 6 months old SHGs Part of Village Organisation | 590 | 0 | 590
| No. of CLF Formed | 1 | 0 | 1
| No. of one year old VO part of CLF | 20 | 0 | 20
| No. of VO Registered under Cooperative Society Act-1999 | 5 | 0 | 5
COMMUNITY CADRES - IB & CB
1.2.6 | Number of CM working | 100 | 0 | 100
1.2.7 | Number of VO Book Keepers working | 13 | 0 | 13
1.2.8 | Number of Internal CRPs - SHG Formation working | 64 | 0 | 64
1.2.9 | Number of Internal CRPs-VO formation working | 0 | 0 | 0
1.2.10 | Number of Internal CRPs -Master Trainer working | 0 | 0 | 0
| No. of TSC CRP identified/Trained | 0 | 0 | 0
In-1.3 | At least 75% of formed VOs accessed and managed project funds as per project processes at any point of time
1.3.1 | No of VOs having Bank Account | 50 | 1 | 51
1.3.2 | No of VO to manage Baalwaadi | 0 | 0 | 0
1.3.3 | No of VO to be promoted as Health & Nutrition center | 0 | 0 | 0
1.3.4 | Number of VO participating in HRF | 33 | 0 | 33
1.3.5 | No. of members benefitted in HRF | 135 | 7 | 142
1.3.6 | No of VO received funding for its Action Plan | 0 | 0 | 0
In-1.4
1.4.2 | No. of SHGs having Bank A/C | 702 | 25 | 727
1.4.3 | No of Bank Mitra working | 4 | 0 | 4
1.4.4 | No of eligible SHGs ( six month old SHG + following PANCHSUTRA ) financed by Banks | 483 | 80 | 563
1.4.5 | Amount Loaned by Banks to SHG | 24150000 | 4000000 | 28150000
1.4.6 | No of Groups repeat financed by Banks | 0 | 0 | 0
1.4.7 | Repeat financed Amount by Banks | 0 | 0 | 0
1.4.10 | No. of SHG members received bond under insurance programme. | 733 | 0 | 733
Result-2 | Establishment and use of Community Investment Fund for food security, social services, assets and income generation and service sector investment
2.1.1 | No of Group visited for Social plan | 0 | 0 | 0
2.1.2 | No of SHG members made signature literate | 4015 | 87 | 4102
2.1.3 | No of SHG made financial literate | 0 | 0 | 0
5 | No of SHG Member linked with RSBY - Health insurance | 2000 | 0 | 2000
2.1.5 | Sanitation Programme initiated with number of SHGs | 0 | 0 | 0
2.1.6 | No. of SHG HHs linked with Social Security Programme | 0 | 0 | 0
2.1.7 | No of Social Security Resource Person working | 0 | 0 | 0
2.1.8 | NO of Social Security community professional working | 0 | 0 | 0
2.1.9 | No of groups to complete Micro Planing exercise within 3 months of Group formation | 697 | 10 | 707
2.1.10 | No of Group Recd ICF through BPIU | 0 | 0 | 0
2.1.11 | No of Group Recd ICF through VO | 0 | 0 | 0
2.1.12 | Total No. of Groups received ICF through Vo/BPIU | 597 | 0 | 597
2.1.13 | No of groups/Farmers to complete Livelihoods Micro Planing exercise(SWI) | 100 | 0 | 100
2.1.14 | No of Group Revisited for Micro plan | 0 | 0 | 0
2.1.15 | No of trained CM generating Micro Plan | 11 | 0 | 11
Food security increased for 80% of target households as compared to the baseline
2.1.16 | Number of VO participating in FSF | 41 | 0 | 41
2.1.17 | No of HH linked with FS Intervention | 934 | 524 | 1458
Result - 3 | Establishment and operationalization of Technical Assistance Fund.
In- 3.1 | At least 5 major business linkages established through public/private partnership by CBOs
3.1.1 | No of SHG members registered in VO for SRI | 946 | 0 | 946
3.1.2 | No of SHG members registered in VO for SWI | 0 | 0 | 0
3.1.3 | No of Acres of land will be under Agriculture Intervention-SRI | 61 | 0 | 61
3.1.4 | No of Acres of land will be under Agriculture Intervention- SWI | 0 | 0 | 0
3.1.5 | No of vermi-compost pit will be prepared | 0 | 0 | 0
3.1.6 | No of VRP will work in the Agriculture Intervention | 24 | 2 | 26
3.1.7 | No of Skilled Extension Worker will be created in Agriculture Intervention | 0 | 0 | 0
3.1.8 | No of SHG members will be registered in existing DCS | 0 | 0 | 0
3.1.9 | No of New DCS formed | 0 | 0 | 0
3.1.10 | No of SHG members will be registered in new DCS | 0 | 0 | 0
3.1.11 | No of DCS promoted as resource DCS | 0 | 0 | 0
3.1.13 | No of Kishan days will be organized | 0 | 0 | 0
3.1.14 | No of Cluster Adhibesan will be organized | 0 | 0 | 0
3.1.15 | No of VO have efficient equipment management system in place | 0 | 0 | 0
| Moong MP | 0 | 0 | 0
| No. of Katta for moong cultivation0 | 0 | 0 | 0
Atleast 5,000 Direct jobs created through Project facilitation and atleast 75% of them are getting sustained income
3.1.16 | No of youth identified - data base prepared | 3136 | 0 | 3136
3.1.17 | No of Youth Placed by direct placement | 0 | 0 | 0
3.1.18 | No of Youth Placed by service sector agency | 0 | 0 | 0
3.1.19 | No of JRP working | 3 | 0 | 3
Project Monitoring and Learning System established, including RLMIS, learning and experience sharing forums at different levels of Project management
3.1.20 | % of Cluster generating reports through MIS | 95 | 0 | 95
3.1.21 | No of SHG graded | 697 | 10 | 707
3.1.22 | No of VO rated | 2 | 0 | 2
3.1.23 | No of Case study generated ( Best Practice - Institution Program,Procurement, Financial Mgmt.) | 6 | 0 | 6
Result 4 | Project implementation procedures and agreed business standards are followed for at least 80% of project interventions at any point in time
4.2.1 | No of MOU signed between BPIU and Community Based Organisation | 41 | 0 | 41
4.2.2 | No of UC received within One month time of CIF release from CBOs | 413 | 0 | 413
4.2.3 | No of CBOs trained on Community Procurement | 0 | 0 | 0
4.2.4 | % of Community Cadre payment made in the Ist week of the month | 0 | 0 | 0
4.2.5 | No of VO submitting Receipt & payment on monthly basis | 46 | 0 | 46
4.2.6 | No of VO two months old procured establishment materials | 23 | 0 | 23
Note on B9: Anurag Kumar (MIS Exeucutive) Please mention in this field cluster wise no. of SHG.
Note on B17: Anurag Kumar (MIS Exeucutive) Please mention in this field cluster wise no. of VO.

## Pratapganj
MPPR OF - Pratapganj . Month - September . 2014
Sl. | DESCRIPTION OF PROGRAM | Cummalitive achievement Previous month | Cummalitive achievement in current month | Cummalative achievement
1 | No. of Panchayats | 8 | 0 | 8
2 | No of revenue villages to be covered | 10 | 0 | 10
3 | No of Village to be saturated (geographically) - certification from the VO | 10 | 0 | 10
Result-1 | Formation of self reliant and inclusive community institutions including SHGs, Village Organizations and Federations.
In-1.2 | Self managed self help groups (SHGs) established, covering at least 80% of the target households, 60% of formed SHGs into VO; and 40% of the formed VOs into BLF.
| Total SGSY groups in JEEViKA fold | 46 | 1 | 47 | Only Validate
1.2.1 | Total No of SHG formed (C1- . . . . . . . . . . , C2- . . . . . . . . . . , C3- . . . . . . . . . . .) *** | 715 | 56 | 771
| TOTAL NO OF POOR MOBILISED | 8707 | 627 | 9334
| No. of SC | 1723 | 84 | 1807
| No. ST | 187 | 0 | 187
| No.EBC | 2597 | 354 | 2951
| No. OBC | 2777 | 109 | 2886
| No. Minority | 1144 | 79 | 1223
| General | 279 | 1 | 280
1.2.2 | No. of Village Organisation Formed (C1- . . . . . . . . . . , C2- . . . . . . . . . . , C3- . . . . . . . . . . .) | 54 | 0 | 54
1.2.3 | No. of 6 months old SHGs Part of Village Organisation | 638 | 0 | 638
| No. of CLF Formed | 2 | 0 | 2
| No. of one year old VO part of CLF | 33 | 0 | 33
| No. of VO Registered under Cooperative Society Act-1999 | 4 | 0 | 4
COMMUNITY CADRES - IB & CB
1.2.6 | Number of CM working | 81 | 3 | 84
1.2.7 | Number of VO Book Keepers working | 11 | 0 | 11
1.2.8 | Number of Internal CRPs - SHG Formation working | 93 | 35 | 128
1.2.9 | Number of Internal CRPs-VO formation working | 0 | 0 | 0
1.2.10 | Number of Internal CRPs -Master Trainer working | 0 | 0 | 0
| No. of TSC CRP identified/Trained | 0 | 0 | 0
In-1.3 | At least 75% of formed VOs accessed and managed project funds as per project processes at any point of time
1.3.1 | No of VOs having Bank Account | 48 | 3 | 51
1.3.2 | No of VO to manage Baalwaadi | 0 | 0 | 0
1.3.3 | No of VO to be promoted as Health & Nutrition center | 0 | 0 | 0
1.3.4 | Number of VO participating in HRF | 44 | 0 | 44
1.3.5 | No. of members benefitted in HRF | 73 | 5 | 78
1.3.6 | No of VO received funding for its Action Plan | 0 | 0 | 0
In-1.4
1.4.2 | No. of SHGs having Bank A/C | 616 | 8 | 624
1.4.3 | No of Bank Mitra working | 4 | 0 | 4
1.4.4 | No of eligible SHGs ( six month old SHG + following PANCHSUTRA ) financed by Banks | 471 | 59 | 530
1.4.5 | Amount Loaned by Banks to SHG | 23550000 | 2950000 | 26500000
1.4.6 | No of Groups repeat financed by Banks | 0 | 0 | 0
1.4.7 | Repeat financed Amount by Banks | 0 | 0 | 0
1.4.10 | No. of SHG members received bond under insurance programme. | 2754 | 0 | 2754
Result-2 | Establishment and use of Community Investment Fund for food security, social services, assets and income generation and service sector investment
2.1.1 | No of Group visited for Social plan | 36 | 0 | 36
2.1.2 | No of SHG members made signature literate | 5812 | 48 | 5860
2.1.3 | No of SHG made financial literate | 0 | 0 | 0
5 | No of SHG Member linked with RSBY - Health insurance | 1200 | 0 | 1200
2.1.5 | Sanitation Programme initiated with number of SHGs | 0 | 0 | 0
2.1.6 | No. of SHG HHs linked with Social Security Programme | 0 | 0 | 0
2.1.7 | No of Social Security Resource Person working | 0 | 0 | 0
2.1.8 | NO of Social Security community professional working | 0 | 0 | 0
2.1.9 | No of groups to complete Micro Planing exercise within 3 months of Group formation | 567 | 33 | 600
2.1.10 | No of Group Recd ICF through BPIU | 0 | 0 | 0
2.1.11 | No of Group Recd ICF through VO | 0 | 0 | 0
2.1.12 | Total No. of Groups received ICF through Vo/BPIU | 564 | 0 | 564
2.1.13 | No of groups/Farmers to complete Livelihoods Micro Planing exercise(SWI) | 0 | 0 | 0
2.1.14 | No of Group Revisited for Micro plan | 0 | 0 | 0
2.1.15 | No of trained CM generating Micro Plan | 0 | 0 | 0
Food security increased for 80% of target households as compared to the baseline
2.1.16 | Number of VO participating in FSF | 46 | 0 | 46
2.1.17 | No of HH linked with FS Intervention | 2717 | 206 | 2923
Result - 3 | Establishment and operationalization of Technical Assistance Fund.
In- 3.1 | At least 5 major business linkages established through public/private partnership by CBOs
3.1.1 | No of SHG members registered in VO for SRI | 4166 | 0 | 4166
3.1.2 | No of SHG members registered in VO for SWI | 718 | 0 | 718
3.1.3 | No of Acres of land will be under Agriculture Intervention-SRI | 5788 | 0 | 5788
3.1.4 | No of Acres of land will be under Agriculture Intervention- SWI | 2765 | 0 | 2765
3.1.5 | No of vermi-compost pit will be prepared | 1 | 0 | 1
3.1.6 | No of VRP will work in the Agriculture Intervention | 50 | 0 | 50
3.1.7 | No of Skilled Extension Worker will be created in Agriculture Intervention | 0 | 0 | 0
3.1.8 | No of SHG members will be registered in existing DCS | 0 | 0 | 0
3.1.9 | No of New DCS formed | 0 | 0 | 0
3.1.10 | No of SHG members will be registered in new DCS | 0 | 0 | 0
3.1.11 | No of DCS promoted as resource DCS | 0 | 0 | 0
3.1.13 | No of Kishan days will be organized | 0 | 0 | 0
3.1.14 | No of Cluster Adhibesan will be organized | 0 | 0 | 0
3.1.15 | No of VO have efficient equipment management system in place | 0 | 44 | 44
| Moong MP | 925 | 0 | 925
| No. of Katta for moong cultivation0 | 2593 | 0 | 2593
Atleast 5,000 Direct jobs created through Project facilitation and atleast 75% of them are getting sustained income
3.1.16 | No of youth identified - data base prepared | 3549 | 220 | 3769
3.1.17 | No of Youth Placed by direct placement | 5 | 10 | 15
3.1.18 | No of Youth Placed by service sector agency | 0 | 0 | 0
3.1.19 | No of JRP working | 3 | 0 | 3
Project Monitoring and Learning System established, including RLMIS, learning and experience sharing forums at different levels of Project management
3.1.20 | % of Cluster generating reports through MIS | 0 | 0 | 0
3.1.21 | No of SHG graded | 567 | 33 | 600
3.1.22 | No of VO rated | 0 | 0 | 0
3.1.23 | No of Case study generated ( Best Practice - Institution Program,Procurement, Financial Mgmt.) | 0 | 0 | 0
Result 4 | Project implementation procedures and agreed business standards are followed for at least 80% of project interventions at any point in time
4.2.1 | No of MOU signed between BPIU and Community Based Organisation | 46 | 0 | 46
4.2.2 | No of UC received within One month time of CIF release from CBOs | 461 | 12 | 473
4.2.3 | No of CBOs trained on Community Procurement | 44 | 0 | 44
4.2.4 | % of Community Cadre payment made in the Ist week of the month | 0 | 0 | 0
4.2.5 | No of VO submitting Receipt & payment on monthly basis | 45 | 0 | 45
4.2.6 | No of VO two months old procured establishment materials | 10 | 0 | 10
Note on B9: Anurag Kumar (MIS Exeucutive) Please mention in this field cluster wise no. of SHG.
Note on B17: Anurag Kumar (MIS Exeucutive) Please mention in this field cluster wise no. of VO.

## Chhatapur
MPPR OF - Chhatapur. Month - September -2014
Sl. | DESCRIPTION OF PROGRAM | Cummalitive achievement Previous month | Cummalitive achievement in current month | Cummalative achievement
1 | No. of Panchayats | 23 | 0 | 23
2 | No of revenue villages to be covered | 56 | 0 | 56
3 | No of Village to be saturated (geographically) - certification from the VO | 27 | 0 | 27
Result-1 | Formation of self reliant and inclusive community institutions including SHGs, Village Organizations and Federations.
In-1.2 | Self managed self help groups (SHGs) established, covering at least 80% of the target households, 60% of formed SHGs into VO; and 40% of the formed VOs into BLF.
| Total SGSY groups in JEEViKA fold | 0 | 0 | 0
1.2.1 | Total No of SHG formed (C1- . . . . . . . . , C2- . . . . . . . , C3- . . . . . . ) *** | 2032 | 14 | 2046
| TOTAL NO OF POOR MOBILISED | 24392 | 168 | 24560
| No. of SC | 6158 | 0 | 6158
| No. ST | 716 | 0 | 716
| No.EBC | 6987 | 0 | 6987
| No. OBC | 5866 | 0 | 5866
| No. Minority | 3152 | 0 | 3152
| General | 1513 | 0 | 1513
1.2.2 | No. of Village Organisation Formed (C1-54,C2-38,C3-54) *** | 154 | 0 | 154
1.2.3 | No. of 6 months old SHGs Part of Village Organisation | 1518 | 0 | 1518
| No. of CLF Formed | 3 | 0 | 3
| No. of one year old VO part of CLF | 52 | 0 | 52
| No. of VO Registered under Cooperative Society Act-1999 | 8 | 0 | 8
COMMUNITY CADRES - IB & CB
1.2.6 | Number of CM working | 207 | 0 | 207
1.2.7 | Number of VO Book Keepers working | 26 | 0 | 26
1.2.8 | Number of Internal CRPs - SHG Formation working | 122 | 0 | 122
1.2.9 | Number of Internal CRPs-VO formation working | 28 | 0 | 28
1.2.10 | Number of Internal CRPs -Master Trainer working | 37 | 0 | 37
| No. of TSC CRP identified/Trained | 0 | 0 | 0
In-1.3 | At least 75% of formed VOs accessed and managed project funds as per project processes at any point of time
1.3.1 | No of VOs having Bank Account | 142 | 0 | 142
1.3.2 | No of VO to manage Baalwaadi | 0 | 0 | 0
1.3.3 | No of VO to be promoted as Health & Nutrition center | 0 | 0 | 0
1.3.4 | Number of VO participating in HRF | 52 | 0 | 52
1.3.5 | No. of members benefitted in HRF | 414 | 0 | 414
1.3.6 | No of VO received funding for its Action Plan | 0 | 0 | 0
In-1.4
1.4.2 | No. of SHGs having Bank A/C | 1671 | 21 | 1692
1.4.3 | No of Bank Mitra working | 7 | 0 | 7
1.4.4 | No of eligible SHGs ( six month old SHG + following PANCHSUTRA ) financed by Banks | 1145 | 273 | 1418
1.4.5 | Amount Loaned by Banks to SHG | 57250000 | 13650000 | 70900000
1.4.6 | No of Groups repeat financed by Banks | 0 | 0 | 0
1.4.7 | Repeat financed Amount by Banks | 0 | 0 | 0
1.4.10 | No. of SHG members received bond under insurance programme. | 5378 | 0 | 5378
Result-2 | Establishment and use of Community Investment Fund for food security, social services, assets and income generation and service sector investment
2.1.1 | No of Group visited for Social plan | 0 | 0 | 0
2.1.2 | No of SHG members made signature literate | 13123 | 0 | 13123
2.1.3 | No of SHG made financial literate | 30 | 0 | 30
5 | No of SHG Member linked with RSBY - Health insurance | 1650 | 0 | 1650
2.1.5 | Sanitation Programme initiated with number of SHGs | 60 | 0 | 60
2.1.6 | No. of SHG HHs linked with Social Security Programme | 0 | 0 | 0
2.1.7 | No of Social Security Resource Person working | 0 | 0 | 0
2.1.8 | NO of Social Security community professional working | 0 | 0 | 0
2.1.9 | No of groups to complete Micro Planing exercise within 3 months of Group formation | 1538 | 0 | 1538
2.1.10 | No of Group Recd ICF through BPIU | 1365 | 0 | 1365
2.1.11 | No of Group Recd ICF through VO | 0 | 0 | 0
2.1.12 | Total No. of Groups received ICF through Vo/BPIU | 1365 | 0 | 1365
2.1.13 | No of groups/Farmers to complete Livelihoods Micro Planing exercise(SWI) | 1100 | 0 | 1100
2.1.14 | No of Group Revisited for Micro plan | 0 | 0 | 0
2.1.15 | No of trained CM generating Micro Plan | 40 | 0 | 40
Food security increased for 80% of target households as compared to the baseline
2.1.16 | Number of VO participating in FSF | 39 | 0 | 39
2.1.17 | No of HH linked with FS Intervention | 1796 | 0 | 1796
Result - 3 | Establishment and operationalization of Technical Assistance Fund.
In- 3.1 | At least 5 major business linkages established through public/private partnership by CBOs
3.1.1 | No of SHG members registered in VO for SRI | 2792 | 0 | 2792
3.1.2 | No of SHG members registered in VO for SWI | 0 | 0 | 0
3.1.3 | No of Acres of land will be under Agriculture Intervention-SRI | 371 | 0 | 371
3.1.4 | No of Acres of land will be under Agriculture Intervention- SWI | 0 | 0 | 0
3.1.5 | No of vermi-compost pit will be prepared | 2 | 0 | 2
3.1.6 | No of VRP will work in the Agriculture Intervention | 53 | 0 | 53
3.1.7 | No of Skilled Extension Worker will be created in Agriculture Intervention | 0 | 0 | 0
3.1.8 | No of SHG members will be registered in existing DCS | 0 | 0 | 0
3.1.9 | No of New DCS formed | 0 | 0 | 0
3.1.10 | No of SHG members will be registered in new DCS | 0 | 0 | 0
3.1.11 | No of DCS promoted as resource DCS | 0 | 0 | 0
3.1.13 | No of Kishan days will be organized | 0 | 0 | 0
3.1.14 | No of Cluster Adhibesan will be organized | 0 | 0 | 0
3.1.15 | No of VO have efficient equipment management system in place | 0 | 0 | 0
| Moong MP | 480 | 0 | 480
| No. of Katta for moong cultivation0 | 4705 | 0 | 4705
Atleast 5,000 Direct jobs created through Project facilitation and atleast 75% of them are getting sustained income
3.1.16 | No of youth identified - data base prepared | 600 | 0 | 600
3.1.17 | No of Youth Placed by direct placement | 40 | 0 | 40
3.1.18 | No of Youth Placed by service sector agency | 0 | 0 | 0
3.1.19 | No of JRP working | 1 | 0 | 1
Project Monitoring and Learning System established, including RLMIS, learning and experience sharing forums at different levels of Project management
3.1.20 | % of Cluster generating reports through MIS | 0 | 0 | 0
3.1.21 | No of SHG graded | 1508 | 0 | 1508
3.1.22 | No of VO rated | 59 | 0 | 59
3.1.23 | No of Case study generated ( Best Practice - Institution Program,Procurement, Financial Mgmt.) | 0 | 0 | 0
Result 4 | Project implementation procedures and agreed business standards are followed for at least 80% of project interventions at any point in time
4.2.1 | No of MOU signed between BPIU and Community Based Organisation | 71 | 0 | 71
4.2.2 | No of UC received within One month time of CIF release from CBOs | 514 | 0 | 514
4.2.3 | No of CBOs trained on Community Procurement | 45 | 0 | 45
4.2.4 | % of Community Cadre payment made in the Ist week of the month | 0 | 0 | 0
4.2.5 | No of VO submitting Receipt & payment on monthly basis | 132 | 0 | 132
4.2.6 | No of VO two months old procured establishment materials | 23 | 0 | 23
Note on B9: Anurag Kumar (MIS Exeucutive) Please mention in this field cluster wise no. of SHG.
Note on B17: Anurag Kumar (MIS Exeucutive) Please mention in this field cluster wise no. of VO.

## Supaul Sadar
MPPR OF -Supaul Sadar. Month - September 2014
Sl. | DESCRIPTION OF PROGRAM | Cummalitive achievement Previous month | Cummalitive achievement in current month | Cummalative achievement
1 | No. of Panchayats | 5 | 0 | 5
2 | No of revenue villages to be covered | 8 | 0 | 8
3 | No of Village to be saturated (geographically) - certification from the VO | 0 | 0 | 0
Result-1 | Formation of self reliant and inclusive community institutions including SHGs, Village Organizations and Federations.
In-1.2 | Self managed self help groups (SHGs) established, covering at least 80% of the target households, 60% of formed SHGs into VO; and 40% of the formed VOs into BLF.
| Total SGSY groups in JEEViKA fold | 25 | 0 | 25
1.2.1 | Total No of SHG formed (C1- . . . . . . . . . . , C2- . . . . . . . . . . , C3- . . . . . . . . . . .) *** | 102 | 0 | 102
| TOTAL NO OF POOR MOBILISED | 1048 | 0 | 1048
| No. of SC | 378 | 0 | 378
| No. ST | 0 | 0 | 0
| No.EBC | 521 | 0 | 521
| No. OBC | 103 | 0 | 103
| No. Minority | 32 | 0 | 32
| General | 14 | 0 | 14
1.2.2 | No. of Village Organisation Formed (C1- . . . . . . . . . . , C2- . . . . . . . . . . , C3- . . . . . . . . . . .) | 0 | 0 | 0
1.2.3 | No. of 6 months old SHGs Part of Village Organisation | 0 | 0 | 0
| No. of CLF Formed | 0 | 0 | 0
| No. of one year old VO part of CLF | 0 | 0 | 0
| No. of VO Registered under Cooperative Society Act-1999 | 0 | 0 | 0
COMMUNITY CADRES - IB & CB
1.2.6 | Number of CM working | 13 | 1 | 14
1.2.7 | Number of VO Book Keepers working | 0 | 0 | 0
1.2.8 | Number of Internal CRPs - SHG Formation working | 0 | 0 | 0
1.2.9 | Number of Internal CRPs-VO formation working | 0 | 0 | 0
1.2.10 | Number of Internal CRPs -Master Trainer working | 0 | 0 | 0
| No. of TSC CRP identified/Trained | 0 | 0 | 0
In-1.3 | At least 75% of formed VOs accessed and managed project funds as per project processes at any point of time
1.3.1 | No of VOs having Bank Account | 0 | 0 | 0
1.3.2 | No of VO to manage Baalwaadi | 0 | 0 | 0
1.3.3 | No of VO to be promoted as Health & Nutrition center | 0 | 0 | 0
1.3.4 | Number of VO participating in HRF | 0 | 0 | 0
1.3.5 | No. of members benefitted in HRF | 0 | 0 | 0
1.3.6 | No of VO received funding for its Action Plan | 0 | 0 | 0
In-1.4
1.4.2 | No. of SHGs having Bank A/C | 0 | 16 | 16
1.4.3 | No of Bank Mitra working | 0 | 0 | 0
1.4.4 | No of eligible SHGs ( six month old SHG + following PANCHSUTRA ) financed by Banks | 0 | 0 | 0
1.4.5 | Amount Loaned by Banks to SHG | 0 | 0 | 0
1.4.6 | No of Groups repeat financed by Banks | 0 | 0 | 0
1.4.7 | Repeat financed Amount by Banks | 0 | 0 | 0
1.4.10 | No. of SHG members received bond under insurance programme. | 0 | 0 | 0
Result-2 | Establishment and use of Community Investment Fund for food security, social services, assets and income generation and service sector investment
2.1.1 | No of Group visited for Social plan | 0 | 0 | 0
2.1.2 | No of SHG members made signature literate | 0 | 0 | 0
2.1.3 | No of SHG made financial literate | 0 | 0 | 0
5 | No of SHG Member linked with RSBY - Health insurance | 0 | 0 | 0
2.1.5 | Sanitation Programme initiated with number of SHGs | 0 | 0 | 0
2.1.6 | No. of SHG HHs linked with Social Security Programme | 0 | 0 | 0
2.1.7 | No of Social Security Resource Person working | 0 | 0 | 0
2.1.8 | NO of Social Security community professional working | 0 | 0 | 0
2.1.9 | No of groups to complete Micro Planing exercise within 3 months of Group formation | 0 | 0 | 0
2.1.10 | No of Group Recd ICF through BPIU | 0 | 0 | 0
2.1.11 | No of Group Recd ICF through VO | 0 | 0 | 0
2.1.12 | Total No. of Groups received ICF through Vo/BPIU | 0 | 0 | 0
2.1.13 | No of groups/Farmers to complete Livelihoods Micro Planing exercise(SWI) | 0 | 0 | 0
2.1.14 | No of Group Revisited for Micro plan | 0 | 0 | 0
2.1.15 | No of trained CM generating Micro Plan | 0 | 0 | 0
Food security increased for 80% of target households as compared to the baseline
2.1.16 | Number of VO participating in FSF | 0 | 0 | 0
2.1.17 | No of HH linked with FS Intervention | 0 | 0 | 0
Result - 3 | Establishment and operationalization of Technical Assistance Fund.
In- 3.1 | At least 5 major business linkages established through public/private partnership by CBOs
3.1.1 | No of SHG members registered in VO for SRI | 0 | 0 | 0
3.1.2 | No of SHG members registered in VO for SWI | 0 | 0 | 0
3.1.3 | No of Acres of land will be under Agriculture Intervention-SRI | 0 | 0 | 0
3.1.4 | No of Acres of land will be under Agriculture Intervention- SWI | 0 | 0 | 0
3.1.5 | No of vermi-compost pit will be prepared | 0 | 0 | 0
3.1.6 | No of VRP will work in the Agriculture Intervention | 0 | 0 | 0
3.1.7 | No of Skilled Extension Worker will be created in Agriculture Intervention | 0 | 0 | 0
3.1.8 | No of SHG members will be registered in existing DCS | 0 | 0 | 0
3.1.9 | No of New DCS formed | 0 | 0 | 0
3.1.10 | No of SHG members will be registered in new DCS | 0 | 0 | 0
3.1.11 | No of DCS promoted as resource DCS | 0 | 0 | 0
3.1.13 | No of Kishan days will be organized | 0 | 0 | 0
3.1.14 | No of Cluster Adhibesan will be organized | 0 | 0 | 0
3.1.15 | No of VO have efficient equipment management system in place | 0 | 0 | 0
| Moong MP | 0 | 0 | 0
| No. of Katta for moong cultivation0 | 0 | 0 | 0
Atleast 5,000 Direct jobs created through Project facilitation and atleast 75% of them are getting sustained income
3.1.16 | No of youth identified - data base prepared | 0 | 0 | 0
3.1.17 | No of Youth Placed by direct placement | 0 | 0 | 0
3.1.18 | No of Youth Placed by service sector agency | 0 | 0 | 0
3.1.19 | No of JRP working | 0 | 0 | 0
Project Monitoring and Learning System established, including RLMIS, learning and experience sharing forums at different levels of Project management
3.1.20 | % of Cluster generating reports through MIS | 0 | 0 | 0
3.1.21 | No of SHG graded | 0 | 0 | 0
3.1.22 | No of VO rated | 0 | 0 | 0
3.1.23 | No of Case study generated ( Best Practice - Institution Program,Procurement, Financial Mgmt.) | 0 | 0 | 0
Result 4 | Project implementation procedures and agreed business standards are followed for at least 80% of project interventions at any point in time
4.2.1 | No of MOU signed between BPIU and Community Based Organisation | 0 | 0 | 0
4.2.2 | No of UC received within One month time of CIF release from CBOs | 0 | 0 | 0
4.2.3 | No of CBOs trained on Community Procurement | 0 | 0 | 0
4.2.4 | % of Community Cadre payment made in the Ist week of the month | 0 | 0 | 0
4.2.5 | No of VO submitting Receipt & payment on monthly basis | 0 | 0 | 0
4.2.6 | No of VO two months old procured establishment materials | 0 | 0 | 0
Note on B9: Anurag Kumar (MIS Exeucutive) Please mention in this field cluster wise no. of SHG.
Note on B17: Anurag Kumar (MIS Exeucutive) Please mention in this field cluster wise no. of VO.

## Pipra
MPPR OF - Pipra Month - September 2014
Sl. | DESCRIPTION OF PROGRAM | Cummalitive achievement Previous month | Cummalitive achievement in current month | Cummalative achievement
1 | No. of Panchayats | 4 | 0 | 4
2 | No of revenue villages to be covered | 3 | 0 | 3
3 | No of Village to be saturated (geographically) - certification from the VO | 0 | 0 | 0
Result-1 | Formation of self reliant and inclusive community institutions including SHGs, Village Organizations and Federations.
In-1.2 | Self managed self help groups (SHGs) established, covering at least 80% of the target households, 60% of formed SHGs into VO; and 40% of the formed VOs into BLF.
| Total SGSY groups in JEEViKA fold | 0 | 0 | 0
1.2.1 | Total No of SHG formed (C1- . . . . . . . . . . , C2- . . . . . . . . . . , C3- . . . . . . . . . . .) *** | 140 | 14 | 154
| TOTAL NO OF POOR MOBILISED | 1655 | 210 | 1865
| No. of SC | 168 | 0 | 168
| No. ST | 0 | 0 | 0
| No.EBC | 50 | 0 | 50
| No. OBC | 370 | 0 | 370
| No. Minority | 12 | 0 | 12
| General | 0 | 0 | 0
1.2.2 | No. of Village Organisation Formed (C1- . . . . . . . . . . , C2- . . . . . . . . . . , C3- . . . . . . . . . . .) | 0 | 0 | 0
1.2.3 | No. of 6 months old SHGs Part of Village Organisation | 0 | 0 | 0
| No. of CLF Formed | 0 | 0 | 0
| No. of one year old VO part of CLF | 0 | 0 | 0
| No. of VO Registered under Cooperative Society Act-1999 | 0 | 0 | 0
COMMUNITY CADRES - IB & CB
1.2.6 | Number of CM working | 16 | 4 | 20
1.2.7 | Number of VO Book Keepers working | 0 | 0 | 0
1.2.8 | Number of Internal CRPs - SHG Formation working | 0 | 0 | 0
1.2.9 | Number of Internal CRPs-VO formation working | 0 | 0 | 0
1.2.10 | Number of Internal CRPs -Master Trainer working | 0 | 0 | 0
| No. of TSC CRP identified/Trained | 0 | 0 | 0
In-1.3 | At least 75% of formed VOs accessed and managed project funds as per project processes at any point of time
1.3.1 | No of VOs having Bank Account | 0 | 0 | 0
1.3.2 | No of VO to manage Baalwaadi | 0 | 0 | 0
1.3.3 | No of VO to be promoted as Health & Nutrition center | 0 | 0 | 0
1.3.4 | Number of VO participating in HRF | 0 | 0 | 0
1.3.5 | No. of members benefitted in HRF | 0 | 0 | 0
1.3.6 | No of VO received funding for its Action Plan | 0 | 0 | 0
In-1.4
1.4.2 | No. of SHGs having Bank A/C | 28 | 15 | 43
1.4.3 | No of Bank Mitra working | 1 | 0 | 1
1.4.4 | No of eligible SHGs ( six month old SHG + following PANCHSUTRA ) financed by Banks | 0 | 0 | 0
1.4.5 | Amount Loaned by Banks to SHG | 0 | 0 | 0
1.4.6 | No of Groups repeat financed by Banks | 0 | 0 | 0
1.4.7 | Repeat financed Amount by Banks | 0 | 0 | 0
1.4.10 | No. of SHG members received bond under insurance programme. | 0 | 0 | 0
Result-2 | Establishment and use of Community Investment Fund for food security, social services, assets and income generation and service sector investment
2.1.1 | No of Group visited for Social plan | 0 | 0 | 0
2.1.2 | No of SHG members made signature literate | 0 | 0 | 0
2.1.3 | No of SHG made financial literate | 0 | 0 | 0
5 | No of SHG Member linked with RSBY - Health insurance | 0 | 0 | 0
2.1.5 | Sanitation Programme initiated with number of SHGs | 0 | 0 | 0
2.1.6 | No. of SHG HHs linked with Social Security Programme | 0 | 0 | 0
2.1.7 | No of Social Security Resource Person working | 0 | 0 | 0
2.1.8 | NO of Social Security community professional working | 0 | 0 | 0
2.1.9 | No of groups to complete Micro Planing exercise within 3 months of Group formation | 0 | 0 | 0
2.1.10 | No of Group Recd ICF through BPIU | 0 | 19 | 19
2.1.11 | No of Group Recd ICF through VO | 0 | 0 | 0
2.1.12 | Total No. of Groups received ICF through Vo/BPIU | 0 | 19 | 19
2.1.13 | No of groups/Farmers to complete Livelihoods Micro Planing exercise(SWI) | 0 | 0 | 0
2.1.14 | No of Group Revisited for Micro plan | 0 | 0 | 0
2.1.15 | No of trained CM generating Micro Plan | 4 | 0 | 4
Food security increased for 80% of target households as compared to the baseline
2.1.16 | Number of VO participating in FSF | 0 | 0 | 0
2.1.17 | No of HH linked with FS Intervention | 0 | 0 | 0
Result - 3 | Establishment and operationalization of Technical Assistance Fund.
In- 3.1 | At least 5 major business linkages established through public/private partnership by CBOs
3.1.1 | No of SHG members registered in VO for SRI | 0 | 0 | 0
3.1.2 | No of SHG members registered in VO for SWI | 0 | 0 | 0
3.1.3 | No of Acres of land will be under Agriculture Intervention-SRI | 0 | 0 | 0
3.1.4 | No of Acres of land will be under Agriculture Intervention- SWI | 0 | 0 | 0
3.1.5 | No of vermi-compost pit will be prepared | 0 | 0 | 0
3.1.6 | No of VRP will work in the Agriculture Intervention | 0 | 0 | 0
3.1.7 | No of Skilled Extension Worker will be created in Agriculture Intervention | 0 | 0 | 0
3.1.8 | No of SHG members will be registered in existing DCS | 0 | 0 | 0
3.1.9 | No of New DCS formed | 0 | 0 | 0
3.1.10 | No of SHG members will be registered in new DCS | 0 | 0 | 0
3.1.11 | No of DCS promoted as resource DCS | 0 | 0 | 0
3.1.13 | No of Kishan days will be organized | 0 | 0 | 0
3.1.14 | No of Cluster Adhibesan will be organized | 0 | 0 | 0
3.1.15 | No of VO have efficient equipment management system in place | 0 | 0 | 0
| Moong MP | 0 | 0 | 0
| No. of Katta for moong cultivation0 | 0 | 0 | 0
Atleast 5,000 Direct jobs created through Project facilitation and atleast 75% of them are getting sustained income
3.1.16 | No of youth identified - data base prepared | 0 | 0 | 0
3.1.17 | No of Youth Placed by direct placement | 0 | 0 | 0
3.1.18 | No of Youth Placed by service sector agency | 0 | 0 | 0
3.1.19 | No of JRP working | 0 | 0 | 0
Project Monitoring and Learning System established, including RLMIS, learning and experience sharing forums at different levels of Project management
3.1.20 | % of Cluster generating reports through MIS | 0 | 0 | 0
3.1.21 | No of SHG graded | 0 | 0 | 0
3.1.22 | No of VO rated | 0 | 0 | 0
3.1.23 | No of Case study generated ( Best Practice - Institution Program,Procurement, Financial Mgmt.) | 0 | 0 | 0
Result 4 | Project implementation procedures and agreed business standards are followed for at least 80% of project interventions at any point in time
4.2.1 | No of MOU signed between BPIU and Community Based Organisation | 0 | 0 | 0
4.2.2 | No of UC received within One month time of CIF release from CBOs | 0 | 0 | 0
4.2.3 | No of CBOs trained on Community Procurement | 0 | 0 | 0
4.2.4 | % of Community Cadre payment made in the Ist week of the month | 0 | 0 | 0
4.2.5 | No of VO submitting Receipt & payment on monthly basis | 0 | 0 | 0
4.2.6 | No of VO two months old procured establishment materials | 0 | 0 | 0
Note on B9: Anurag Kumar (MIS Exeucutive) Please mention in this field cluster wise no. of SHG.
Note on B17: Anurag Kumar (MIS Exeucutive) Please mention in this field cluster wise no. of VO.

## Kisanpur
MPPR OF - Kisanpur, Month - September 2014
Sl. | DESCRIPTION OF PROGRAM | Cummalitive achievement Previous month | Cummalitive achievement in current month | Cummalative achievement
1 | No. of Panchayats | 3 | 1 | 4
2 | No of revenue villages to be covered | 8 | 2 | 10
3 | No of Village to be saturated (geographically) - certification from the VO | 0 | 0 | 0
Result-1 | Formation of self reliant and inclusive community institutions including SHGs, Village Organizations and Federations.
In-1.2 | Self managed self help groups (SHGs) established, covering at least 80% of the target households, 60% of formed SHGs into VO; and 40% of the formed VOs into BLF.
| Total SGSY groups in JEEViKA fold | 0 | 0 | 0
1.2.1 | Total No of SHG formed (C1- ……., C2- ………..., C3- . . . . .. . .) *** | 112 | 0 | 112
| TOTAL NO OF POOR MOBILISED | 1337 | 132 | 1469
| No. of SC | 0 | 0 | 0
| No. ST | 0 | 0 | 0
| No.EBC | 0 | 0 | 0
| No. OBC | 0 | 0 | 0
| No. Minority | 0 | 0 | 0
| General | 0 | 0 | 0
1.2.2 | No. of Village Organisation Formed (C1- . . . . . . . . . . , C2- . . . . . . . . . . , C3- . . . . . . . . . . .) | 0 | 0 | 0
1.2.3 | No. of 6 months old SHGs Part of Village Organisation | 0 | 0 | 0
| No. of CLF Formed | 0 | 0 | 0
| No. of one year old VO part of CLF | 0 | 0 | 0
| No. of VO Registered under Cooperative Society Act-1999 | 0 | 0 | 0
COMMUNITY CADRES - IB & CB
1.2.6 | Number of CM working | 11 | 0 | 11
1.2.7 | Number of VO Book Keepers working | 0 | 0 | 0
1.2.8 | Number of Internal CRPs - SHG Formation working | 0 | 0 | 0
1.2.9 | Number of Internal CRPs-VO formation working | 0 | 0 | 0
1.2.10 | Number of Internal CRPs -Master Trainer working | 0 | 0 | 0
| No. of TSC CRP identified/Trained | 9 | 2 | 11
In-1.3 | At least 75% of formed VOs accessed and managed project funds as per project processes at any point of time
1.3.1 | No of VOs having Bank Account | 0 | 0 | 0
1.3.2 | No of VO to manage Baalwaadi | 0 | 0 | 0
1.3.3 | No of VO to be promoted as Health & Nutrition center | 0 | 0 | 0
1.3.4 | Number of VO participating in HRF | 0 | 0 | 0
1.3.5 | No. of members benefitted in HRF | 0 | 0 | 0
1.3.6 | No of VO received funding for its Action Plan | 0 | 0 | 0
In-1.4
1.4.2 | No. of SHGs having Bank A/C | 0 | 0 | 0
1.4.3 | No of Bank Mitra working | 0 | 0 | 0
1.4.4 | No of eligible SHGs ( six month old SHG + following PANCHSUTRA ) financed by Banks | 0 | 0 | 0
1.4.5 | Amount Loaned by Banks to SHG | 0 | 0 | 0
1.4.6 | No of Groups repeat financed by Banks | 0 | 0 | 0
1.4.7 | Repeat financed Amount by Banks | 0 | 0 | 0
1.4.10 | No. of SHG members received bond under insurance programme. | 0 | 0 | 0
Result-2 | Establishment and use of Community Investment Fund for food security, social services, assets and income generation and service sector investment
2.1.1 | No of Group visited for Social plan | 0 | 5 | 5
2.1.2 | No of SHG members made signature literate | 20 | 20 | 40
2.1.3 | No of SHG made financial literate | 0 | 0 | 0
5 | No of SHG Member linked with RSBY - Health insurance | 0 | 0 | 0
2.1.5 | Sanitation Programme initiated with number of SHGs | 0 | 0 | 0
2.1.6 | No. of SHG HHs linked with Social Security Programme | 0 | 0 | 0
2.1.7 | No of Social Security Resource Person working | 0 | 0 | 0
2.1.8 | NO of Social Security community professional working | 0 | 0 | 0
2.1.9 | No of groups to complete Micro Planing exercise within 3 months of Group formation | 16 | 4 | 20
2.1.10 | No of Group Recd ICF through BPIU | 0 | 0 | 0
2.1.11 | No of Group Recd ICF through VO | 0 | 0 | 0
2.1.12 | Total No. of Groups received ICF through Vo/BPIU | 0 | 0 | 0
2.1.13 | No of groups/Farmers to complete Livelihoods Micro Planing exercise(SWI) | 0 | 0 | 0
2.1.14 | No of Group Revisited for Micro plan | 0 | 0 | 0
2.1.15 | No of trained CM generating Micro Plan | 0 | 0 | 0
Food security increased for 80% of target households as compared to the baseline
2.1.16 | Number of VO participating in FSF | 0 | 0 | 0
2.1.17 | No of HH linked with FS Intervention | 0 | 0 | 0
Result - 3 | Establishment and operationalization of Technical Assistance Fund.
In- 3.1 | At least 5 major business linkages established through public/private partnership by CBOs
3.1.1 | No of SHG members registered in VO for SRI | 0 | 0 | 0
3.1.2 | No of SHG members registered in VO for SWI | 0 | 0 | 0
3.1.3 | No of Acres of land will be under Agriculture Intervention-SRI | 0 | 0 | 0
3.1.4 | No of Acres of land will be under Agriculture Intervention- SWI | 0 | 0 | 0
3.1.5 | No of vermi-compost pit will be prepared | 0 | 0 | 0
3.1.6 | No of VRP will work in the Agriculture Intervention | 0 | 0 | 0
3.1.7 | No of Skilled Extension Worker will be created in Agriculture Intervention | 0 | 0 | 0
3.1.8 | No of SHG members will be registered in existing DCS | 0 | 0 | 0
3.1.9 | No of New DCS formed | 0 | 0 | 0
3.1.10 | No of SHG members will be registered in new DCS | 0 | 0 | 0
3.1.11 | No of DCS promoted as resource DCS | 0 | 0 | 0
3.1.13 | No of Kishan days will be organized | 0 | 0 | 0
3.1.14 | No of Cluster Adhibesan will be organized | 0 | 0 | 0
3.1.15 | No of VO have efficient equipment management system in place | 0 | 0 | 0
| Moong MP | 0 | 0 | 0
| No. of Katta for moong cultivation0 | 0 | 0 | 0
Atleast 5,000 Direct jobs created through Project facilitation and atleast 75% of them are getting sustained income
3.1.16 | No of youth identified - data base prepared | 0 | 0 | 0
3.1.17 | No of Youth Placed by direct placement | 0 | 0 | 0
3.1.18 | No of Youth Placed by service sector agency | 0 | 0 | 0
3.1.19 | No of JRP working | 0 | 0 | 0
Project Monitoring and Learning System established, including RLMIS, learning and experience sharing forums at different levels of Project management
3.1.20 | % of Cluster generating reports through MIS | 0 | 0 | 0
3.1.21 | No of SHG graded | 0 | 0 | 0
3.1.22 | No of VO rated | 0 | 0 | 0
3.1.23 | No of Case study generated ( Best Practice - Institution Program,Procurement, Financial Mgmt.) | 0 | 0 | 0
Result 4 | Project implementation procedures and agreed business standards are followed for at least 80% of project interventions at any point in time
4.2.1 | No of MOU signed between BPIU and Community Based Organisation | 0 | 0 | 0
4.2.2 | No of UC received within One month time of CIF release from CBOs | 0 | 0 | 0
4.2.3 | No of CBOs trained on Community Procurement | 0 | 0 | 0
4.2.4 | % of Community Cadre payment made in the Ist week of the month | 0 | 0 | 0
4.2.5 | No of VO submitting Receipt & payment on monthly basis | 0 | 0 | 0
4.2.6 | No of VO two months old procured establishment materials | 0 | 0 | 0
Note on B9: Anurag Kumar (MIS Exeucutive) Please mention in this field cluster wise no. of SHG.
Note on B17: Anurag Kumar (MIS Exeucutive) Please mention in this field cluster wise no. of VO.

## Raghopur
MPPR OF - Raghopur, Month -September 2014
Sl. | DESCRIPTION OF PROGRAM | Cummalitive achievement Previous month | Cummalitive achievement in current month | Cummalative achievement
1 | No. of Panchayats | 4 | 0 | 4
2 | No of revenue villages to be covered | 4 | 10 | 14
3 | No of Village to be saturated (geographically) - certification from the VO | 0 | 0 | 0
Result-1 | Formation of self reliant and inclusive community institutions including SHGs, Village Organizations and Federations.
In-1.2 | Self managed self help groups (SHGs) established, covering at least 80% of the target households, 60% of formed SHGs into VO; and 40% of the formed VOs into BLF.
| Total SGSY groups in JEEViKA fold | 24 | 9 | 33
1.2.1 | Total No of SHG formed (C1- . . . . . . . . . . , C2- . . . . . . . . . . , C3- …..) *** | 107 | 26 | 133
| TOTAL NO OF POOR MOBILISED | 1227 | 338 | 1565
| No. of SC | 550 | 99 | 649
| No. ST | 0 | 0 | 0
| No.EBC | 325 | 48 | 373
| No. OBC | 224 | 127 | 351
| No. Minority | 108 | 17 | 125
| General | 20 | 47 | 67
1.2.2 | No. of Village Organisation Formed (C1- . . . . . . . . . . , C2- . . . . . . . . . . , C3- . . . . . . . . . . .) | 0 | 0 | 0
1.2.3 | No. of 6 months old SHGs Part of Village Organisation | 0 | 0 | 0
| No. of CLF Formed | 0 | 0 | 0
| No. of one year old VO part of CLF | 0 | 0 | 0
| No. of VO Registered under Cooperative Society Act-1999 | 0 | 0 | 0
COMMUNITY CADRES - IB & CB
1.2.6 | Number of CM working | 17 | 0 | 17
1.2.7 | Number of VO Book Keepers working | 0 | 0 | 0
1.2.8 | Number of Internal CRPs - SHG Formation working | 0 | 0 | 0
1.2.9 | Number of Internal CRPs-VO formation working | 0 | 0 | 0
1.2.10 | Number of Internal CRPs -Master Trainer working | 0 | 0 | 0
| No. of TSC CRP identified/Trained | 0 | 0 | 0
In-1.3 | At least 75% of formed VOs accessed and managed project funds as per project processes at any point of time
1.3.1 | No of VOs having Bank Account | 0 | 0 | 0
1.3.2 | No of VO to manage Baalwaadi | 0 | 0 | 0
1.3.3 | No of VO to be promoted as Health & Nutrition center | 0 | 0 | 0
1.3.4 | Number of VO participating in HRF | 0 | 0 | 0
1.3.5 | No. of members benefitted in HRF | 0 | 0 | 0
1.3.6 | No of VO received funding for its Action Plan | 0 | 0 | 0
In-1.4
1.4.2 | No. of SHGs having Bank A/C | 5 | 26 | 31
1.4.3 | No of Bank Mitra working | 0 | 0 | 0
1.4.4 | No of eligible SHGs ( six month old SHG + following PANCHSUTRA ) financed by Banks | 0 | 0 | 0
1.4.5 | Amount Loaned by Banks to SHG | 0 | 0 | 0
1.4.6 | No of Groups repeat financed by Banks | 0 | 0 | 0
1.4.7 | Repeat financed Amount by Banks | 0 | 0 | 0
1.4.10 | No. of SHG members received bond under insurance programme. | 0 | 0 | 0
Result-2 | Establishment and use of Community Investment Fund for food security, social services, assets and income generation and service sector investment
2.1.1 | No of Group visited for Social plan | 0 | 0 | 0
2.1.2 | No of SHG members made signature literate | 155 | 31 | 186
2.1.3 | No of SHG made financial literate | 0 | 0 | 0
5 | No of SHG Member linked with RSBY - Health insurance | 0 | 0 | 0
2.1.5 | Sanitation Programme initiated with number of SHGs | 0 | 0 | 0
2.1.6 | No. of SHG HHs linked with Social Security Programme | 0 | 0 | 0
2.1.7 | No of Social Security Resource Person working | 0 | 0 | 0
2.1.8 | NO of Social Security community professional working | 0 | 0 | 0
2.1.9 | No of groups to complete Micro Planing exercise within 3 months of Group formation | 0 | 0 | 0
2.1.10 | No of Group Recd ICF through BPIU | 0 | 0 | 0
2.1.11 | No of Group Recd ICF through VO | 0 | 0 | 0
2.1.12 | Total No. of Groups received ICF through Vo/BPIU | 0 | 0 | 0
2.1.13 | No of groups/Farmers to complete Livelihoods Micro Planing exercise(SWI) | 0 | 0 | 0
2.1.14 | No of Group Revisited for Micro plan | 0 | 0 | 0
2.1.15 | No of trained CM generating Micro Plan | 0 | 0 | 0
Food security increased for 80% of target households as compared to the baseline
2.1.16 | Number of VO participating in FSF | 0 | 0 | 0
2.1.17 | No of HH linked with FS Intervention | 0 | 0 | 0
Result - 3 | Establishment and operationalization of Technical Assistance Fund.
In- 3.1 | At least 5 major business linkages established through public/private partnership by CBOs
3.1.1 | No of SHG members registered in VO for SRI | 0 | 0 | 0
3.1.2 | No of SHG members registered in VO for SWI | 0 | 0 | 0
3.1.3 | No of Acres of land will be under Agriculture Intervention-SRI | 0 | 0 | 0
3.1.4 | No of Acres of land will be under Agriculture Intervention- SWI | 0 | 0 | 0
3.1.5 | No of vermi-compost pit will be prepared | 0 | 0 | 0
3.1.6 | No of VRP will work in the Agriculture Intervention | 0 | 0 | 0
3.1.7 | No of Skilled Extension Worker will be created in Agriculture Intervention | 0 | 0 | 0
3.1.8 | No of SHG members will be registered in existing DCS | 0 | 0 | 0
3.1.9 | No of New DCS formed | 0 | 0 | 0
3.1.10 | No of SHG members will be registered in new DCS | 0 | 0 | 0
3.1.11 | No of DCS promoted as resource DCS | 0 | 0 | 0
3.1.13 | No of Kishan days will be organized | 0 | 0 | 0
3.1.14 | No of Cluster Adhibesan will be organized | 0 | 0 | 0
3.1.15 | No of VO have efficient equipment management system in place | 0 | 0 | 0
| Moong MP | 0 | 0 | 0
| No. of Katta for moong cultivation0 | 0 | 0 | 0
Atleast 5,000 Direct jobs created through Project facilitation and atleast 75% of them are getting sustained income
3.1.16 | No of youth identified - data base prepared | 0 | 0 | 0
3.1.17 | No of Youth Placed by direct placement | 0 | 0 | 0
3.1.18 | No of Youth Placed by service sector agency | 0 | 0 | 0
3.1.19 | No of JRP working | 0 | 0 | 0
Project Monitoring and Learning System established, including RLMIS, learning and experience sharing forums at different levels of Project management
3.1.20 | % of Cluster generating reports through MIS | 0 | 0 | 0
3.1.21 | No of SHG graded | 0 | 0 | 0
3.1.22 | No of VO rated | 0 | 0 | 0
3.1.23 | No of Case study generated ( Best Practice - Institution Program,Procurement, Financial Mgmt.) | 0 | 0 | 0
Result 4 | Project implementation procedures and agreed business standards are followed for at least 80% of project interventions at any point in time
4.2.1 | No of MOU signed between BPIU and Community Based Organisation | 0 | 0 | 0
4.2.2 | No of UC received within One month time of CIF release from CBOs | 0 | 0 | 0
4.2.3 | No of CBOs trained on Community Procurement | 0 | 0 | 0
4.2.4 | % of Community Cadre payment made in the Ist week of the month | 0 | 0 | 0
4.2.5 | No of VO submitting Receipt & payment on monthly basis | 0 | 0 | 0
4.2.6 | No of VO two months old procured establishment materials | 0 | 0 | 0
Note on B9: Anurag Kumar (MIS Exeucutive) Please mention in this field cluster wise no. of SHG.
Note on B17: Anurag Kumar (MIS Exeucutive) Please mention in this field cluster wise no. of VO.

## Nirmali
MPPR OF - Nirmali , Month - September 2014
Sl. | DESCRIPTION OF PROGRAM | Cummalitive achievement Previous month | Cummalitive achievement in current month | Cummalative achievement
1 | No. of Panchayats | 4 | 0 | 4
2 | No of revenue villages to be covered | 7 | 0 | 7
3 | No of Village to be saturated (geographically) - certification from the VO | 0 | 0 | 0
Result-1 | Formation of self reliant and inclusive community institutions including SHGs, Village Organizations and Federations.
In-1.2 | Self managed self help groups (SHGs) established, covering at least 80% of the target households, 60% of formed SHGs into VO; and 40% of the formed VOs into BLF.
| Total SGSY groups in JEEViKA fold | 2 | 0 | 2
1.2.1 | Total No of SHG formed (C1- ……. , C2- . . . . . . . . . . , C3- . . . . . . . . . . .) *** | 96 | 15 | 111
| TOTAL NO OF POOR MOBILISED | 1056 | 130 | 1186
| No. of SC | 30 | 0 | 30
| No. ST | 0 | 0 | 0
| No.EBC | 130 | 0 | 130
| No. OBC | 0 | 0 | 0
| No. Minority | 0 | 0 | 0
| General | 0 | 0 | 0
1.2.2 | No. of Village Organisation Formed (C1- . . . . . . . . . . , C2- . . . . . . . . . . , C3- . . . . . . . . . . .) | 0 | 0 | 0
1.2.3 | No. of 6 months old SHGs Part of Village Organisation | 0 | 0 | 0
| No. of CLF Formed | 0 | 0 | 0
| No. of one year old VO part of CLF | 0 | 0 | 0
| No. of VO Registered under Cooperative Society Act-1999 | 0 | 0 | 0
COMMUNITY CADRES - IB & CB
1.2.6 | Number of CM working | 14 | 1 | 15
1.2.7 | Number of VO Book Keepers working | 0 | 0 | 0
1.2.8 | Number of Internal CRPs - SHG Formation working | 0 | 0 | 0
1.2.9 | Number of Internal CRPs-VO formation working | 0 | 0 | 0
1.2.10 | Number of Internal CRPs -Master Trainer working | 0 | 0 | 0
| No. of TSC CRP identified/Trained | 0 | 0 | 0
In-1.3 | At least 75% of formed VOs accessed and managed project funds as per project processes at any point of time
1.3.1 | No of VOs having Bank Account | 0 | 0 | 0
1.3.2 | No of VO to manage Baalwaadi | 0 | 0 | 0
1.3.3 | No of VO to be promoted as Health & Nutrition center | 0 | 0 | 0
1.3.4 | Number of VO participating in HRF | 0 | 0 | 0
1.3.5 | No. of members benefitted in HRF | 0 | 0 | 0
1.3.6 | No of VO received funding for its Action Plan | 0 | 0 | 0
In-1.4
1.4.2 | No. of SHGs having Bank A/C | 23 | 11 | 34
1.4.3 | No of Bank Mitra working | 0 | 0 | 0
1.4.4 | No of eligible SHGs ( six month old SHG + following PANCHSUTRA ) financed by Banks | 0 | 0 | 0
1.4.5 | Amount Loaned by Banks to SHG | 0 | 0 | 0
1.4.6 | No of Groups repeat financed by Banks | 0 | 0 | 0
1.4.7 | Repeat financed Amount by Banks | 0 | 0 | 0
1.4.10 | No. of SHG members received bond under insurance programme. | 0 | 0 | 0
Result-2 | Establishment and use of Community Investment Fund for food security, social services, assets and income generation and service sector investment
2.1.1 | No of Group visited for Social plan | 0 | 0 | 0
2.1.2 | No of SHG members made signature literate | 0 | 0 | 0
2.1.3 | No of SHG made financial literate | 0 | 0 | 0
5 | No of SHG Member linked with RSBY - Health insurance | 0 | 0 | 0
2.1.5 | Sanitation Programme initiated with number of SHGs | 0 | 0 | 0
2.1.6 | No. of SHG HHs linked with Social Security Programme | 0 | 0 | 0
2.1.7 | No of Social Security Resource Person working | 0 | 0 | 0
2.1.8 | NO of Social Security community professional working | 0 | 0 | 0
2.1.9 | No of groups to complete Micro Planing exercise within 3 months of Group formation | 0 | 0 | 0
2.1.10 | No of Group Recd ICF through BPIU | 0 | 0 | 0
2.1.11 | No of Group Recd ICF through VO | 0 | 0 | 0
2.1.12 | Total No. of Groups received ICF through Vo/BPIU | 0 | 0 | 0
2.1.13 | No of groups/Farmers to complete Livelihoods Micro Planing exercise(SWI) | 0 | 0 | 0
2.1.14 | No of Group Revisited for Micro plan | 0 | 0 | 0
2.1.15 | No of trained CM generating Micro Plan | 0 | 0 | 0
Food security increased for 80% of target households as compared to the baseline
2.1.16 | Number of VO participating in FSF | 0 | 0 | 0
2.1.17 | No of HH linked with FS Intervention | 0 | 0 | 0
Result - 3 | Establishment and operationalization of Technical Assistance Fund.
In- 3.1 | At least 5 major business linkages established through public/private partnership by CBOs
3.1.1 | No of SHG members registered in VO for SRI | 0 | 0 | 0
3.1.2 | No of SHG members registered in VO for SWI | 0 | 0 | 0
3.1.3 | No of Acres of land will be under Agriculture Intervention-SRI | 0 | 0 | 0
3.1.4 | No of Acres of land will be under Agriculture Intervention- SWI | 0 | 0 | 0
3.1.5 | No of vermi-compost pit will be prepared | 0 | 0 | 0
3.1.6 | No of VRP will work in the Agriculture Intervention | 0 | 0 | 0
3.1.7 | No of Skilled Extension Worker will be created in Agriculture Intervention | 0 | 0 | 0
3.1.8 | No of SHG members will be registered in existing DCS | 0 | 0 | 0
3.1.9 | No of New DCS formed | 0 | 0 | 0
3.1.10 | No of SHG members will be registered in new DCS | 0 | 0 | 0
3.1.11 | No of DCS promoted as resource DCS | 0 | 0 | 0
3.1.13 | No of Kishan days will be organized | 0 | 0 | 0
3.1.14 | No of Cluster Adhibesan will be organized | 0 | 0 | 0
3.1.15 | No of VO have efficient equipment management system in place | 0 | 0 | 0
| Moong MP | 0 | 0 | 0
| No. of Katta for moong cultivation0 | 0 | 0 | 0
Atleast 5,000 Direct jobs created through Project facilitation and atleast 75% of them are getting sustained income
3.1.16 | No of youth identified - data base prepared | 0 | 0 | 0
3.1.17 | No of Youth Placed by direct placement | 0 | 0 | 0
3.1.18 | No of Youth Placed by service sector agency | 0 | 0 | 0
3.1.19 | No of JRP working | 0 | 0 | 0
Project Monitoring and Learning System established, including RLMIS, learning and experience sharing forums at different levels of Project management
3.1.20 | % of Cluster generating reports through MIS | 0 | 0 | 0
3.1.21 | No of SHG graded | 0 | 0 | 0
3.1.22 | No of VO rated | 0 | 0 | 0
3.1.23 | No of Case study generated ( Best Practice - Institution Program,Procurement, Financial Mgmt.) | 0 | 0 | 0
Result 4 | Project implementation procedures and agreed business standards are followed for at least 80% of project interventions at any point in time
4.2.1 | No of MOU signed between BPIU and Community Based Organisation | 0 | 0 | 0
4.2.2 | No of UC received within One month time of CIF release from CBOs | 0 | 0 | 0
4.2.3 | No of CBOs trained on Community Procurement | 0 | 0 | 0
4.2.4 | % of Community Cadre payment made in the Ist week of the month | 0 | 0 | 0
4.2.5 | No of VO submitting Receipt & payment on monthly basis | 0 | 0 | 0
4.2.6 | No of VO two months old procured establishment materials | 0 | 0 | 0
Note on B9: Anurag Kumar (MIS Exeucutive) Please mention in this field cluster wise no. of SHG.
Note on B17: Anurag Kumar (MIS Exeucutive) Please mention in this field cluster wise no. of VO.

## Marauna
MPPR OF - Marauna, Month - September 2014
Sl. | DESCRIPTION OF PROGRAM | Cummalitive achievement Previous month | Cummalitive achievement in current month | Cummalative achievement
1 | No. of Panchayats | 4 | 0 | 4
2 | No of revenue villages to be covered | 13 | 0 | 13
3 | No of Village to be saturated (geographically) - certification from the VO | 0 | 0 | 0
Result-1 | Formation of self reliant and inclusive community institutions including SHGs, Village Organizations and Federations.
In-1.2 | Self managed self help groups (SHGs) established, covering at least 80% of the target households, 60% of formed SHGs into VO; and 40% of the formed VOs into BLF.
| Total SGSY groups in JEEViKA fold | 22 | 0 | 22
1.2.1 | Total No of SHG formed (C1- …………….. , C2- . . . . . . . . . . , C3- . . . . . . . . . . .) *** | 125 | 21 | 146
| TOTAL NO OF POOR MOBILISED | 1479 | 90 | 1569
| No. of SC | 360 | 10 | 370
| No. ST | 0 | 0 | 0
| No.EBC | 687 | 20 | 707
| No. OBC | 363 | 40 | 403
| No. Minority | 68 | 10 | 78
| General | 4 | 2 | 6
1.2.2 | No. of Village Organisation Formed (C1- . . . . . . . . . . , C2- . . . . . . . . . . , C3- . . . . . . . . . . .) | 0 | 0 | 0
1.2.3 | No. of 6 months old SHGs Part of Village Organisation | 0 | 0 | 0
| No. of CLF Formed | 0 | 0 | 0
| No. of one year old VO part of CLF | 0 | 0 | 0
| No. of VO Registered under Cooperative Society Act-1999 | 0 | 0 | 0
COMMUNITY CADRES - IB & CB
1.2.6 | Number of CM working | 15 | 9 | 24
1.2.7 | Number of VO Book Keepers working | 0 | 0 | 0
1.2.8 | Number of Internal CRPs - SHG Formation working | 0 | 0 | 0
1.2.9 | Number of Internal CRPs-VO formation working | 0 | 0 | 0
1.2.10 | Number of Internal CRPs -Master Trainer working | 0 | 0 | 0
| No. of TSC CRP identified/Trained | 0 | 0 | 0
In-1.3 | At least 75% of formed VOs accessed and managed project funds as per project processes at any point of time
1.3.1 | No of VOs having Bank Account | 0 | 0 | 0
1.3.2 | No of VO to manage Baalwaadi | 0 | 0 | 0
1.3.3 | No of VO to be promoted as Health & Nutrition center | 0 | 0 | 0
1.3.4 | Number of VO participating in HRF | 0 | 0 | 0
1.3.5 | No. of members benefitted in HRF | 0 | 0 | 0
1.3.6 | No of VO received funding for its Action Plan | 0 | 0 | 0
In-1.4
1.4.2 | No. of SHGs having Bank A/C | 62 | 5 | 67
1.4.3 | No of Bank Mitra working | 0 | 0 | 0
1.4.4 | No of eligible SHGs ( six month old SHG + following PANCHSUTRA ) financed by Banks | 0 | 0 | 0
1.4.5 | Amount Loaned by Banks to SHG | 0 | 0 | 0
1.4.6 | No of Groups repeat financed by Banks | 0 | 0 | 0
1.4.7 | Repeat financed Amount by Banks | 0 | 0 | 0
1.4.10 | No. of SHG members received bond under insurance programme. | 0 | 0 | 0
Result-2 | Establishment and use of Community Investment Fund for food security, social services, assets and income generation and service sector investment
2.1.1 | No of Group visited for Social plan | 0 | 0 | 0
2.1.2 | No of SHG members made signature literate | 279 | 30 | 309
2.1.3 | No of SHG made financial literate | 0 | 0 | 0
5 | No of SHG Member linked with RSBY - Health insurance | 0 | 0 | 0
2.1.5 | Sanitation Programme initiated with number of SHGs | 0 | 0 | 0
2.1.6 | No. of SHG HHs linked with Social Security Programme | 0 | 0 | 0
2.1.7 | No of Social Security Resource Person working | 0 | 0 | 0
2.1.8 | NO of Social Security community professional working | 0 | 0 | 0
2.1.9 | No of groups to complete Micro Planing exercise within 3 months of Group formation | 0 | 0 | 0
2.1.10 | No of Group Recd ICF through BPIU | 0 | 0 | 0
2.1.11 | No of Group Recd ICF through VO | 0 | 0 | 0
2.1.12 | Total No. of Groups received ICF through Vo/BPIU | 0 | 0 | 0
2.1.13 | No of groups/Farmers to complete Livelihoods Micro Planing exercise(SWI) | 0 | 0 | 0
2.1.14 | No of Group Revisited for Micro plan | 0 | 0 | 0
2.1.15 | No of trained CM generating Micro Plan | 0 | 0 | 0
Food security increased for 80% of target households as compared to the baseline
2.1.16 | Number of VO participating in FSF | 0 | 0 | 0
2.1.17 | No of HH linked with FS Intervention | 0 | 0 | 0
Result - 3 | Establishment and operationalization of Technical Assistance Fund.
In- 3.1 | At least 5 major business linkages established through public/private partnership by CBOs
3.1.1 | No of SHG members registered in VO for SRI | 0 | 0 | 0
3.1.2 | No of SHG members registered in VO for SWI | 0 | 0 | 0
3.1.3 | No of Acres of land will be under Agriculture Intervention-SRI | 0 | 0 | 0
3.1.4 | No of Acres of land will be under Agriculture Intervention- SWI | 0 | 0 | 0
3.1.5 | No of vermi-compost pit will be prepared | 0 | 0 | 0
3.1.6 | No of VRP will work in the Agriculture Intervention | 0 | 0 | 0
3.1.7 | No of Skilled Extension Worker will be created in Agriculture Intervention | 0 | 0 | 0
3.1.8 | No of SHG members will be registered in existing DCS | 0 | 0 | 0
3.1.9 | No of New DCS formed | 0 | 0 | 0
3.1.10 | No of SHG members will be registered in new DCS | 0 | 0 | 0
3.1.11 | No of DCS promoted as resource DCS | 0 | 0 | 0
3.1.13 | No of Kishan days will be organized | 0 | 0 | 0
3.1.14 | No of Cluster Adhibesan will be organized | 0 | 0 | 0
3.1.15 | No of VO have efficient equipment management system in place | 0 | 0 | 0
| Moong MP | 0 | 0 | 0
| No. of Katta for moong cultivation0 | 0 | 0 | 0
Atleast 5,000 Direct jobs created through Project facilitation and atleast 75% of them are getting sustained income
3.1.16 | No of youth identified - data base prepared | 0 | 0 | 0
3.1.17 | No of Youth Placed by direct placement | 0 | 0 | 0
3.1.18 | No of Youth Placed by service sector agency | 0 | 0 | 0
3.1.19 | No of JRP working | 0 | 0 | 0
Project Monitoring and Learning System established, including RLMIS, learning and experience sharing forums at different levels of Project management
3.1.20 | % of Cluster generating reports through MIS | 0 | 0 | 0
3.1.21 | No of SHG graded | 0 | 0 | 0
3.1.22 | No of VO rated | 0 | 0 | 0
3.1.23 | No of Case study generated ( Best Practice - Institution Program,Procurement, Financial Mgmt.) | 0 | 0 | 0
Result 4 | Project implementation procedures and agreed business standards are followed for at least 80% of project interventions at any point in time
4.2.1 | No of MOU signed between BPIU and Community Based Organisation | 0 | 0 | 0
4.2.2 | No of UC received within One month time of CIF release from CBOs | 0 | 0 | 0
4.2.3 | No of CBOs trained on Community Procurement | 0 | 0 | 0
4.2.4 | % of Community Cadre payment made in the Ist week of the month | 0 | 0 | 0
4.2.5 | No of VO submitting Receipt & payment on monthly basis | 0 | 0 | 0
4.2.6 | No of VO two months old procured establishment materials | 0 | 0 | 0
Note on B9: Anurag Kumar (MIS Exeucutive) Please mention in this field cluster wise no. of SHG.
Note on B17: Anurag Kumar (MIS Exeucutive) Please mention in this field cluster wise no. of VO.

## Saraigadh Bhaptihai
MPPR OF - Saraigadh, Month - September 2014
Sl. | DESCRIPTION OF PROGRAM | Cummalitive achievement Previous month | Cummalitive achievement in current month | Cummalative achievement
1 | No. of Panchayats | 4 | 0 | 4
2 | No of revenue villages to be covered | 8 | 2 | 10
3 | No of Village to be saturated (geographically) - certification from the VO | 0 | 0 | 0
Result-1 | Formation of self reliant and inclusive community institutions including SHGs, Village Organizations and Federations.
In-1.2 | Self managed self help groups (SHGs) established, covering at least 80% of the target households, 60% of formed SHGs into VO; and 40% of the formed VOs into BLF.
| Total SGSY groups in JEEViKA fold | 21 | 0 | 21
1.2.1 | Total No of SHG formed (C1- . . . . . . . . . . , C2- . . . . . . . . . . , C3- . . . . . . . . . . .) *** | 127 | 14 | 141
| TOTAL NO OF POOR MOBILISED | 1529 | 223 | 1752
| No. of SC | 316 | 60 | 376
| No. ST | 0 | 0 | 0
| No.EBC | 429 | 20 | 449
| No. OBC | 662 | 88 | 750
| No. Minority | 128 | 0 | 128
| General | 49 | 0 | 49
1.2.2 | No. of Village Organisation Formed (C1- . . . . . . . . . . , C2- . . . . . . . . . . , C3- . . . . . . . . . . .) | 0 | 1 | 1
1.2.3 | No. of 6 months old SHGs Part of Village Organisation | 0 | 8 | 8
| No. of CLF Formed | 0 | 0 | 0
| No. of one year old VO part of CLF | 0 | 0 | 0
| No. of VO Registered under Cooperative Society Act-1999 | 0 | 0 | 0
COMMUNITY CADRES - IB & CB
1.2.6 | Number of CM working | 16 | 2 | 18
1.2.7 | Number of VO Book Keepers working | 0 | 0 | 0
1.2.8 | Number of Internal CRPs - SHG Formation working | 0 | 0 | 0
1.2.9 | Number of Internal CRPs-VO formation working | 0 | 0 | 0
1.2.10 | Number of Internal CRPs -Master Trainer working | 0 | 0 | 0
| No. of TSC CRP identified/Trained | 0 | 0 | 0
In-1.3 | At least 75% of formed VOs accessed and managed project funds as per project processes at any point of time
1.3.1 | No of VOs having Bank Account | 0 | 0 | 0
1.3.2 | No of VO to manage Baalwaadi | 0 | 0 | 0
1.3.3 | No of VO to be promoted as Health & Nutrition center | 0 | 0 | 0
1.3.4 | Number of VO participating in HRF | 0 | 0 | 0
1.3.5 | No. of members benefitted in HRF | 0 | 0 | 0
1.3.6 | No of VO received funding for its Action Plan | 0 | 0 | 0
In-1.4
1.4.2 | No. of SHGs having Bank A/C | 20 | 13 | 33
1.4.3 | No of Bank Mitra working | 0 | 0 | 0
1.4.4 | No of eligible SHGs ( six month old SHG + following PANCHSUTRA ) financed by Banks | 0 | 0 | 0
1.4.5 | Amount Loaned by Banks to SHG | 0 | 0 | 0
1.4.6 | No of Groups repeat financed by Banks | 0 | 0 | 0
1.4.7 | Repeat financed Amount by Banks | 0 | 0 | 0
1.4.10 | No. of SHG members received bond under insurance programme. | 0 | 0 | 0
Result-2 | Establishment and use of Community Investment Fund for food security, social services, assets and income generation and service sector investment
2.1.1 | No of Group visited for Social plan | 0 | 0 | 0
2.1.2 | No of SHG members made signature literate | 26 | 10 | 36
2.1.3 | No of SHG made financial literate | 0 | 0 | 0
5 | No of SHG Member linked with RSBY - Health insurance | 0 | 0 | 0
2.1.5 | Sanitation Programme initiated with number of SHGs | 0 | 0 | 0
2.1.6 | No. of SHG HHs linked with Social Security Programme | 0 | 0 | 0
2.1.7 | No of Social Security Resource Person working | 0 | 0 | 0
2.1.8 | NO of Social Security community professional working | 0 | 0 | 0
2.1.9 | No of groups to complete Micro Planing exercise within 3 months of Group formation | 7 | 8 | 15
2.1.10 | No of Group Recd ICF through BPIU | 0 | 0 | 0
2.1.11 | No of Group Recd ICF through VO | 0 | 0 | 0
2.1.12 | Total No. of Groups received ICF through Vo/BPIU | 0 | 0 | 0
2.1.13 | No of groups/Farmers to complete Livelihoods Micro Planing exercise(SWI) | 0 | 0 | 0
2.1.14 | No of Group Revisited for Micro plan | 12 | 0 | 12
2.1.15 | No of trained CM generating Micro Plan | 0 | 1 | 1
Food security increased for 80% of target households as compared to the baseline
2.1.16 | Number of VO participating in FSF | 0 | 0 | 0
2.1.17 | No of HH linked with FS Intervention | 0 | 0 | 0
Result - 3 | Establishment and operationalization of Technical Assistance Fund.
In- 3.1 | At least 5 major business linkages established through public/private partnership by CBOs
3.1.1 | No of SHG members registered in VO for SRI | 0 | 0 | 0
3.1.2 | No of SHG members registered in VO for SWI | 0 | 0 | 0
3.1.3 | No of Acres of land will be under Agriculture Intervention-SRI | 0 | 0 | 0
3.1.4 | No of Acres of land will be under Agriculture Intervention- SWI | 0 | 0 | 0
3.1.5 | No of vermi-compost pit will be prepared | 0 | 0 | 0
3.1.6 | No of VRP will work in the Agriculture Intervention | 0 | 0 | 0
3.1.7 | No of Skilled Extension Worker will be created in Agriculture Intervention | 0 | 0 | 0
3.1.8 | No of SHG members will be registered in existing DCS | 0 | 0 | 0
3.1.9 | No of New DCS formed | 0 | 0 | 0
3.1.10 | No of SHG members will be registered in new DCS | 0 | 0 | 0
3.1.11 | No of DCS promoted as resource DCS | 0 | 0 | 0
3.1.13 | No of Kishan days will be organized | 0 | 0 | 0
3.1.14 | No of Cluster Adhibesan will be organized | 0 | 0 | 0
3.1.15 | No of VO have efficient equipment management system in place | 0 | 0 | 0
| Moong MP | 0 | 0 | 0
| No. of Katta for moong cultivation0 | 0 | 0 | 0
Atleast 5,000 Direct jobs created through Project facilitation and atleast 75% of them are getting sustained income
3.1.16 | No of youth identified - data base prepared | 0 | 0 | 0
3.1.17 | No of Youth Placed by direct placement | 0 | 0 | 0
3.1.18 | No of Youth Placed by service sector agency | 0 | 0 | 0
3.1.19 | No of JRP working | 0 | 0 | 0
Project Monitoring and Learning System established, including RLMIS, learning and experience sharing forums at different levels of Project management
3.1.20 | % of Cluster generating reports through MIS | 0 | 0 | 0
3.1.21 | No of SHG graded | 0 | 0 | 0
3.1.22 | No of VO rated | 0 | 0 | 0
3.1.23 | No of Case study generated ( Best Practice - Institution Program,Procurement, Financial Mgmt.) | 0 | 0 | 0
Result 4 | Project implementation procedures and agreed business standards are followed for at least 80% of project interventions at any point in time
4.2.1 | No of MOU signed between BPIU and Community Based Organisation | 0 | 0 | 0
4.2.2 | No of UC received within One month time of CIF release from CBOs | 0 | 0 | 0
4.2.3 | No of CBOs trained on Community Procurement | 0 | 0 | 0
4.2.4 | % of Community Cadre payment made in the Ist week of the month | 85 | 0 | 85
4.2.5 | No of VO submitting Receipt & payment on monthly basis | 0 | 0 | 0
4.2.6 | No of VO two months old procured establishment materials | 0 | 0 | 0
Note on B9: Anurag Kumar (MIS Exeucutive) Please mention in this field cluster wise no. of SHG.
Note on B17: Anurag Kumar (MIS Exeucutive) Please mention in this field cluster wise no. of VO.

## SUPAUL
MPPR OF DPCU- Supaul , Month -September 2014
Sl. | DESCRIPTION OF PROGRAM | Cummalitive achievement Previous month | Cummalitive achievement in current month | Cummalative achievement
1 | No. of Panchayats | 86 | 1 | 87
2 | No of revenue villages to be covered | 198 | 14 | 212
3 | No of Village to be saturated (geographically) - certification from the VO | 86 | 0 | 86
Result-1 | Formation of self reliant and inclusive community institutions including SHGs, Village Organizations and Federations.
In-1.2 | Self managed self help groups (SHGs) established, covering at least 80% of the target households, 60% of formed SHGs into VO; and 40% of the formed VOs into BLF.
| Total SGSY groups in JEEViKA fold | 165 | 16 | 181 | Only Validate
1.2.1 | Total No of SHG formed | 5773 | 200 | 5973
| TOTAL NO OF POOR MOBILISED | 68980 | 2346 | 71326
| No. of SC | 17143 | 395 | 17538
| No. ST | 1055 | 0 | 1055
| No.EBC | 17060 | 454 | 17514
| No. OBC | 19955 | 573 | 20528
| No. Minority | 10032 | 154 | 10186
| General | 2162 | 67 | 2229
1.2.2 | No. of Village Organisation Formed | 350 | 1 | 351
1.2.3 | No. of 6 months old SHGs Part of Village Organisation | 3606 | 8 | 3614
| No. of CLF Formed | 7 | 0 | 7
| No. of one year old VO part of CLF | 120 | 0 | 120
| No. of VO Registered under Cooperative Society Act-1999 | 22 | 0 | 22
COMMUNITY CADRES - IB & CB
1.2.6 | Number of CM working | 629 | 20 | 649
1.2.7 | Number of VO Book Keepers working | 67 | 0 | 67
1.2.8 | Number of Internal CRPs - SHG Formation working | 341 | 35 | 376
1.2.9 | Number of Internal CRPs-VO formation working | 28 | 0 | 28
1.2.10 | Number of Internal CRPs -Master Trainer working | 37 | 0 | 37
| No. of TSC CRP identified/Trained | 9 | 2 | 11
In-1.3 | At least 75% of formed VOs accessed and managed project funds as per project processes at any point of time
1.3.1 | No of VOs having Bank Account | 317 | 6 | 323
1.3.2 | No of VO to manage Baalwaadi | 0 | 0 | 0
1.3.3 | No of VO to be promoted as Health & Nutrition center | 0 | 0 | 0
1.3.4 | Number of VO participating in HRF | 190 | 0 | 190
1.3.5 | No. of members benefitted in HRF | 800 | 12 | 812
1.3.6 | No of VO received funding for its Action Plan | 0 | 0 | 0
In-1.4
1.4.2 | No. of SHGs having Bank A/C | 4291 | 207 | 4498
1.4.3 | No of Bank Mitra working | 20 | 0 | 20
1.4.4 | No of eligible SHGs ( six month old SHG + following PANCHSUTRA ) financed by Banks | 2899 | 462 | 3361
1.4.5 | Amount Loaned by Banks to SHG | 144950000 | 23100000 | 168050000
1.4.6 | No of Groups repeat financed by Banks | 13 | 18 | 31
1.4.7 | Repeat financed Amount by Banks | 1300000 | 1800000 | 3100000
1.4.10 | No. of SHG members received bond under insurance programme. | 12360 | 0 | 12360
Result-2 | Establishment and use of Community Investment Fund for food security, social services, assets and income generation and service sector investment
2.1.1 | No of Group visited for Social plan | 36 | 5 | 41
2.1.2 | No of SHG members made signature literate | 30462 | 348 | 30810
2.1.3 | No of SHG made financial literate | 30 | 0 | 30
5 | No of SHG Member linked with RSBY - Health insurance | 5989 | 0 | 5989
2.1.5 | Sanitation Programme initiated with number of SHGs | 60 | 0 | 60
2.1.6 | No. of SHG HHs linked with Social Security Programme | 0 | 0 | 0
2.1.7 | No of Social Security Resource Person working | 0 | 0 | 0
2.1.8 | NO of Social Security community professional working | 0 | 0 | 0
2.1.9 | No of groups to complete Micro Planing exercise within 3 months of Group formation | 3824 | 87 | 3911
2.1.10 | No of Group Recd ICF through BPIU | 2289 | 118 | 2407
2.1.11 | No of Group Recd ICF through VO | 0 | 0 | 0
2.1.12 | Total No. of Groups received ICF through Vo/BPIU | 3323 | 130 | 3453
2.1.13 | No of groups/Farmers to complete Livelihoods Micro Planing exercise(SWI) | 1200 | 0 | 1200
2.1.14 | No of Group Revisited for Micro plan | 12 | 0 | 12
2.1.15 | No of trained CM generating Micro Plan | 55 | 1 | 56
Food security increased for 80% of target households as compared to the baseline
2.1.16 | Number of VO participating in FSF | 186 | 0 | 186
2.1.17 | No of HH linked with FS Intervention | 7010 | 730 | 7740
Result - 3 | Establishment and operationalization of Technical Assistance Fund.
In- 3.1 | At least 5 major business linkages established through public/private partnership by CBOs
3.1.1 | No of SHG members registered in VO for SRI | 10444 | 0 | 10444
3.1.2 | No of SHG members registered in VO for SWI | 1178 | 0 | 1178
3.1.3 | No of Acres of land will be under Agriculture Intervention-SRI | 6337 | 0 | 6337
3.1.4 | No of Acres of land will be under Agriculture Intervention- SWI | 2765 | 0 | 2765
3.1.5 | No of vermi-compost pit will be prepared | 3 | 0 | 3
3.1.6 | No of VRP will work in the Agriculture Intervention | 168 | 2 | 170
3.1.7 | No of Skilled Extension Worker will be created in Agriculture Intervention | 0 | 0 | 0
3.1.8 | No of SHG members will be registered in existing DCS | 0 | 0 | 0
3.1.9 | No of New DCS formed | 0 | 0 | 0
3.1.10 | No of SHG members will be registered in new DCS | 0 | 0 | 0
3.1.11 | No of DCS promoted as resource DCS | 0 | 0 | 0
3.1.13 | No of Kishan days will be organized | 0 | 0 | 0
3.1.14 | No of Cluster Adhibesan will be organized | 0 | 0 | 0
3.1.15 | No of VO have efficient equipment management system in place | 0 | 44 | 44
| Moong MP | 1405 | 0 | 1405
| No. of Katta for moong cultivation0 | 7298 | 0 | 7298
Atleast 5,000 Direct jobs created through Project facilitation and atleast 75% of them are getting sustained income
3.1.16 | No of youth identified - data base prepared | 9929 | 220 | 10149
3.1.17 | No of Youth Placed by direct placement | 55 | 10 | 65
3.1.18 | No of Youth Placed by service sector agency | 0 | 0 | 0
3.1.19 | No of JRP working | 10 | 0 | 10
Project Monitoring and Learning System established, including RLMIS, learning and experience sharing forums at different levels of Project management
3.1.20 | % of Cluster generating reports through MIS | 95 | 0 | 95
3.1.21 | No of SHG graded | 3657 | 43 | 3700
3.1.22 | No of VO rated | 135 | 0 | 135
3.1.23 | No of Case study generated ( Best Practice - Institution Program,Procurement, Financial Mgmt.) | 6 | 0 | 6
Result 4 | Project implementation procedures and agreed business standards are followed for at least 80% of project interventions at any point in time
4.2.1 | No of MOU signed between BPIU and Community Based Organisation | 228 | 0 | 228
4.2.2 | No of UC received within One month time of CIF release from CBOs | 1434 | 12 | 1446
4.2.3 | No of CBOs trained on Community Procurement | 91 | 0 | 91
4.2.4 | % of Community Cadre payment made in the Ist week of the month | 153 | 0 | 153
4.2.5 | No of VO submitting Receipt & payment on monthly basis | 258 | 0 | 258
4.2.6 | No of VO two months old procured establishment materials | 84 | 0 | 84