## Chhatapur
MPPR of BPIU - Chhatapur Month - December . 2014
Sl. | DESCRIPTION OF PROGRAM | Cummalitive achievement Previous month | Cummalitive achievement in current month | Cummalative achievement
1 | No. of Panchayats entered | 23 | 0 | 23
2 | No of revenue villages Covered | 56 | 0 | 56
3 | No of Village saturated (geographically) - certification from the VO & passed by Gram Sabha | 27 | 0 | 27
Result-1 | Formation of self reliant and inclusive community institutions including SHGs, Village Organizations and Federations. (IB-CB)
1.1 | No Of SGSY Groups Validated | 0 | 51 | 51
1.2 | No Of SGSY Groups Adopted | 0 | 39 | 39
1.3 | Total No of SHG formed (C1- ……... , C2- ………., C3-……….) *** | 2092 | 22 | 2114
1.4 | TOTAL NO OF POOR MOBILISED | 25020 | 256 | 25276
a | No. of SC | 6221 | 88 | 6309
b | No. ST | 741 | 44 | 785
c | No.EBC | 7106 | 64 | 7170
d | No. OBC | 6159 | 36 | 6195
e | No. Minority | 3212 | 24 | 3236
f | General | 1568 | 0 | 1568
1.5 | No. of predominantly SC-SHGs(SC>=50%) | 536 | 4 | 540
1.6 | No. of predominantly ST-SHGs(ST>=50%) | 306 | 2 | 308
1.7 | No. of predominantly Minority-SHGs(Minority >=50%) | 990 | 16 | 1006
1.8 | No. of Village Organisation Formed (C1- …….., C2-….….., C3- ……..) *** | 156 | 5 | 161
1.9 | No. of 4 months old SHGs Part of Village Organisation | 1531 | 24 | 1555
1.10 | No. of CLF Formed | 3 | 0 | 3
1.11 | No. of one year old VO part of CLF | 52 | 0 | 52
1.12 | No. of VO Registered under Bihar self supporting cooperative Society Act-1996 | 8 | 0 | 8
Result-2 | COMMUNITY CADRES
2.1 | Number of CM working | 216 | 5 | 221
2.2 | Number of VO Book Keepers working | 27 | 0 | 27
2.3 | Number of Internal CRPs - SHG Formation working | 123 | 0 | 123
2.4 | Number of Internal CRPs-VO formation working | 28 | 0 | 28
2.5 | Number of Internal CRPs -Master Trainer working | 37 | 0 | 37
2.6 | No. of TSC CRP identified/Trained | 0 | 0 | 0
2.7 | No of Bank Mitra working | 8 | 0 | 8
2.8 | No of VRP is work in the Agriculture Intervention | 55 | 0 | 55
2.9 | No of Skilled Extension Worker (SEW)in Agriculture Intervention | 0 | 0 | 0
2.10 | No of JRP working | 1 | 0 | 1
2.11 | No of Jeevika Saheli working | 0 | 0 | 0
Result- 3 | Micro Finance
3.1 | No. of SHGs having Bank A/C | 1811 | 27 | 1838
3.2 | No of VOs having Bank Account | 144 | 1 | 145
3.3 | No of eligible SHGs ( six month old SHG + following PANCHSUTRA ) financed by Banks (Credit Linkage) | 1418 | 0 | 1418
3.4 | Amount Loaned by Banks to SHG | 70900000 | 0 | 70900000
3.5 | No of Groups repeat financed by Banks (Second Dose) | 0 | 0 | 0
3.6 | Repeat financed Amount by Banks | 0 | 0 | 0
3.7 | No. of SHG member Linked with insurance programme. (AABY) | 3985 | 145 | 4130
3.8 | No of SHG member Linked with RSBY - Health insurance | 1650 | 0 | 1650
3.9 | No of groups to complete Micro Planing exercise within 3 months of Group formation | 1594 | 99 | 1693
3.10 | No of Groups LCM done | 1536 | 34 | 1570
3.11 | Total No. of Groups received ICF through VO/BPIU | 1536 | 0 | 1536
3.12 | No of Group Revisited for Micro plan | 0 | 0 | 0
3.13 | No of trained CM/CRP generating Micro Plan | 40 | 0 | 40
Result-4 | Social Development & Health Nutrition
4.1 | No of SHG members made signature literate | 13233 | 99 | 13332
4.2 | No of SHG made financial literate | 31 | 0 | 31
4.3 | Sanitation Programme initiated with number of SHGs | 60 | 0 | 60
4.4 | No. of SHG HHs linked with Social Security Programme | 0 | 0 | 0
4.5 | No of Social Security Resource Person working | 0 | 0 | 0
4.6 | NO of Social Security community professional working | 0 | 0 | 0
4.7 | Number of VO participating in HRF | 52 | 0 | 52
4.8 | No. of members benefitted in HRF | 414 | 0 | 414
4.9 | Number of VO participating in FSF | 39 | 0 | 39
4.10 | No of HH linked with FS Intervention | 1796 | 0 | 1796
4.11 | No of VO involved in PDS | 0 | 0 | 0
4.12 | No of VO involved in CNCC | 0 | 0 | 0
4.13 | No. VO Completed 1st Cycle of FS Member | 0 | 0 | 0
4.14 | No. VO Completed 2nd Cycle of FS Member | 0 | 0 | 0
4.15 | No. VO Completed 3rd Cycle of FS Member | 0 | 0 | 0
Result-5 | Livelihoods Activities
5.1 | No of SHG members registered in VO for SRI | 2990 | 0 | 2990
5.2 | No of SHG members registered in VO for SWI | 0 | 1445 | 1445
5.3 | No of SHG members registered in VO for Vegetable cultivation | 0 | 1309 | 1309
5.4 | No of Acres of land under Agriculture Intervention-SRI | 381 | 0 | 381
5.5 | No of Acres of land under Agriculture Intervention- SWI | 0 | 0 | 0
5.6 | No of Acres of land under Vegetable Intervention- | 0 | 122 | 122
5.7 | No of vermi-compost pit will be prepared | 2 | 0 | 2
5.8 | No of SHG members is registered in existing DCS | 0 | 0 | 0
5.9 | No of agri culture PG formed | 1 | 0 | 1
5.10 | No of PG having Bank A/C opened | 3 | 0 | 3
5.11 | No of Vegetable PG formed | 0 | 0 | 0
5.12 | No of Poultry Mother Unit opened | 1 | 0 | 1
5.13 | No of Non-farm PG formed | 0 | 0 | 0
5.14 | No of DCS formed (Dairy Cooperative Society) | 0 | 0 | 0
5.15 | No of SHG members registered in DCS | 0 | 0 | 0
5.16 | No of DCS promoted as resource DCS | 0 | 0 | 0
5.17 | No of Kishan days organized | 0 | 0 | 0
5.18 | No of Cluster Adhibesan organized | 0 | 0 | 0
5.19 | No of VO having efficient equipment management system | 0 | 0 | 0
5.20 | No of MP for Moong Cultivation completed | 480 | 0 | 480
5.21 | No of Acres of land under Moong Cultivation | 4705 | 0 | 4705
Result- 6 | Skills Development (JOBs)
6.1 | No of youth identified - data base prepared | 800 | 100 | 900
6.2 | No of Youth Placed | 40 | 0 | 40
6.3 | No of Youth Placed by service sector agency | 0 | 0 | 0
6.4 | No. of Youth Trained | 0 | 0 | 0
Result- 7 | Project Monitoring and Learning System established, including RLMIS, learning and experience sharing forums at different levels of Project management
7.1 | % of Cluster generating reports through MIS | 0 | 0 | 0
7.2 | % of VO submitting Receipt & payment on monthly basis | 132 | 0 | 132
7.3 | No of SHG graded | 1508 | 0 | 1508
7.4 | No of VO rated | 59 | 0 | 59
7.5 | No of Case study generated (Best Practice - Institution Program,Procurement, Financial) | 0 | 0 | 0
Result- 8 | Project implementation procedures and agreed business standards are followed for at least 80% of project interventions at any point in time
8.1 | No of MOU signed between BPIU and CBOs | 71 | 0 | 71
8.2 | No of VO received establishment materials | 23 | 0 | 23
8.3 | No of CLF received establishment materials | 2 | 1 | 3
Result- 9 | Status of Utilization Certificate (UC)
9.1 | No of UC received for ICF (SHG) | 514 | 18 | 532
9.2 | No of UC received for HRF (VO) | 0 | 0 | 0
9.3 | No of UC received for FSF (VO) | 0 | 0 | 0
9.4 | No of UC received for VO Establishment Materials | 0 | 0 | 0
9.5 | No of CBOs trained on Community Procurement | 45 | 0 | 45
9.6 | % of Community Cadre payment made till month | 0 | 0 | 0

## Triveniganj
MPPR of BPIU - Triveniganj Month - December . 2014
Sl. | DESCRIPTION OF PROGRAM | Cummalitive achievement Previous month | Cummalitive achievement in current month | Cummalative achievement
1 | No. of Panchayats entered | 23 | 0 | 23
2 | No of revenue villages Covered | 51 | 0 | 51
3 | No of Village saturated (geographically) - certification from the VO & passed by Gram Sabha | 22 | 0 | 22
Result-1 | Formation of self reliant and inclusive community institutions including SHGs, Village Organizations and Federations. (IB-CB)
1.1 | No Of SGSY Groups Validated | 0 | 0 | 0
1.2 | No Of SGSY Groups Adopted | 0 | 0 | 0
1.3 | Total No of SHG formed (C1- ……... , C2- ………., C3-……….) *** | 1488 | 240 | 1728
1.4 | TOTAL NO OF POOR MOBILISED | 17645 | 2640 | 20285
a | No. of SC | 4383 | 945 | 5328
b | No. ST | 152 | 0 | 152
c | No.EBC | 3399 | 395 | 3794
d | No. OBC | 7649 | 1025 | 8674
e | No. Minority | 1968 | 210 | 2178
f | General | 94 | 65 | 159
1.5 | No. of predominantly SC-SHGs(SC>=50%) | 0 | 0 | 0
1.6 | No. of predominantly ST-SHGs(ST>=50%) | 0 | 0 | 0
1.7 | No. of predominantly Minority-SHGs(Minority >=50%) | 0 | 0 | 0
1.8 | No. of Village Organisation Formed (C1- …….., C2-….….., C3- ……..) *** | 88 | 0 | 88
1.9 | No. of 4 months old SHGs Part of Village Organisation | 920 | 0 | 920
1.10 | No. of CLF Formed | 1 | 0 | 1
1.11 | No. of one year old VO part of CLF | 15 | 0 | 15
1.12 | No. of VO Registered under Bihar self supporting cooperative Society Act-1996 | 5 | 0 | 5
Result-2 | COMMUNITY CADRES
2.1 | Number of CM working | 143 | 0 | 143
2.2 | Number of VO Book Keepers working | 17 | 0 | 17
2.3 | Number of Internal CRPs - SHG Formation working | 62 | 0 | 62
2.4 | Number of Internal CRPs-VO formation working | 0 | 0 | 0
2.5 | Number of Internal CRPs -Master Trainer working | 0 | 0 | 0
2.6 | No. of TSC CRP identified/Trained | 0 | 0 | 0
2.7 | No of Bank Mitra working | 9 | 0 | 9
2.8 | No of VRP is work in the Agriculture Intervention | 41 | 0 | 41
2.9 | No of Skilled Extension Worker (SEW)in Agriculture Intervention | 0 | 0 | 0
2.10 | No of JRP working | 3 | 0 | 3
2.11 | No of Jeevika Saheli working | 29 | 31 | 60
Result- 3 | Micro Finance
3.1 | No. of SHGs having Bank A/C | 1264 | 20 | 1284
3.2 | No of VOs having Bank Account | 79 | 0 | 79
3.3 | No of eligible SHGs ( six month old SHG + following PANCHSUTRA ) financed by Banks (Credit Linkage) | 850 | 0 | 850
3.4 | Amount Loaned by Banks to SHG | 42500000 | 0 | 42500000
3.5 | No of Groups repeat financed by Banks (Second Dose) | 31 | 0 | 31
3.6 | Repeat financed Amount by Banks | 3100000 | 0 | 3100000
3.7 | No. of SHG member Linked with insurance programme. (AABY) | 3495 | 370 | 3865
3.8 | No of SHG member Linked with RSBY - Health insurance | 1139 | 0 | 1139
3.9 | No of groups to complete Micro Planing exercise within 3 months of Group formation | 1062 | 0 | 1062
3.10 | No of Groups LCM done | 1007 | 155 | 1162
3.11 | Total No. of Groups received ICF through VO/BPIU | 1007 | 0 | 1007
3.12 | No of Group Revisited for Micro plan | 0 | 0 | 0
3.13 | No of trained CM/CRP generating Micro Plan | 0 | 0 | 0
Result-4 | Social Development & Health Nutrition
4.1 | No of SHG members made signature literate | 7294 | 594 | 7888
4.2 | No of SHG made financial literate | 0 | 0 | 0
4.3 | Sanitation Programme initiated with number of SHGs | 0 | 0 | 0
4.4 | No. of SHG HHs linked with Social Security Programme | 0 | 0 | 0
4.5 | No of Social Security Resource Person working | 0 | 0 | 0
4.6 | NO of Social Security community professional working | 0 | 0 | 0
4.7 | Number of VO participating in HRF | 61 | 0 | 61
4.8 | No. of members benefitted in HRF | 178 | 0 | 178
4.9 | Number of VO participating in FSF | 60 | 0 | 60
4.10 | No of HH linked with FS Intervention | 1563 | 0 | 1563
4.11 | No of VO involved in PDS | 0 | 0 | 0
4.12 | No of VO involved in CNCC | 0 | 0 | 0
4.13 | No. VO Completed 1st Cycle of FS Member | 0 | 0 | 0
4.14 | No. VO Completed 2nd Cycle of FS Member | 0 | 0 | 0
4.15 | No. VO Completed 3rd Cycle of FS Member | 0 | 0 | 0
Result-5 | Livelihoods Activities
5.1 | No of SHG members registered in VO for SRI | 2540 | 0 | 2540
5.2 | No of SHG members registered in VO for SWI | 1060 | 491 | 1551
5.3 | No of SHG members registered in VO for Vegetable cultivation | 783 | 0 | 783
5.4 | No of Acres of land under Agriculture Intervention-SRI | 117 | 0 | 117
5.5 | No of Acres of land under Agriculture Intervention- SWI | 55 | 41 | 96
5.6 | No of Acres of land under Vegetable Intervention- | 42 | 0 | 42
5.7 | No of vermi-compost pit will be prepared | 0 | 0 | 0
5.8 | No of SHG members is registered in existing DCS | 0 | 0 | 0
5.9 | No of agri culture PG formed | 0 | 0 | 0
5.10 | No of PG having Bank A/C opened | 0 | 0 | 0
5.11 | No of Vegetable PG formed | 0 | 2 | 2
5.12 | No of Poultry Mother Unit opened | 0 | 0 | 0
5.13 | No of Non-farm PG formed | 0 | 0 | 0
5.14 | No of DCS formed (Dairy Cooperative Society) | 0 | 0 | 0
5.15 | No of SHG members registered in DCS | 0 | 0 | 0
5.16 | No of DCS promoted as resource DCS | 0 | 0 | 0
5.17 | No of Kishan days organized | 0 | 0 | 0
5.18 | No of Cluster Adhibesan organized | 0 | 0 | 0
5.19 | No of VO having efficient equipment management system | 0 | 0 | 0
5.20 | No of MP for Moong Cultivation completed | 0 | 0 | 0
5.21 | No of Acres of land under Moong Cultivation | 19 | 0 | 19
Result- 6 | Skills Development (JOBs)
6.1 | No of youth identified - data base prepared | 2844 | 0 | 2844
6.2 | No of Youth Placed | 10 | 0 | 10
6.3 | No of Youth Placed by service sector agency | 0 | 0 | 0
6.4 | No. of Youth Trained | 0 | 0 | 0
Result- 7 | Project Monitoring and Learning System established, including RLMIS, learning and experience sharing forums at different levels of Project management
7.1 | % of Cluster generating reports through MIS | 0 | 0 | 0
7.2 | % of VO submitting Receipt & payment on monthly basis | 0 | 0 | 0
7.3 | No of SHG graded | 885 | 0 | 885
7.4 | No of VO rated | 74 | 0 | 74
7.5 | No of Case study generated (Best Practice - Institution Program,Procurement, Financial) | 0 | 0 | 0
Result- 8 | Project implementation procedures and agreed business standards are followed for at least 80% of project interventions at any point in time
8.1 | No of MOU signed between BPIU and CBOs | 70 | 0 | 70
8.2 | No of VO received establishment materials | 28 | 0 | 28
8.3 | No of CLF received establishment materials | 0 | 0 | 0
Result- 9 | Status of Utilization Certificate (UC)
9.1 | No of UC received for ICF (SHG) | 76 | 0 | 76
9.2 | No of UC received for HRF (VO) | 0 | 0 | 0
9.3 | No of UC received for FSF (VO) | 0 | 0 | 0
9.4 | No of UC received for VO Establishment Materials | 0 | 0 | 0
9.5 | No of CBOs trained on Community Procurement | 2 | 0 | 2
9.6 | % of Community Cadre payment made till month | 0 | 0 | 0

## Pratapganj
MPPR of BPIU - Pratapganj Month - December . 2014
Sl. | DESCRIPTION OF PROGRAM | Cummalitive achievement Previous month | Cummalitive achievement in current month | Cummalative achievement
1 | No. of Panchayats entered | 9 | 0 | 9
2 | No of revenue villages Covered | 11 | 1 | 12
3 | No of Village saturated (geographically) - certification from the VO & passed by Gram Sabha | 10 | 0 | 10
Result-1 | Formation of self reliant and inclusive community institutions including SHGs, Village Organizations and Federations. (IB-CB)
1.1 | No Of SGSY Groups Validated | 68 | 7 | 75
1.2 | No Of SGSY Groups Adopted | 0 | 3 | 3
1.3 | Total No of SHG formed (C1- ……... , C2- ………., C3-……….) *** | 812 | 92 | 904
1.4 | TOTAL NO OF POOR MOBILISED | 9840 | 1049 | 10889
a | No. of SC | 1883 | 465 | 2348
b | No. ST | 187 | 0 | 187
c | No.EBC | 3009 | 112 | 3121
d | No. OBC | 3186 | 285 | 3471
e | No. Minority | 1295 | 38 | 1333
f | General | 280 | 149 | 429
1.5 | No. of predominantly SC-SHGs(SC>=50%) | 112 | 0 | 112
1.6 | No. of predominantly ST-SHGs(ST>=50%) | 8 | 0 | 8
1.7 | No. of predominantly Minority-SHGs(Minority >=50%) | 117 | 0 | 117
1.8 | No. of Village Organisation Formed (C1- …….., C2-….….., C3- ……..) *** | 55 | 0 | 55
1.9 | No. of 4 months old SHGs Part of Village Organisation | 646 | 0 | 646
1.10 | No. of CLF Formed | 2 | 0 | 2
1.11 | No. of one year old VO part of CLF | 33 | 0 | 33
1.12 | No. of VO Registered under Bihar self supporting cooperative Society Act-1996 | 4 | 0 | 4
Result-2 | COMMUNITY CADRES
2.1 | Number of CM working | 86 | 14 | 100
2.2 | Number of VO Book Keepers working | 11 | 0 | 11
2.3 | Number of Internal CRPs - SHG Formation working | 128 | 0 | 128
2.4 | Number of Internal CRPs-VO formation working | 0 | 0 | 0
2.5 | Number of Internal CRPs -Master Trainer working | 0 | 0 | 0
2.6 | No. of TSC CRP identified/Trained | 0 | 0 | 0
2.7 | No of Bank Mitra working | 4 | 0 | 4
2.8 | No of VRP is work in the Agriculture Intervention | 50 | 0 | 50
2.9 | No of Skilled Extension Worker (SEW)in Agriculture Intervention | 0 | 0 | 0
2.10 | No of JRP working | 3 | 0 | 3
2.11 | No of Jeevika Saheli working | 38 | 0 | 38
Result- 3 | Micro Finance
3.1 | No. of SHGs having Bank A/C | 639 | 10 | 649
3.2 | No of VOs having Bank Account | 52 | 0 | 52
3.3 | No of eligible SHGs ( six month old SHG + following PANCHSUTRA ) financed by Banks (Credit Linkage) | 532 | 0 | 532
3.4 | Amount Loaned by Banks to SHG | 26600000 | 0 | 26600000
3.5 | No of Groups repeat financed by Banks (Second Dose) | 0 | 0 | 0
3.6 | Repeat financed Amount by Banks | 0 | 0 | 0
3.7 | No. of SHG member Linked with insurance programme. (AABY) | 4452 | 6 | 4458
3.8 | No of SHG member Linked with RSBY - Health insurance | 1200 | 0 | 1200
3.9 | No of groups to complete Micro Planing exercise within 3 months of Group formation | 629 | 0 | 629
3.10 | No of Groups LCM done | 626 | 0 | 626
3.11 | Total No. of Groups received ICF through VO/BPIU | 599 | 27 | 626
3.12 | No of Group Revisited for Micro plan | 0 | 0 | 0
3.13 | No of trained CM/CRP generating Micro Plan | 0 | 0 | 0
Result-4 | Social Development & Health Nutrition
4.1 | No of SHG members made signature literate | 5961 | 57 | 6018
4.2 | No of SHG made financial literate | 0 | 0 | 0
4.3 | Sanitation Programme initiated with number of SHGs | 0 | 0 | 0
4.4 | No. of SHG HHs linked with Social Security Programme | 0 | 0 | 0
4.5 | No of Social Security Resource Person working | 0 | 0 | 0
4.6 | NO of Social Security community professional working | 0 | 0 | 0
4.7 | Number of VO participating in HRF | 46 | 0 | 46
4.8 | No. of members benefitted in HRF | 85 | 4 | 89
4.9 | Number of VO participating in FSF | 46 | 0 | 46
4.10 | No of HH linked with FS Intervention | 3294 | 92 | 3386
4.11 | No of VO involved in PDS | 0 | 0 | 0
4.12 | No of VO involved in CNCC | 0 | 0 | 0
4.13 | No. VO Completed 1st Cycle of FS Member | 37 | 0 | 37
4.14 | No. VO Completed 2nd Cycle of FS Member | 9 | 1 | 10
4.15 | No. VO Completed 3rd Cycle of FS Member | 4 | 0 | 4
Result-5 | Livelihoods Activities
5.1 | No of SHG members registered in VO for SRI | 4166 | 0 | 4166
5.2 | No of SHG members registered in VO for SWI | 718 | 1206 | 1924
5.3 | No of SHG members registered in VO for Vegetable cultivation | 2479 | 0 | 2479
5.4 | No of Acres of land under Agriculture Intervention-SRI | 5788 | 0 | 5788
5.5 | No of Acres of land under Agriculture Intervention- SWI | 2765 | 2015 | 4780
5.6 | No of Acres of land under Vegetable Intervention- | 2587 | 0 | 2587
5.7 | No of vermi-compost pit will be prepared | 1 | 0 | 1
5.8 | No of SHG members is registered in existing DCS | 0 | 0 | 0
5.9 | No of agri culture PG formed | 2 | 0 | 2
5.10 | No of PG having Bank A/C opened | 0 | 0 | 0
5.11 | No of Vegetable PG formed | 0 | 0 | 0
5.12 | No of Poultry Mother Unit opened | 0 | 1 | 1
5.13 | No of Non-farm PG formed | 0 | 0 | 0
5.14 | No of DCS formed (Dairy Cooperative Society) | 0 | 0 | 0
5.15 | No of SHG members registered in DCS | 0 | 0 | 0
5.16 | No of DCS promoted as resource DCS | 0 | 0 | 0
5.17 | No of Kishan days organized | 0 | 0 | 0
5.18 | No of Cluster Adhibesan organized | 0 | 0 | 0
5.19 | No of VO having efficient equipment management system | 44 | 0 | 44
5.20 | No of MP for Moong Cultivation completed | 925 | 0 | 925
5.21 | No of Acres of land under Moong Cultivation | 2593 | 0 | 2593
Result- 6 | Skills Development (JOBs)
6.1 | No of youth identified - data base prepared | 4369 | 230 | 4599
6.2 | No of Youth Placed | 15 | 0 | 15
6.3 | No of Youth Placed by service sector agency | 0 | 0 | 0
6.4 | No. of Youth Trained | 0 | 0 | 0
Result- 7 | Project Monitoring and Learning System established, including RLMIS, learning and experience sharing forums at different levels of Project management
7.1 | % of Cluster generating reports through MIS | 0 | 0 | 0
7.2 | % of VO submitting Receipt & payment on monthly basis | 83 | 0 | 83
7.3 | No of SHG graded | 629 | 0 | 629
7.4 | No of VO rated | 0 | 0 | 0
7.5 | No of Case study generated (Best Practice - Institution Program,Procurement, Financial) | 0 | 0 | 0
Result- 8 | Project implementation procedures and agreed business standards are followed for at least 80% of project interventions at any point in time
8.1 | No of MOU signed between BPIU and CBOs | 46 | 0 | 46
8.2 | No of VO received establishment materials | 10 | 0 | 10
8.3 | No of CLF received establishment materials | 1 | 0 | 1
Result- 9 | Status of Utilization Certificate (UC)
9.1 | No of UC received for ICF (SHG) | 484 | 9 | 493
9.2 | No of UC received for HRF (VO) | 12 | 3 | 15
9.3 | No of UC received for FSF (VO) | 16 | 0 | 16
9.4 | No of UC received for VO Establishment Materials | 0 | 0 | 0
9.5 | No of CBOs trained on Community Procurement | 44 | 0 | 44
9.6 | % of Community Cadre payment made till month | 0 | 80 | 80

## Basantpur
MPPR of BPIU - Basantpur Month - December . 2014
Sl. | DESCRIPTION OF PROGRAM | Cummalitive achievement Previous month | Cummalitive achievement in current month | Cummalative achievement
1 | No. of Panchayats entered | 14 | 0 | 14
2 | No of revenue villages Covered | 50 | 7 | 57
3 | No of Village saturated (geographically) - certification from the VO & passed by Gram Sabha | 27 | 0 | 27
Result-1 | Formation of self reliant and inclusive community institutions including SHGs, Village Organizations and Federations. (IB-CB)
1.1 | No Of SGSY Groups Validated | 150 | 0 | 150
1.2 | No Of SGSY Groups Adopted | 4 | 0 | 4
1.3 | Total No of SHG formed (C1- ……... , C2- ………., C3-……….) *** | 888 | 163 | 1051
1.4 | TOTAL NO OF POOR MOBILISED | 10687 | 1841 | 12528
a | No. of SC | 3553 | 778 | 4331
b | No. ST | 20 | 1 | 21
c | No.EBC | 2360 | 340 | 2700
d | No. OBC | 2636 | 621 | 3257
e | No. Minority | 3539 | 59 | 3598
f | General | 236 | 42 | 278
1.5 | No. of predominantly SC-SHGs(SC>=50%) | 0 | 387 | 387
1.6 | No. of predominantly ST-SHGs(ST>=50%) | 0 | 3 | 3
1.7 | No. of predominantly Minority-SHGs(Minority >=50%) | 0 | 196 | 196
1.8 | No. of Village Organisation Formed (C1- …….., C2-….….., C3- ……..) *** | 61 | 2 | 63
1.9 | No. of 4 months old SHGs Part of Village Organisation | 598 | 17 | 615
1.10 | No. of CLF Formed | 1 | 0 | 1
1.11 | No. of one year old VO part of CLF | 20 | 0 | 20
1.12 | No. of VO Registered under Bihar self supporting cooperative Society Act-1996 | 5 | 0 | 5
Result-2 | COMMUNITY CADRES
2.1 | Number of CM working | 100 | 13 | 113
2.2 | Number of VO Book Keepers working | 13 | 0 | 13
2.3 | Number of Internal CRPs - SHG Formation working | 64 | 0 | 64
2.4 | Number of Internal CRPs-VO formation working | 0 | 0 | 0
2.5 | Number of Internal CRPs -Master Trainer working | 0 | 0 | 0
2.6 | No. of TSC CRP identified/Trained | 0 | 0 | 0
2.7 | No of Bank Mitra working | 4 | 0 | 4
2.8 | No of VRP is work in the Agriculture Intervention | 31 | 1 | 32
2.9 | No of Skilled Extension Worker (SEW)in Agriculture Intervention | 0 | 0 | 0
2.10 | No of JRP working | 3 | 0 | 3
2.11 | No of Jeevika Saheli working | 0 | 0 | 0
Result- 3 | Micro Finance
3.1 | No. of SHGs having Bank A/C | 754 | 9 | 763
3.2 | No of VOs having Bank Account | 51 | 3 | 54
3.3 | No of eligible SHGs ( six month old SHG + following PANCHSUTRA ) financed by Banks (Credit Linkage) | 575 | 0 | 575
3.4 | Amount Loaned by Banks to SHG | 28750000 | 0 | 28750000
3.5 | No of Groups repeat financed by Banks (Second Dose) | 0 | 0 | 0
3.6 | Repeat financed Amount by Banks | 0 | 0 | 0
3.7 | No. of SHG member Linked with insurance programme. (AABY) | 5259 | 102 | 5361
3.8 | No of SHG member Linked with RSBY - Health insurance | 2000 | 0 | 2000
3.9 | No of groups to complete Micro Planing exercise within 3 months of Group formation | 716 | 27 | 743
3.10 | No of Groups LCM done | 678 | 45 | 723
3.11 | Total No. of Groups received ICF through VO/BPIU | 656 | 0 | 656
3.12 | No of Group Revisited for Micro plan | 0 | 0 | 0
3.13 | No of trained CM/CRP generating Micro Plan | 0 | 4 | 4
Result-4 | Social Development & Health Nutrition
4.1 | No of SHG members made signature literate | 4772 | 100 | 4872
4.2 | No of SHG made financial literate | 0 | 0 | 0
4.3 | Sanitation Programme initiated with number of SHGs | 0 | 0 | 0
4.4 | No. of SHG HHs linked with Social Security Programme | 0 | 0 | 0
4.5 | No of Social Security Resource Person working | 0 | 0 | 0
4.6 | NO of Social Security community professional working | 0 | 0 | 0
4.7 | Number of VO participating in HRF | 33 | 0 | 33
4.8 | No. of members benefitted in HRF | 150 | 0 | 150
4.9 | Number of VO participating in FSF | 41 | 0 | 41
4.10 | No of HH linked with FS Intervention | 2364 | 0 | 2364
4.11 | No of VO involved in PDS | 0 | 0 | 0
4.12 | No of VO involved in CNCC | 0 | 0 | 0
4.13 | No. VO Completed 1st Cycle of FS Member | 28 | 0 | 28
4.14 | No. VO Completed 2nd Cycle of FS Member | 2 | 0 | 2
4.15 | No. VO Completed 3rd Cycle of FS Member | 1 | 0 | 1
Result-5 | Livelihoods Activities
5.1 | No of SHG members registered in VO for SRI | 946 | 0 | 946
5.2 | No of SHG members registered in VO for SWI | 0 | 1200 | 1200
5.3 | No of SHG members registered in VO for Vegetable cultivation | 0 | 485 | 485
5.4 | No of Acres of land under Agriculture Intervention-SRI | 0 | 61 | 61
5.5 | No of Acres of land under Agriculture Intervention- SWI | 0 | 283 | 283
5.6 | No of Acres of land under Vegetable Intervention- | 0 | 75 | 75
5.7 | No of vermi-compost pit will be prepared | 0 | 3 | 3
5.8 | No of SHG members is registered in existing DCS | 0 | 0 | 0
5.9 | No of agri culture PG formed | 2 | 1 | 3
5.10 | No of PG having Bank A/C opened | 0 | 0 | 0
5.11 | No of Vegetable PG formed | 0 | 0 | 0
5.12 | No of Poultry Mother Unit opened | 0 | 0 | 0
5.13 | No of Non-farm PG formed | 0 | 0 | 0
5.14 | No of DCS formed (Dairy Cooperative Society) | 0 | 0 | 0
5.15 | No of SHG members registered in DCS | 0 | 0 | 0
5.16 | No of DCS promoted as resource DCS | 0 | 0 | 0
5.17 | No of Kishan days organized | 0 | 0 | 0
5.18 | No of Cluster Adhibesan organized | 0 | 0 | 0
5.19 | No of VO having efficient equipment management system | 0 | 0 | 0
5.20 | No of MP for Moong Cultivation completed | 0 | 0 | 0
5.21 | No of Acres of land under Moong Cultivation | 0 | 0 | 0
Result- 6 | Skills Development (JOBs)
6.1 | No of youth identified - data base prepared | 3436 | 100 | 3536
6.2 | No of Youth Placed | 0 | 0 | 0
6.3 | No of Youth Placed by service sector agency | 0 | 0 | 0
6.4 | No. of Youth Trained | 0 | 0 | 0
Result- 7 | Project Monitoring and Learning System established, including RLMIS, learning and experience sharing forums at different levels of Project management
7.1 | % of Cluster generating reports through MIS | 95 | 0 | 95
7.2 | % of VO submitting Receipt & payment on monthly basis | 70 | 0 | 70
7.3 | No of SHG graded | 716 | 27 | 743
7.4 | No of VO rated | 2 | 0 | 2
7.5 | No of Case study generated (Best Practice - Institution Program,Procurement, Financial) | 6 | 0 | 6
Result- 8 | Project implementation procedures and agreed business standards are followed for at least 80% of project interventions at any point in time
8.1 | No of MOU signed between BPIU and CBOs | 41 | 7 | 48
8.2 | No of VO received establishment materials | 23 | 0 | 23
8.3 | No of CLF received establishment materials | 0 | 0 | 0
Result- 9 | Status of Utilization Certificate (UC)
9.1 | No of UC received for ICF (SHG) | 546 | 25 | 571
9.2 | No of UC received for HRF (VO) | 20 | 6 | 26
9.3 | No of UC received for FSF (VO) | 22 | 7 | 29
9.4 | No of UC received for VO Establishment Materials | 0 | 0 | 0
9.5 | No of CBOs trained on Community Procurement | 31 | 1 | 32
9.6 | % of Community Cadre payment made till month | 50 | 0 | 50

## Supaul
MPPR of BPIU - Supaul Sadar Month - December . 2014
Sl. | DESCRIPTION OF PROGRAM | Cummalitive achievement Previous month | Cummalitive achievement in current month | Cummalative achievement
1 | No. of Panchayats entered | 8 | 0 | 8
2 | No of revenue villages Covered | 11 | 0 | 11
3 | No of Village saturated (geographically) - certification from the VO & passed by Gram Sabha | 0 | 0 | 0
Result-1 | Formation of self reliant and inclusive community institutions including SHGs, Village Organizations and Federations. (IB-CB)
1.1 | No Of SGSY Groups Validated | 35 | 0 | 35
1.2 | No Of SGSY Groups Adopted | 0 | 0 | 0
1.3 | Total No of SHG formed (C1- ……... , C2- ………., C3-……….) *** | 121 | 98 | 219
1.4 | TOTAL NO OF POOR MOBILISED | 1285 | 1078 | 2363
a | No. of SC | 418 | 0 | 418
b | No. ST | 0 | 0 | 0
c | No.EBC | 634 | 0 | 634
d | No. OBC | 149 | 0 | 149
e | No. Minority | 70 | 0 | 70
f | General | 14 | 0 | 14
1.5 | No. of predominantly SC-SHGs(SC>=50%) | 0 | 0 | 0
1.6 | No. of predominantly ST-SHGs(ST>=50%) | 0 | 0 | 0
1.7 | No. of predominantly Minority-SHGs(Minority >=50%) | 0 | 0 | 0
1.8 | No. of Village Organisation Formed (C1- …….., C2-….….., C3- ……..) *** | 0 | 1 | 1
1.9 | No. of 4 months old SHGs Part of Village Organisation | 0 | 9 | 9
1.10 | No. of CLF Formed | 0 | 0 | 0
1.11 | No. of one year old VO part of CLF | 0 | 0 | 0
1.12 | No. of VO Registered under Bihar self supporting cooperative Society Act-1996 | 0 | 0 | 0
Result-2 | COMMUNITY CADRES
2.1 | Number of CM working | 18 | 9 | 27
2.2 | Number of VO Book Keepers working | 0 | 0 | 0
2.3 | Number of Internal CRPs - SHG Formation working | 0 | 0 | 0
2.4 | Number of Internal CRPs-VO formation working | 0 | 0 | 0
2.5 | Number of Internal CRPs -Master Trainer working | 0 | 0 | 0
2.6 | No. of TSC CRP identified/Trained | 0 | 0 | 0
2.7 | No of Bank Mitra working | 0 | 0 | 0
2.8 | No of VRP is work in the Agriculture Intervention | 0 | 0 | 0
2.9 | No of Skilled Extension Worker (SEW)in Agriculture Intervention | 0 | 0 | 0
2.10 | No of JRP working | 0 | 0 | 0
2.11 | No of Jeevika Saheli working | 0 | 0 | 0
Result- 3 | Micro Finance
3.1 | No. of SHGs having Bank A/C | 22 | 24 | 46
3.2 | No of VOs having Bank Account | 0 | 0 | 0
3.3 | No of eligible SHGs ( six month old SHG + following PANCHSUTRA ) financed by Banks (Credit Linkage) | 0 | 0 | 0
3.4 | Amount Loaned by Banks to SHG | 0 | 0 | 0
3.5 | No of Groups repeat financed by Banks (Second Dose) | 0 | 0 | 0
3.6 | Repeat financed Amount by Banks | 0 | 0 | 0
3.7 | No. of SHG member Linked with insurance programme. (AABY) | 0 | 0 | 0
3.8 | No of SHG member Linked with RSBY - Health insurance | 0 | 0 | 0
3.9 | No of groups to complete Micro Planing exercise within 3 months of Group formation | 0 | 0 | 0
3.10 | No of Groups LCM done | 0 | 0 | 0
3.11 | Total No. of Groups received ICF through VO/BPIU | 12 | 0 | 12
3.12 | No of Group Revisited for Micro plan | 0 | 0 | 0
3.13 | No of trained CM/CRP generating Micro Plan | 0 | 0 | 0
Result-4 | Social Development & Health Nutrition
4.1 | No of SHG members made signature literate | 44 | 0 | 44
4.2 | No of SHG made financial literate | 0 | 0 | 0
4.3 | Sanitation Programme initiated with number of SHGs | 0 | 0 | 0
4.4 | No. of SHG HHs linked with Social Security Programme | 0 | 0 | 0
4.5 | No of Social Security Resource Person working | 0 | 0 | 0
4.6 | NO of Social Security community professional working | 0 | 0 | 0
4.7 | Number of VO participating in HRF | 0 | 0 | 0
4.8 | No. of members benefitted in HRF | 0 | 0 | 0
4.9 | Number of VO participating in FSF | 0 | 0 | 0
4.10 | No of HH linked with FS Intervention | 0 | 0 | 0
4.11 | No of VO involved in PDS | 0 | 0 | 0
4.12 | No of VO involved in CNCC | 0 | 0 | 0
4.13 | No. VO Completed 1st Cycle of FS Member | 0 | 0 | 0
4.14 | No. VO Completed 2nd Cycle of FS Member | 0 | 0 | 0
4.15 | No. VO Completed 3rd Cycle of FS Member | 0 | 0 | 0
Result-5 | Livelihoods Activities
5.1 | No of SHG members registered in VO for SRI | 0 | 0 | 0
5.2 | No of SHG members registered in VO for SWI | 0 | 0 | 0
5.3 | No of SHG members registered in VO for Vegetable cultivation | 0 | 0 | 0
5.4 | No of Acres of land under Agriculture Intervention-SRI | 0 | 0 | 0
5.5 | No of Acres of land under Agriculture Intervention- SWI | 0 | 0 | 0
5.6 | No of Acres of land under Vegetable Intervention- | 0 | 0 | 0
5.7 | No of vermi-compost pit will be prepared | 0 | 0 | 0
5.8 | No of SHG members is registered in existing DCS | 0 | 0 | 0
5.9 | No of agri culture PG formed | 0 | 0 | 0
5.10 | No of PG having Bank A/C opened | 0 | 0 | 0
5.11 | No of Vegetable PG formed | 0 | 0 | 0
5.12 | No of Poultry Mother Unit opened | 0 | 0 | 0
5.13 | No of Non-farm PG formed | 0 | 0 | 0
5.14 | No of DCS formed (Dairy Cooperative Society) | 0 | 0 | 0
5.15 | No of SHG members registered in DCS | 0 | 0 | 0
5.16 | No of DCS promoted as resource DCS | 0 | 0 | 0
5.17 | No of Kishan days organized | 0 | 0 | 0
5.18 | No of Cluster Adhibesan organized | 0 | 0 | 0
5.19 | No of VO having efficient equipment management system | 0 | 0 | 0
5.20 | No of MP for Moong Cultivation completed | 0 | 0 | 0
5.21 | No of Acres of land under Moong Cultivation | 0 | 0 | 0
Result- 6 | Skills Development (JOBs)
6.1 | No of youth identified - data base prepared | 0 | 0 | 0
6.2 | No of Youth Placed | 0 | 0 | 0
6.3 | No of Youth Placed by service sector agency | 0 | 0 | 0
6.4 | No. of Youth Trained | 0 | 0 | 0
Result- 7 | Project Monitoring and Learning System established, including RLMIS, learning and experience sharing forums at different levels of Project management
7.1 | % of Cluster generating reports through MIS | 0 | 0 | 0
7.2 | % of VO submitting Receipt & payment on monthly basis | 0 | 0 | 0
7.3 | No of SHG graded | 32 | 0 | 32
7.4 | No of VO rated | 0 | 0 | 0
7.5 | No of Case study generated (Best Practice - Institution Program,Procurement, Financial) | 0 | 0 | 0
Result- 8 | Project implementation procedures and agreed business standards are followed for at least 80% of project interventions at any point in time
8.1 | No of MOU signed between BPIU and CBOs | 0 | 0 | 0
8.2 | No of VO received establishment materials | 0 | 0 | 0
8.3 | No of CLF received establishment materials | 0 | 0 | 0
Result- 9 | Status of Utilization Certificate (UC)
9.1 | No of UC received for ICF (SHG) | 0 | 0 | 0
9.2 | No of UC received for HRF (VO) | 0 | 0 | 0
9.3 | No of UC received for FSF (VO) | 0 | 0 | 0
9.4 | No of UC received for VO Establishment Materials | 0 | 0 | 0
9.5 | No of CBOs trained on Community Procurement | 0 | 0 | 0
9.6 | % of Community Cadre payment made till month | 80 | 0 | 80

## Pipra
MPPR of BPIU - Pipra Month - December . 2014
Sl. | DESCRIPTION OF PROGRAM | Cummalitive achievement Previous month | Cummalitive achievement in current month | Cummalative achievement
1 | No. of Panchayats entered | 4 | 0 | 4
2 | No of revenue villages Covered | 3 | 0 | 3
3 | No of Village saturated (geographically) - certification from the VO & passed by Gram Sabha | 0 | 0 | 0
Result-1 | Formation of self reliant and inclusive community institutions including SHGs, Village Organizations and Federations. (IB-CB)
1.1 | No Of SGSY Groups Validated | 15 | 0 | 15
1.2 | No Of SGSY Groups Adopted | 0 | 0 | 0
1.3 | Total No of SHG formed (C1- ……... , C2- ………., C3-……….) *** | 188 | 86 | 274
1.4 | TOTAL NO OF POOR MOBILISED | 2275 | 860 | 3135
a | No. of SC | 766 | 0 | 766
b | No. ST | 0 | 0 | 0
c | No.EBC | 340 | 0 | 340
d | No. OBC | 236 | 0 | 236
e | No. Minority | 96 | 0 | 96
f | General | 45 | 0 | 45
1.5 | No. of predominantly SC-SHGs(SC>=50%) | 0 | 0 | 0
1.6 | No. of predominantly ST-SHGs(ST>=50%) | 0 | 0 | 0
1.7 | No. of predominantly Minority-SHGs(Minority >=50%) | 0 | 0 | 0
1.8 | No. of Village Organisation Formed (C1- …….., C2-….….., C3- ……..) *** | 0 | 0 | 0
1.9 | No. of 4 months old SHGs Part of Village Organisation | 0 | 0 | 0
1.10 | No. of CLF Formed | 0 | 0 | 0
1.11 | No. of one year old VO part of CLF | 0 | 0 | 0
1.12 | No. of VO Registered under Bihar self supporting cooperative Society Act-1996 | 0 | 0 | 0
Result-2 | COMMUNITY CADRES
2.1 | Number of CM working | 28 | 3 | 31
2.2 | Number of VO Book Keepers working | 0 | 0 | 0
2.3 | Number of Internal CRPs - SHG Formation working | 0 | 0 | 0
2.4 | Number of Internal CRPs-VO formation working | 0 | 0 | 0
2.5 | Number of Internal CRPs -Master Trainer working | 0 | 0 | 0
2.6 | No. of TSC CRP identified/Trained | 0 | 0 | 0
2.7 | No of Bank Mitra working | 1 | 0 | 1
2.8 | No of VRP is work in the Agriculture Intervention | 0 | 0 | 0
2.9 | No of Skilled Extension Worker (SEW)in Agriculture Intervention | 0 | 0 | 0
2.10 | No of JRP working | 0 | 0 | 0
2.11 | No of Jeevika Saheli working | 0 | 0 | 0
Result- 3 | Micro Finance
3.1 | No. of SHGs having Bank A/C | 77 | 18 | 95
3.2 | No of VOs having Bank Account | 0 | 0 | 0
3.3 | No of eligible SHGs ( six month old SHG + following PANCHSUTRA ) financed by Banks (Credit Linkage) | 0 | 0 | 0
3.4 | Amount Loaned by Banks to SHG | 0 | 0 | 0
3.5 | No of Groups repeat financed by Banks (Second Dose) | 0 | 0 | 0
3.6 | Repeat financed Amount by Banks | 0 | 0 | 0
3.7 | No. of SHG member Linked with insurance programme. (AABY) | 0 | 0 | 0
3.8 | No of SHG member Linked with RSBY - Health insurance | 0 | 0 | 0
3.9 | No of groups to complete Micro Planing exercise within 3 months of Group formation | 0 | 0 | 0
3.10 | No of Groups LCM done | 53 | 0 | 53
3.11 | Total No. of Groups received ICF through VO/BPIU | 51 | 0 | 51
3.12 | No of Group Revisited for Micro plan | 0 | 0 | 0
3.13 | No of trained CM/CRP generating Micro Plan | 7 | 0 | 7
Result-4 | Social Development & Health Nutrition
4.1 | No of SHG members made signature literate | 698 | 45 | 743
4.2 | No of SHG made financial literate | 0 | 0 | 0
4.3 | Sanitation Programme initiated with number of SHGs | 0 | 0 | 0
4.4 | No. of SHG HHs linked with Social Security Programme | 0 | 0 | 0
4.5 | No of Social Security Resource Person working | 0 | 0 | 0
4.6 | NO of Social Security community professional working | 0 | 0 | 0
4.7 | Number of VO participating in HRF | 0 | 0 | 0
4.8 | No. of members benefitted in HRF | 0 | 0 | 0
4.9 | Number of VO participating in FSF | 0 | 0 | 0
4.10 | No of HH linked with FS Intervention | 0 | 0 | 0
4.11 | No of VO involved in PDS | 0 | 0 | 0
4.12 | No of VO involved in CNCC | 0 | 0 | 0
4.13 | No. VO Completed 1st Cycle of FS Member | 0 | 0 | 0
4.14 | No. VO Completed 2nd Cycle of FS Member | 0 | 0 | 0
4.15 | No. VO Completed 3rd Cycle of FS Member | 0 | 0 | 0
Result-5 | Livelihoods Activities
5.1 | No of SHG members registered in VO for SRI | 0 | 0 | 0
5.2 | No of SHG members registered in VO for SWI | 0 | 0 | 0
5.3 | No of SHG members registered in VO for Vegetable cultivation | 0 | 0 | 0
5.4 | No of Acres of land under Agriculture Intervention-SRI | 0 | 0 | 0
5.5 | No of Acres of land under Agriculture Intervention- SWI | 0 | 0 | 0
5.6 | No of Acres of land under Vegetable Intervention- | 0 | 0 | 0
5.7 | No of vermi-compost pit will be prepared | 0 | 0 | 0
5.8 | No of SHG members is registered in existing DCS | 0 | 0 | 0
5.9 | No of agri culture PG formed | 0 | 0 | 0
5.10 | No of PG having Bank A/C opened | 0 | 0 | 0
5.11 | No of Vegetable PG formed | 0 | 0 | 0
5.12 | No of Poultry Mother Unit opened | 0 | 0 | 0
5.13 | No of Non-farm PG formed | 0 | 0 | 0
5.14 | No of DCS formed (Dairy Cooperative Society) | 0 | 0 | 0
5.15 | No of SHG members registered in DCS | 0 | 0 | 0
5.16 | No of DCS promoted as resource DCS | 0 | 0 | 0
5.17 | No of Kishan days organized | 0 | 0 | 0
5.18 | No of Cluster Adhibesan organized | 0 | 0 | 0
5.19 | No of VO having efficient equipment management system | 0 | 0 | 0
5.20 | No of MP for Moong Cultivation completed | 0 | 0 | 0
5.21 | No of Acres of land under Moong Cultivation | 0 | 0 | 0
Result- 6 | Skills Development (JOBs)
6.1 | No of youth identified - data base prepared | 0 | 0 | 0
6.2 | No of Youth Placed | 0 | 0 | 0
6.3 | No of Youth Placed by service sector agency | 0 | 0 | 0
6.4 | No. of Youth Trained | 0 | 0 | 0
Result- 7 | Project Monitoring and Learning System established, including RLMIS, learning and experience sharing forums at different levels of Project management
7.1 | % of Cluster generating reports through MIS | 0 | 0 | 0
7.2 | % of VO submitting Receipt & payment on monthly basis | 0 | 0 | 0
7.3 | No of SHG graded | 0 | 0 | 0
7.4 | No of VO rated | 0 | 0 | 0
7.5 | No of Case study generated (Best Practice - Institution Program,Procurement, Financial) | 0 | 0 | 0
Result- 8 | Project implementation procedures and agreed business standards are followed for at least 80% of project interventions at any point in time
8.1 | No of MOU signed between BPIU and CBOs | 0 | 0 | 0
8.2 | No of VO received establishment materials | 0 | 0 | 0
8.3 | No of CLF received establishment materials | 0 | 0 | 0
Result- 9 | Status of Utilization Certificate (UC)
9.1 | No of UC received for ICF (SHG) | 0 | 0 | 0
9.2 | No of UC received for HRF (VO) | 0 | 0 | 0
9.3 | No of UC received for FSF (VO) | 0 | 0 | 0
9.4 | No of UC received for VO Establishment Materials | 0 | 0 | 0
9.5 | No of CBOs trained on Community Procurement | 0 | 0 | 0
9.6 | % of Community Cadre payment made till month | 0 | 0 | 0

## Kisanpur
MPPR of BPIU - Kisanpur Month - December . 2014
Sl. | DESCRIPTION OF PROGRAM | Cummalitive achievement Previous month | Cummalitive achievement in current month | Cummalative achievement
1 | No. of Panchayats entered | 5 | 2 | 7
2 | No of revenue villages Covered | 11 | 2 | 13
3 | No of Village saturated (geographically) - certification from the VO & passed by Gram Sabha | 0 | 0 | 0
Result-1 | Formation of self reliant and inclusive community institutions including SHGs, Village Organizations and Federations. (IB-CB)
1.1 | No Of SGSY Groups Validated | 85 | 0 | 85
1.2 | No Of SGSY Groups Adopted | 2 | 5 | 7
1.3 | Total No of SHG formed (C1- ……... , C2- ………., C3-……….) *** | 135 | 64 | 199
1.4 | TOTAL NO OF POOR MOBILISED | 1679 | 881 | 2560
a | No. of SC | 0 | 630 | 630
b | No. ST | 0 | 0 | 0
c | No.EBC | 0 | 834 | 834
d | No. OBC | 0 | 475 | 475
e | No. Minority | 0 | 575 | 575
f | General | 0 | 46 | 46
1.5 | No. of predominantly SC-SHGs(SC>=50%) | 0 | 37 | 37
1.6 | No. of predominantly ST-SHGs(ST>=50%) | 0 | 0 | 0
1.7 | No. of predominantly Minority-SHGs(Minority >=50%) | 0 | 60 | 60
1.8 | No. of Village Organisation Formed (C1- …….., C2-….….., C3- ……..) *** | 0 | 5 | 5
1.9 | No. of 4 months old SHGs Part of Village Organisation | 0 | 47 | 47
1.10 | No. of CLF Formed | 0 | 0 | 0
1.11 | No. of one year old VO part of CLF | 0 | 0 | 0
1.12 | No. of VO Registered under Bihar self supporting cooperative Society Act-1996 | 0 | 0 | 0
Result-2 | COMMUNITY CADRES
2.1 | Number of CM working | 19 | 2 | 21
2.2 | Number of VO Book Keepers working | 0 | 0 | 0
2.3 | Number of Internal CRPs - SHG Formation working | 0 | 0 | 0
2.4 | Number of Internal CRPs-VO formation working | 0 | 0 | 0
2.5 | Number of Internal CRPs -Master Trainer working | 0 | 0 | 0
2.6 | No. of TSC CRP identified/Trained | 11 | 0 | 11
2.7 | No of Bank Mitra working | 0 | 0 | 0
2.8 | No of VRP is work in the Agriculture Intervention | 0 | 0 | 0
2.9 | No of Skilled Extension Worker (SEW)in Agriculture Intervention | 0 | 0 | 0
2.10 | No of JRP working | 0 | 0 | 0
2.11 | No of Jeevika Saheli working | 0 | 0 | 0
Result- 3 | Micro Finance
3.1 | No. of SHGs having Bank A/C | 31 | 10 | 41
3.2 | No of VOs having Bank Account | 0 | 0 | 0
3.3 | No of eligible SHGs ( six month old SHG + following PANCHSUTRA ) financed by Banks (Credit Linkage) | 0 | 0 | 0
3.4 | Amount Loaned by Banks to SHG | 0 | 0 | 0
3.5 | No of Groups repeat financed by Banks (Second Dose) | 0 | 0 | 0
3.6 | Repeat financed Amount by Banks | 0 | 0 | 0
3.7 | No. of SHG member Linked with insurance programme. (AABY) | 0 | 0 | 0
3.8 | No of SHG member Linked with RSBY - Health insurance | 0 | 0 | 0
3.9 | No of groups to complete Micro Planing exercise within 3 months of Group formation | 50 | 7 | 57
3.10 | No of Groups LCM done | 29 | 0 | 29
3.11 | Total No. of Groups received ICF through VO/BPIU | 10 | 19 | 29
3.12 | No of Group Revisited for Micro plan | 0 | 0 | 0
3.13 | No of trained CM/CRP generating Micro Plan | 0 | 0 | 0
Result-4 | Social Development & Health Nutrition
4.1 | No of SHG members made signature literate | 360 | 328 | 688
4.2 | No of SHG made financial literate | 0 | 0 | 0
4.3 | Sanitation Programme initiated with number of SHGs | 0 | 0 | 0
4.4 | No. of SHG HHs linked with Social Security Programme | 0 | 0 | 0
4.5 | No of Social Security Resource Person working | 0 | 0 | 0
4.6 | NO of Social Security community professional working | 0 | 0 | 0
4.7 | Number of VO participating in HRF | 0 | 0 | 0
4.8 | No. of members benefitted in HRF | 0 | 0 | 0
4.9 | Number of VO participating in FSF | 0 | 0 | 0
4.10 | No of HH linked with FS Intervention | 0 | 0 | 0
4.11 | No of VO involved in PDS | 0 | 0 | 0
4.12 | No of VO involved in CNCC | 0 | 0 | 0
4.13 | No. VO Completed 1st Cycle of FS Member | 0 | 0 | 0
4.14 | No. VO Completed 2nd Cycle of FS Member | 0 | 0 | 0
4.15 | No. VO Completed 3rd Cycle of FS Member | 0 | 0 | 0
Result-5 | Livelihoods Activities
5.1 | No of SHG members registered in VO for SRI | 0 | 0 | 0
5.2 | No of SHG members registered in VO for SWI | 0 | 0 | 0
5.3 | No of SHG members registered in VO for Vegetable cultivation | 0 | 0 | 0
5.4 | No of Acres of land under Agriculture Intervention-SRI | 0 | 0 | 0
5.5 | No of Acres of land under Agriculture Intervention- SWI | 0 | 0 | 0
5.6 | No of Acres of land under Vegetable Intervention- | 0 | 0 | 0
5.7 | No of vermi-compost pit will be prepared | 0 | 0 | 0
5.8 | No of SHG members is registered in existing DCS | 0 | 0 | 0
5.9 | No of agri culture PG formed | 0 | 0 | 0
5.10 | No of PG having Bank A/C opened | 0 | 0 | 0
5.11 | No of Vegetable PG formed | 0 | 0 | 0
5.12 | No of Poultry Mother Unit opened | 0 | 0 | 0
5.13 | No of Non-farm PG formed | 0 | 0 | 0
5.14 | No of DCS formed (Dairy Cooperative Society) | 0 | 0 | 0
5.15 | No of SHG members registered in DCS | 0 | 0 | 0
5.16 | No of DCS promoted as resource DCS | 0 | 0 | 0
5.17 | No of Kishan days organized | 0 | 0 | 0
5.18 | No of Cluster Adhibesan organized | 0 | 0 | 0
5.19 | No of VO having efficient equipment management system | 0 | 0 | 0
5.20 | No of MP for Moong Cultivation completed | 0 | 0 | 0
5.21 | No of Acres of land under Moong Cultivation | 0 | 0 | 0
Result- 6 | Skills Development (JOBs)
6.1 | No of youth identified - data base prepared | 0 | 0 | 0
6.2 | No of Youth Placed | 0 | 0 | 0
6.3 | No of Youth Placed by service sector agency | 0 | 0 | 0
6.4 | No. of Youth Trained | 0 | 0 | 0
Result- 7 | Project Monitoring and Learning System established, including RLMIS, learning and experience sharing forums at different levels of Project management
7.1 | % of Cluster generating reports through MIS | 0 | 0 | 0
7.2 | % of VO submitting Receipt & payment on monthly basis | 0 | 0 | 0
7.3 | No of SHG graded | 0 | 0 | 0
7.4 | No of VO rated | 0 | 0 | 0
7.5 | No of Case study generated (Best Practice - Institution Program,Procurement, Financial) | 0 | 0 | 0
Result- 8 | Project implementation procedures and agreed business standards are followed for at least 80% of project interventions at any point in time
8.1 | No of MOU signed between BPIU and CBOs | 0 | 0 | 0
8.2 | No of VO received establishment materials | 0 | 0 | 0
8.3 | No of CLF received establishment materials | 0 | 0 | 0
Result- 9 | Status of Utilization Certificate (UC)
9.1 | No of UC received for ICF (SHG) | 0 | 6 | 6
9.2 | No of UC received for HRF (VO) | 0 | 0 | 0
9.3 | No of UC received for FSF (VO) | 0 | 0 | 0
9.4 | No of UC received for VO Establishment Materials | 0 | 0 | 0
9.5 | No of CBOs trained on Community Procurement | 0 | 0 | 0
9.6 | % of Community Cadre payment made till month | 0 | 0 | 0

## Raghopur
MPPR of BPIU - Raghopur Month - December . 2014
Sl. | DESCRIPTION OF PROGRAM | Cummalitive achievement Previous month | Cummalitive achievement in current month | Cummalative achievement
1 | No. of Panchayats entered | 4 | 4 | 8
2 | No of revenue villages Covered | 14 | 5 | 19
3 | No of Village saturated (geographically) - certification from the VO & passed by Gram Sabha | 0 | 0 | 0
Result-1 | Formation of self reliant and inclusive community institutions including SHGs, Village Organizations and Federations. (IB-CB)
1.1 | No Of SGSY Groups Validated | 71 | 11 | 82
1.2 | No Of SGSY Groups Adopted | 0 | 3 | 3
1.3 | Total No of SHG formed (C1- ……... , C2- ………., C3-……….) *** | 151 | 78 | 229
1.4 | TOTAL NO OF POOR MOBILISED | 1783 | 901 | 2684
a | No. of SC | 730 | 251 | 981
b | No. ST | 0 | 0 | 0
c | No.EBC | 427 | 230 | 657
d | No. OBC | 409 | 185 | 594
e | No. Minority | 125 | 235 | 360
f | General | 92 | 0 | 92
1.5 | No. of predominantly SC-SHGs(SC>=50%) | 0 | 75 | 75
1.6 | No. of predominantly ST-SHGs(ST>=50%) | 0 | 0 | 0
1.7 | No. of predominantly Minority-SHGs(Minority >=50%) | 0 | 39 | 39
1.8 | No. of Village Organisation Formed (C1- …….., C2-….….., C3- ……..) *** | 0 | 1 | 1
1.9 | No. of 4 months old SHGs Part of Village Organisation | 0 | 10 | 10
1.10 | No. of CLF Formed | 0 | 0 | 0
1.11 | No. of one year old VO part of CLF | 0 | 0 | 0
1.12 | No. of VO Registered under Bihar self supporting cooperative Society Act-1996 | 0 | 0 | 0
Result-2 | COMMUNITY CADRES
2.1 | Number of CM working | 17 | 17 | 34
2.2 | Number of VO Book Keepers working | 0 | 0 | 0
2.3 | Number of Internal CRPs - SHG Formation working | 0 | 0 | 0
2.4 | Number of Internal CRPs-VO formation working | 0 | 0 | 0
2.5 | Number of Internal CRPs -Master Trainer working | 0 | 0 | 0
2.6 | No. of TSC CRP identified/Trained | 0 | 0 | 0
2.7 | No of Bank Mitra working | 0 | 0 | 0
2.8 | No of VRP is work in the Agriculture Intervention | 0 | 0 | 0
2.9 | No of Skilled Extension Worker (SEW)in Agriculture Intervention | 0 | 0 | 0
2.10 | No of JRP working | 0 | 0 | 0
2.11 | No of Jeevika Saheli working | 0 | 0 | 0
Result- 3 | Micro Finance
3.1 | No. of SHGs having Bank A/C | 43 | 23 | 66
3.2 | No of VOs having Bank Account | 0 | 0 | 0
3.3 | No of eligible SHGs ( six month old SHG + following PANCHSUTRA ) financed by Banks (Credit Linkage) | 0 | 0 | 0
3.4 | Amount Loaned by Banks to SHG | 0 | 0 | 0
3.5 | No of Groups repeat financed by Banks (Second Dose) | 0 | 0 | 0
3.6 | Repeat financed Amount by Banks | 0 | 0 | 0
3.7 | No. of SHG member Linked with insurance programme. (AABY) | 0 | 0 | 0
3.8 | No of SHG member Linked with RSBY - Health insurance | 0 | 0 | 0
3.9 | No of groups to complete Micro Planing exercise within 3 months of Group formation | 18 | 7 | 25
3.10 | No of Groups LCM done | 0 | 11 | 11
3.11 | Total No. of Groups received ICF through VO/BPIU | 0 | 0 | 0
3.12 | No of Group Revisited for Micro plan | 0 | 0 | 0
3.13 | No of trained CM/CRP generating Micro Plan | 0 | 0 | 0
Result-4 | Social Development & Health Nutrition
4.1 | No of SHG members made signature literate | 360 | 56 | 416
4.2 | No of SHG made financial literate | 0 | 0 | 0
4.3 | Sanitation Programme initiated with number of SHGs | 0 | 0 | 0
4.4 | No. of SHG HHs linked with Social Security Programme | 0 | 0 | 0
4.5 | No of Social Security Resource Person working | 0 | 0 | 0
4.6 | NO of Social Security community professional working | 0 | 0 | 0
4.7 | Number of VO participating in HRF | 0 | 0 | 0
4.8 | No. of members benefitted in HRF | 0 | 0 | 0
4.9 | Number of VO participating in FSF | 0 | 0 | 0
4.10 | No of HH linked with FS Intervention | 0 | 0 | 0
4.11 | No of VO involved in PDS | 0 | 0 | 0
4.12 | No of VO involved in CNCC | 0 | 0 | 0
4.13 | No. VO Completed 1st Cycle of FS Member | 0 | 0 | 0
4.14 | No. VO Completed 2nd Cycle of FS Member | 0 | 0 | 0
4.15 | No. VO Completed 3rd Cycle of FS Member | 0 | 0 | 0
Result-5 | Livelihoods Activities
5.1 | No of SHG members registered in VO for SRI | 0 | 0 | 0
5.2 | No of SHG members registered in VO for SWI | 0 | 0 | 0
5.3 | No of SHG members registered in VO for Vegetable cultivation | 0 | 0 | 0
5.4 | No of Acres of land under Agriculture Intervention-SRI | 0 | 0 | 0
5.5 | No of Acres of land under Agriculture Intervention- SWI | 0 | 0 | 0
5.6 | No of Acres of land under Vegetable Intervention- | 0 | 0 | 0
5.7 | No of vermi-compost pit will be prepared | 0 | 0 | 0
5.8 | No of SHG members is registered in existing DCS | 0 | 0 | 0
5.9 | No of agri culture PG formed | 0 | 0 | 0
5.10 | No of PG having Bank A/C opened | 0 | 0 | 0
5.11 | No of Vegetable PG formed | 0 | 0 | 0
5.12 | No of Poultry Mother Unit opened | 0 | 0 | 0
5.13 | No of Non-farm PG formed | 0 | 0 | 0
5.14 | No of DCS formed (Dairy Cooperative Society) | 0 | 0 | 0
5.15 | No of SHG members registered in DCS | 0 | 0 | 0
5.16 | No of DCS promoted as resource DCS | 0 | 0 | 0
5.17 | No of Kishan days organized | 0 | 0 | 0
5.18 | No of Cluster Adhibesan organized | 0 | 0 | 0
5.19 | No of VO having efficient equipment management system | 0 | 0 | 0
5.20 | No of MP for Moong Cultivation completed | 0 | 0 | 0
5.21 | No of Acres of land under Moong Cultivation | 0 | 0 | 0
Result- 6 | Skills Development (JOBs)
6.1 | No of youth identified - data base prepared | 0 | 0 | 0
6.2 | No of Youth Placed | 0 | 0 | 0
6.3 | No of Youth Placed by service sector agency | 0 | 0 | 0
6.4 | No. of Youth Trained | 0 | 0 | 0
Result- 7 | Project Monitoring and Learning System established, including RLMIS, learning and experience sharing forums at different levels of Project management
7.1 | % of Cluster generating reports through MIS | 0 | 0 | 0
7.2 | % of VO submitting Receipt & payment on monthly basis | 0 | 0 | 0
7.3 | No of SHG graded | 18 | 7 | 25
7.4 | No of VO rated | 0 | 0 | 0
7.5 | No of Case study generated (Best Practice - Institution Program,Procurement, Financial) | 0 | 0 | 0
Result- 8 | Project implementation procedures and agreed business standards are followed for at least 80% of project interventions at any point in time
8.1 | No of MOU signed between BPIU and CBOs | 0 | 0 | 0
8.2 | No of VO received establishment materials | 0 | 0 | 0
8.3 | No of CLF received establishment materials | 0 | 0 | 0
Result- 9 | Status of Utilization Certificate (UC)
9.1 | No of UC received for ICF (SHG) | 0 | 0 | 0
9.2 | No of UC received for HRF (VO) | 0 | 0 | 0
9.3 | No of UC received for FSF (VO) | 0 | 0 | 0
9.4 | No of UC received for VO Establishment Materials | 0 | 0 | 0
9.5 | No of CBOs trained on Community Procurement | 0 | 0 | 0
9.6 | % of Community Cadre payment made till month | 0 | 0 | 0

## Saraigarh
MPPR of BPIU - Saraigarh Month - December . 2014
Sl. | DESCRIPTION OF PROGRAM | Cummalitive achievement Previous month | Cummalitive achievement in current month | Cummalative achievement
1 | No. of Panchayats entered | 5 | 1 | 6
2 | No of revenue villages Covered | 11 | 2 | 13
3 | No of Village saturated (geographically) - certification from the VO & passed by Gram Sabha | 0 | 0 | 0
Result-1 | Formation of self reliant and inclusive community institutions including SHGs, Village Organizations and Federations. (IB-CB)
1.1 | No Of SGSY Groups Validated | 181 | 0 | 181
1.2 | No Of SGSY Groups Adopted | 21 | 2 | 23
1.3 | Total No of SHG formed (C1- ……... , C2- ………., C3-……….) *** | 172 | 138 | 310
1.4 | TOTAL NO OF POOR MOBILISED | 2128 | 1560 | 3688
a | No. of SC | 463 | 552 | 1015
b | No. ST | 0 | 0 | 0
c | No.EBC | 558 | 488 | 1046
d | No. OBC | 912 | 427 | 1339
e | No. Minority | 146 | 120 | 266
f | General | 22 | 0 | 22
1.5 | No. of predominantly SC-SHGs(SC>=50%) | 0 | 0 | 0
1.6 | No. of predominantly ST-SHGs(ST>=50%) | 0 | 0 | 0
1.7 | No. of predominantly Minority-SHGs(Minority >=50%) | 0 | 0 | 0
1.8 | No. of Village Organisation Formed (C1- …….., C2-….….., C3- ……..) *** | 1 | 5 | 6
1.9 | No. of 4 months old SHGs Part of Village Organisation | 8 | 52 | 60
1.10 | No. of CLF Formed | 0 | 0 | 0
1.11 | No. of one year old VO part of CLF | 0 | 0 | 0
1.12 | No. of VO Registered under Bihar self supporting cooperative Society Act-1996 | 0 | 0 | 0
Result-2 | COMMUNITY CADRES
2.1 | Number of CM working | 20 | 12 | 32
2.2 | Number of VO Book Keepers working | 0 | 0 | 0
2.3 | Number of Internal CRPs - SHG Formation working | 0 | 0 | 0
2.4 | Number of Internal CRPs-VO formation working | 0 | 0 | 0
2.5 | Number of Internal CRPs -Master Trainer working | 0 | 0 | 0
2.6 | No. of TSC CRP identified/Trained | 0 | 0 | 0
2.7 | No of Bank Mitra working | 1 | 0 | 1
2.8 | No of VRP is work in the Agriculture Intervention | 0 | 0 | 0
2.9 | No of Skilled Extension Worker (SEW)in Agriculture Intervention | 0 | 0 | 0
2.10 | No of JRP working | 0 | 0 | 0
2.11 | No of Jeevika Saheli working | 0 | 0 | 0
Result- 3 | Micro Finance
3.1 | No. of SHGs having Bank A/C | 65 | 11 | 76
3.2 | No of VOs having Bank Account | 0 | 1 | 1
3.3 | No of eligible SHGs ( six month old SHG + following PANCHSUTRA ) financed by Banks (Credit Linkage) | 0 | 0 | 0
3.4 | Amount Loaned by Banks to SHG | 0 | 0 | 0
3.5 | No of Groups repeat financed by Banks (Second Dose) | 0 | 0 | 0
3.6 | Repeat financed Amount by Banks | 0 | 0 | 0
3.7 | No. of SHG member Linked with insurance programme. (AABY) | 0 | 0 | 0
3.8 | No of SHG member Linked with RSBY - Health insurance | 0 | 0 | 0
3.9 | No of groups to complete Micro Planing exercise within 3 months of Group formation | 36 | 0 | 36
3.10 | No of Groups LCM done | 14 | 45 | 59
3.11 | Total No. of Groups received ICF through VO/BPIU | 14 | 20 | 34
3.12 | No of Group Revisited for Micro plan | 12 | 0 | 12
3.13 | No of trained CM/CRP generating Micro Plan | 4 | 0 | 4
Result-4 | Social Development & Health Nutrition
4.1 | No of SHG members made signature literate | 44 | 10 | 54
4.2 | No of SHG made financial literate | 0 | 0 | 0
4.3 | Sanitation Programme initiated with number of SHGs | 0 | 0 | 0
4.4 | No. of SHG HHs linked with Social Security Programme | 0 | 0 | 0
4.5 | No of Social Security Resource Person working | 0 | 0 | 0
4.6 | NO of Social Security community professional working | 0 | 0 | 0
4.7 | Number of VO participating in HRF | 0 | 0 | 0
4.8 | No. of members benefitted in HRF | 0 | 0 | 0
4.9 | Number of VO participating in FSF | 0 | 0 | 0
4.10 | No of HH linked with FS Intervention | 0 | 0 | 0
4.11 | No of VO involved in PDS | 0 | 0 | 0
4.12 | No of VO involved in CNCC | 0 | 0 | 0
4.13 | No. VO Completed 1st Cycle of FS Member | 0 | 0 | 0
4.14 | No. VO Completed 2nd Cycle of FS Member | 0 | 0 | 0
4.15 | No. VO Completed 3rd Cycle of FS Member | 0 | 0 | 0
Result-5 | Livelihoods Activities
5.1 | No of SHG members registered in VO for SRI | 0 | 0 | 0
5.2 | No of SHG members registered in VO for SWI | 0 | 0 | 0
5.3 | No of SHG members registered in VO for Vegetable cultivation | 0 | 0 | 0
5.4 | No of Acres of land under Agriculture Intervention-SRI | 0 | 0 | 0
5.5 | No of Acres of land under Agriculture Intervention- SWI | 0 | 0 | 0
5.6 | No of Acres of land under Vegetable Intervention- | 0 | 0 | 0
5.7 | No of vermi-compost pit will be prepared | 0 | 0 | 0
5.8 | No of SHG members is registered in existing DCS | 0 | 0 | 0
5.9 | No of agri culture PG formed | 0 | 0 | 0
5.10 | No of PG having Bank A/C opened | 0 | 0 | 0
5.11 | No of Vegetable PG formed | 0 | 0 | 0
5.12 | No of Poultry Mother Unit opened | 0 | 0 | 0
5.13 | No of Non-farm PG formed | 0 | 0 | 0
5.14 | No of DCS formed (Dairy Cooperative Society) | 0 | 0 | 0
5.15 | No of SHG members registered in DCS | 0 | 0 | 0
5.16 | No of DCS promoted as resource DCS | 0 | 0 | 0
5.17 | No of Kishan days organized | 0 | 0 | 0
5.18 | No of Cluster Adhibesan organized | 0 | 0 | 0
5.19 | No of VO having efficient equipment management system | 0 | 0 | 0
5.20 | No of MP for Moong Cultivation completed | 0 | 0 | 0
5.21 | No of Acres of land under Moong Cultivation | 0 | 0 | 0
Result- 6 | Skills Development (JOBs)
6.1 | No of youth identified - data base prepared | 21 | 10 | 31
6.2 | No of Youth Placed | 0 | 0 | 0
6.3 | No of Youth Placed by service sector agency | 0 | 0 | 0
6.4 | No. of Youth Trained | 0 | 0 | 0
Result- 7 | Project Monitoring and Learning System established, including RLMIS, learning and experience sharing forums at different levels of Project management
7.1 | % of Cluster generating reports through MIS | 0 | 0 | 0
7.2 | % of VO submitting Receipt & payment on monthly basis | 0 | 0 | 0
7.3 | No of SHG graded | 0 | 0 | 0
7.4 | No of VO rated | 0 | 0 | 0
7.5 | No of Case study generated (Best Practice - Institution Program,Procurement, Financial) | 0 | 0 | 0
Result- 8 | Project implementation procedures and agreed business standards are followed for at least 80% of project interventions at any point in time
8.1 | No of MOU signed between BPIU and CBOs | 0 | 0 | 0
8.2 | No of VO received establishment materials | 0 | 0 | 0
8.3 | No of CLF received establishment materials | 0 | 0 | 0
Result- 9 | Status of Utilization Certificate (UC)
9.1 | No of UC received for ICF (SHG) | 2 | 6 | 8
9.2 | No of UC received for HRF (VO) | 0 | 0 | 0
9.3 | No of UC received for FSF (VO) | 0 | 0 | 0
9.4 | No of UC received for VO Establishment Materials | 0 | 0 | 0
9.5 | No of CBOs trained on Community Procurement | 0 | 0 | 0
9.6 | % of Community Cadre payment made till month | 0 | 0 | 0

## Nirmali
MPPR of BPIU - Nirmali Month - December . 2014
Sl. | DESCRIPTION OF PROGRAM | Cummalitive achievement Previous month | Cummalitive achievement in current month | Cummalative achievement
1 | No. of Panchayats entered | 4 | 0 | 4
2 | No of revenue villages Covered | 8 | 0 | 8
3 | No of Village saturated (geographically) - certification from the VO & passed by Gram Sabha | 0 | 0 | 0
Result-1 | Formation of self reliant and inclusive community institutions including SHGs, Village Organizations and Federations. (IB-CB)
1.1 | No Of SGSY Groups Validated | 80 | 0 | 80
1.2 | No Of SGSY Groups Adopted | 3 | 2 | 5
1.3 | Total No of SHG formed (C1- ……... , C2- ………., C3-……….) *** | 121 | 100 | 221
1.4 | TOTAL NO OF POOR MOBILISED | 1306 | 1253 | 2559
a | No. of SC | 286 | 252 | 538
b | No. ST | 7 | 3 | 10
c | No.EBC | 483 | 191 | 674
d | No. OBC | 262 | 727 | 989
e | No. Minority | 221 | 52 | 273
f | General | 47 | 28 | 75
1.5 | No. of predominantly SC-SHGs(SC>=50%) | 0 | 16 | 16
1.6 | No. of predominantly ST-SHGs(ST>=50%) | 0 | 0 | 0
1.7 | No. of predominantly Minority-SHGs(Minority >=50%) | 0 | 10 | 10
1.8 | No. of Village Organisation Formed (C1- …….., C2-….….., C3- ……..) *** | 1 | 1 | 2
1.9 | No. of 4 months old SHGs Part of Village Organisation | 10 | 10 | 20
1.10 | No. of CLF Formed | 0 | 0 | 0
1.11 | No. of one year old VO part of CLF | 0 | 0 | 0
1.12 | No. of VO Registered under Bihar self supporting cooperative Society Act-1996 | 0 | 0 | 0
Result-2 | COMMUNITY CADRES
2.1 | Number of CM working | 18 | 9 | 27
2.2 | Number of VO Book Keepers working | 0 | 1 | 1
2.3 | Number of Internal CRPs - SHG Formation working | 0 | 0 | 0
2.4 | Number of Internal CRPs-VO formation working | 0 | 0 | 0
2.5 | Number of Internal CRPs -Master Trainer working | 0 | 0 | 0
2.6 | No. of TSC CRP identified/Trained | 0 | 0 | 0
2.7 | No of Bank Mitra working | 0 | 0 | 0
2.8 | No of VRP is work in the Agriculture Intervention | 0 | 0 | 0
2.9 | No of Skilled Extension Worker (SEW)in Agriculture Intervention | 0 | 0 | 0
2.10 | No of JRP working | 0 | 0 | 0
2.11 | No of Jeevika Saheli working | 0 | 0 | 0
Result- 3 | Micro Finance
3.1 | No. of SHGs having Bank A/C | 37 | 20 | 57
3.2 | No of VOs having Bank Account | 0 | 0 | 0
3.3 | No of eligible SHGs ( six month old SHG + following PANCHSUTRA ) financed by Banks (Credit Linkage) | 0 | 0 | 0
3.4 | Amount Loaned by Banks to SHG | 0 | 0 | 0
3.5 | No of Groups repeat financed by Banks (Second Dose) | 0 | 0 | 0
3.6 | Repeat financed Amount by Banks | 0 | 0 | 0
3.7 | No. of SHG member Linked with insurance programme. (AABY) | 0 | 0 | 0
3.8 | No of SHG member Linked with RSBY - Health insurance | 0 | 0 | 0
3.9 | No of groups to complete Micro Planing exercise within 3 months of Group formation | 10 | 0 | 10
3.10 | No of Groups LCM done | 0 | 37 | 37
3.11 | Total No. of Groups received ICF through VO/BPIU | 5 | 12 | 17
3.12 | No of Group Revisited for Micro plan | 0 | 10 | 10
3.13 | No of trained CM/CRP generating Micro Plan | 0 | 0 | 0
Result-4 | Social Development & Health Nutrition
4.1 | No of SHG members made signature literate | 55 | 300 | 355
4.2 | No of SHG made financial literate | 0 | 55 | 55
4.3 | Sanitation Programme initiated with number of SHGs | 0 | 20 | 20
4.4 | No. of SHG HHs linked with Social Security Programme | 0 | 0 | 0
4.5 | No of Social Security Resource Person working | 0 | 0 | 0
4.6 | NO of Social Security community professional working | 0 | 0 | 0
4.7 | Number of VO participating in HRF | 0 | 0 | 0
4.8 | No. of members benefitted in HRF | 0 | 0 | 0
4.9 | Number of VO participating in FSF | 0 | 0 | 0
4.10 | No of HH linked with FS Intervention | 0 | 0 | 0
4.11 | No of VO involved in PDS | 0 | 0 | 0
4.12 | No of VO involved in CNCC | 0 | 0 | 0
4.13 | No. VO Completed 1st Cycle of FS Member | 0 | 0 | 0
4.14 | No. VO Completed 2nd Cycle of FS Member | 0 | 0 | 0
4.15 | No. VO Completed 3rd Cycle of FS Member | 0 | 0 | 0
Result-5 | Livelihoods Activities
5.1 | No of SHG members registered in VO for SRI | 0 | 0 | 0
5.2 | No of SHG members registered in VO for SWI | 0 | 0 | 0
5.3 | No of SHG members registered in VO for Vegetable cultivation | 0 | 0 | 0
5.4 | No of Acres of land under Agriculture Intervention-SRI | 0 | 0 | 0
5.5 | No of Acres of land under Agriculture Intervention- SWI | 0 | 0 | 0
5.6 | No of Acres of land under Vegetable Intervention- | 0 | 0 | 0
5.7 | No of vermi-compost pit will be prepared | 0 | 0 | 0
5.8 | No of SHG members is registered in existing DCS | 0 | 0 | 0
5.9 | No of agri culture PG formed | 0 | 0 | 0
5.10 | No of PG having Bank A/C opened | 0 | 0 | 0
5.11 | No of Vegetable PG formed | 0 | 0 | 0
5.12 | No of Poultry Mother Unit opened | 0 | 0 | 0
5.13 | No of Non-farm PG formed | 0 | 0 | 0
5.14 | No of DCS formed (Dairy Cooperative Society) | 0 | 0 | 0
5.15 | No of SHG members registered in DCS | 0 | 0 | 0
5.16 | No of DCS promoted as resource DCS | 0 | 0 | 0
5.17 | No of Kishan days organized | 0 | 0 | 0
5.18 | No of Cluster Adhibesan organized | 0 | 0 | 0
5.19 | No of VO having efficient equipment management system | 0 | 0 | 0
5.20 | No of MP for Moong Cultivation completed | 0 | 0 | 0
5.21 | No of Acres of land under Moong Cultivation | 0 | 0 | 0
Result- 6 | Skills Development (JOBs)
6.1 | No of youth identified - data base prepared | 0 | 0 | 0
6.2 | No of Youth Placed | 0 | 0 | 0
6.3 | No of Youth Placed by service sector agency | 0 | 0 | 0
6.4 | No. of Youth Trained | 0 | 0 | 0
Result- 7 | Project Monitoring and Learning System established, including RLMIS, learning and experience sharing forums at different levels of Project management
7.1 | % of Cluster generating reports through MIS | 0 | 0 | 0
7.2 | % of VO submitting Receipt & payment on monthly basis | 0 | 0 | 0
7.3 | No of SHG graded | 20 | 37 | 57
7.4 | No of VO rated | 0 | 1 | 1
7.5 | No of Case study generated (Best Practice - Institution Program,Procurement, Financial) | 0 | 0 | 0
Result- 8 | Project implementation procedures and agreed business standards are followed for at least 80% of project interventions at any point in time
8.1 | No of MOU signed between BPIU and CBOs | 0 | 0 | 0
8.2 | No of VO received establishment materials | 0 | 0 | 0
8.3 | No of CLF received establishment materials | 0 | 0 | 0
Result- 9 | Status of Utilization Certificate (UC)
9.1 | No of UC received for ICF (SHG) | 0 | 3 | 3
9.2 | No of UC received for HRF (VO) | 0 | 0 | 0
9.3 | No of UC received for FSF (VO) | 0 | 0 | 0
9.4 | No of UC received for VO Establishment Materials | 0 | 0 | 0
9.5 | No of CBOs trained on Community Procurement | 0 | 0 | 0
9.6 | % of Community Cadre payment made till month | 0 | 100 | 100

## Marauna
MPPR of BPIU - Marauna Month - December . 2014
Sl. | DESCRIPTION OF PROGRAM | Cummalitive achievement Previous month | Cummalitive achievement in current month | Cummalative achievement
1 | No. of Panchayats entered | 4 | 0 | 4
2 | No of revenue villages Covered | 13 | 0 | 13
3 | No of Village saturated (geographically) - certification from the VO & passed by Gram Sabha | 0 | 0 | 0
Result-1 | Formation of self reliant and inclusive community institutions including SHGs, Village Organizations and Federations. (IB-CB)
1.1 | No Of SGSY Groups Validated | 89 | 1 | 90
1.2 | No Of SGSY Groups Adopted | 22 | 0 | 22
1.3 | Total No of SHG formed (C1- ……... , C2- ………., C3-……….) *** | 176 | 92 | 268
1.4 | TOTAL NO OF POOR MOBILISED | 2009 | 1030 | 3039
a | No. of SC | 580 | 127 | 707
b | No. ST | 10 | 0 | 10
c | No.EBC | 832 | 431 | 1263
d | No. OBC | 468 | 374 | 842
e | No. Minority | 96 | 98 | 194
f | General | 23 | 0 | 23
1.5 | No. of predominantly SC-SHGs(SC>=50%) | 37 | 6 | 43
1.6 | No. of predominantly ST-SHGs(ST>=50%) | 0 | 0 | 0
1.7 | No. of predominantly Minority-SHGs(Minority >=50%) | 7 | 7 | 14
1.8 | No. of Village Organisation Formed (C1- …….., C2-….….., C3- ……..) *** | 2 | 2 | 4
1.9 | No. of 4 months old SHGs Part of Village Organisation | 20 | 18 | 38
1.10 | No. of CLF Formed | 0 | 0 | 0
1.11 | No. of one year old VO part of CLF | 0 | 0 | 0
1.12 | No. of VO Registered under Bihar self supporting cooperative Society Act-1996 | 0 | 0 | 0
Result-2 | COMMUNITY CADRES
2.1 | Number of CM working | 25 | 9 | 34
2.2 | Number of VO Book Keepers working | 0 | 2 | 2
2.3 | Number of Internal CRPs - SHG Formation working | 0 | 0 | 0
2.4 | Number of Internal CRPs-VO formation working | 0 | 0 | 0
2.5 | Number of Internal CRPs -Master Trainer working | 0 | 0 | 0
2.6 | No. of TSC CRP identified/Trained | 0 | 0 | 0
2.7 | No of Bank Mitra working | 0 | 2 | 2
2.8 | No of VRP is work in the Agriculture Intervention | 0 | 0 | 0
2.9 | No of Skilled Extension Worker (SEW)in Agriculture Intervention | 0 | 0 | 0
2.10 | No of JRP working | 0 | 0 | 0
2.11 | No of Jeevika Saheli working | 0 | 0 | 0
Result- 3 | Micro Finance
3.1 | No. of SHGs having Bank A/C | 91 | 31 | 122
3.2 | No of VOs having Bank Account | 0 | 2 | 2
3.3 | No of eligible SHGs ( six month old SHG + following PANCHSUTRA ) financed by Banks (Credit Linkage) | 0 | 0 | 0
3.4 | Amount Loaned by Banks to SHG | 0 | 0 | 0
3.5 | No of Groups repeat financed by Banks (Second Dose) | 0 | 0 | 0
3.6 | Repeat financed Amount by Banks | 0 | 0 | 0
3.7 | No. of SHG member Linked with insurance programme. (AABY) | 0 | 0 | 0
3.8 | No of SHG member Linked with RSBY - Health insurance | 0 | 0 | 0
3.9 | No of groups to complete Micro Planing exercise within 3 months of Group formation | 15 | 14 | 29
3.10 | No of Groups LCM done | 33 | 55 | 88
3.11 | Total No. of Groups received ICF through VO/BPIU | 33 | 26 | 59
3.12 | No of Group Revisited for Micro plan | 0 | 0 | 0
3.13 | No of trained CM/CRP generating Micro Plan | 5 | 1 | 6
Result-4 | Social Development & Health Nutrition
4.1 | No of SHG members made signature literate | 356 | 140 | 496
4.2 | No of SHG made financial literate | 0 | 0 | 0
4.3 | Sanitation Programme initiated with number of SHGs | 0 | 0 | 0
4.4 | No. of SHG HHs linked with Social Security Programme | 0 | 0 | 0
4.5 | No of Social Security Resource Person working | 0 | 0 | 0
4.6 | NO of Social Security community professional working | 0 | 0 | 0
4.7 | Number of VO participating in HRF | 0 | 0 | 0
4.8 | No. of members benefitted in HRF | 0 | 0 | 0
4.9 | Number of VO participating in FSF | 0 | 0 | 0
4.10 | No of HH linked with FS Intervention | 0 | 0 | 0
4.11 | No of VO involved in PDS | 0 | 0 | 0
4.12 | No of VO involved in CNCC | 0 | 0 | 0
4.13 | No. VO Completed 1st Cycle of FS Member | 0 | 0 | 0
4.14 | No. VO Completed 2nd Cycle of FS Member | 0 | 0 | 0
4.15 | No. VO Completed 3rd Cycle of FS Member | 0 | 0 | 0
Result-5 | Livelihoods Activities
5.1 | No of SHG members registered in VO for SRI | 0 | 0 | 0
5.2 | No of SHG members registered in VO for SWI | 0 | 0 | 0
5.3 | No of SHG members registered in VO for Vegetable cultivation | 0 | 0 | 0
5.4 | No of Acres of land under Agriculture Intervention-SRI | 0 | 0 | 0
5.5 | No of Acres of land under Agriculture Intervention- SWI | 0 | 0 | 0
5.6 | No of Acres of land under Vegetable Intervention- | 0 | 0 | 0
5.7 | No of vermi-compost pit will be prepared | 0 | 0 | 0
5.8 | No of SHG members is registered in existing DCS | 0 | 0 | 0
5.9 | No of agri culture PG formed | 0 | 0 | 0
5.10 | No of PG having Bank A/C opened | 0 | 0 | 0
5.11 | No of Vegetable PG formed | 0 | 0 | 0
5.12 | No of Poultry Mother Unit opened | 0 | 0 | 0
5.13 | No of Non-farm PG formed | 0 | 0 | 0
5.14 | No of DCS formed (Dairy Cooperative Society) | 0 | 0 | 0
5.15 | No of SHG members registered in DCS | 0 | 0 | 0
5.16 | No of DCS promoted as resource DCS | 0 | 0 | 0
5.17 | No of Kishan days organized | 0 | 0 | 0
5.18 | No of Cluster Adhibesan organized | 0 | 0 | 0
5.19 | No of VO having efficient equipment management system | 0 | 0 | 0
5.20 | No of MP for Moong Cultivation completed | 0 | 0 | 0
5.21 | No of Acres of land under Moong Cultivation | 0 | 0 | 0
Result- 6 | Skills Development (JOBs)
6.1 | No of youth identified - data base prepared | 0 | 0 | 0
6.2 | No of Youth Placed | 0 | 0 | 0
6.3 | No of Youth Placed by service sector agency | 0 | 0 | 0
6.4 | No. of Youth Trained | 0 | 0 | 0
Result- 7 | Project Monitoring and Learning System established, including RLMIS, learning and experience sharing forums at different levels of Project management
7.1 | % of Cluster generating reports through MIS | 0 | 0 | 0
7.2 | % of VO submitting Receipt & payment on monthly basis | 0 | 0 | 0
7.3 | No of SHG graded | 0 | 0 | 0
7.4 | No of VO rated | 0 | 0 | 0
7.5 | No of Case study generated (Best Practice - Institution Program,Procurement, Financial) | 0 | 0 | 0
Result- 8 | Project implementation procedures and agreed business standards are followed for at least 80% of project interventions at any point in time
8.1 | No of MOU signed between BPIU and CBOs | 0 | 2 | 2
8.2 | No of VO received establishment materials | 0 | 0 | 0
8.3 | No of CLF received establishment materials | 0 | 0 | 0
Result- 9 | Status of Utilization Certificate (UC)
9.1 | No of UC received for ICF (SHG) | 12 | 12 | 24
9.2 | No of UC received for HRF (VO) | 0 | 0 | 0
9.3 | No of UC received for FSF (VO) | 0 | 0 | 0
9.4 | No of UC received for VO Establishment Materials | 0 | 0 | 0
9.5 | No of CBOs trained on Community Procurement | 0 | 0 | 0
9.6 | % of Community Cadre payment made till month | 0 | 98 | 98

## Supaul Dist.
MPPR of DPCU - Supaul Month - December . 2014
Sl. | DESCRIPTION OF PROGRAM | Cummalitive achievement Previous month | Cummalitive achievement in current month | Cummalative achievement
1 | No. of Panchayats entered | 103 | 7 | 110
2 | No of revenue villages Covered | 239 | 17 | 256
3 | No of Village saturated (geographically) - certification from the VO & passed by Gram Sabha | 86 | 0 | 86
Result-1 | Formation of self reliant and inclusive community institutions including SHGs, Village Organizations and Federations. (IB-CB)
1.1 | No Of SGSY Groups Validated | 774 | 70 | 844
1.2 | No Of SGSY Groups Adopted | 52 | 54 | 106
1.3 | Total No of SHG formed (C1- ……... , C2- ………., C3-……….) *** | 6344 | 1173 | 7517
1.4 | TOTAL NO OF POOR MOBILISED | 75657 | 13349 | 89006
a | No. of SC | 19283 | 4088 | 23371
b | No. ST | 1117 | 48 | 1165
c | No.EBC | 19148 | 3085 | 22233
d | No. OBC | 22066 | 4155 | 26221
e | No. Minority | 10768 | 1411 | 12179
f | General | 2421 | 330 | 2751
1.5 | No. of predominantly SC-SHGs(SC>=50%) | 685 | 525 | 1210
1.6 | No. of predominantly ST-SHGs(ST>=50%) | 314 | 5 | 319
1.7 | No. of predominantly Minority-SHGs(Minority >=50%) | 1114 | 328 | 1442
1.8 | No. of Village Organisation Formed (C1- …….., C2-….….., C3- ……..) *** | 364 | 22 | 386
1.9 | No. of 4 months old SHGs Part of Village Organisation | 3733 | 187 | 3920
1.10 | No. of CLF Formed | 7 | 0 | 7
1.11 | No. of one year old VO part of CLF | 120 | 0 | 120
1.12 | No. of VO Registered under Bihar self supporting cooperative Society Act-1996 | 22 | 0 | 22
Result-2 | COMMUNITY CADRES
2.1 | Number of CM working | 690 | 93 | 783
2.2 | Number of VO Book Keepers working | 68 | 3 | 71
2.3 | Number of Internal CRPs - SHG Formation working | 377 | 0 | 377
2.4 | Number of Internal CRPs-VO formation working | 28 | 0 | 28
2.5 | Number of Internal CRPs -Master Trainer working | 37 | 0 | 37
2.6 | No. of TSC CRP identified/Trained | 11 | 0 | 11
2.7 | No of Bank Mitra working | 27 | 2 | 29
2.8 | No of VRP is work in the Agriculture Intervention | 177 | 1 | 178
2.9 | No of Skilled Extension Worker (SEW)in Agriculture Intervention | 0 | 0 | 0
2.10 | No of JRP working | 10 | 0 | 10
2.11 | No of Jeevika Saheli working | 67 | 31 | 98
Result- 3 | Micro Finance
3.1 | No. of SHGs having Bank A/C | 4834 | 203 | 5037
3.2 | No of VOs having Bank Account | 326 | 7 | 333
3.3 | No of eligible SHGs ( six month old SHG + following PANCHSUTRA ) financed by Banks (Credit Linkage) | 3375 | 0 | 3375
3.4 | Amount Loaned by Banks to SHG | 168750000 | 0 | 168750000
3.5 | No of Groups repeat financed by Banks (Second Dose) | 31 | 0 | 31
3.6 | Repeat financed Amount by Banks | 3100000 | 0 | 3100000
3.7 | No. of SHG member Linked with insurance programme. (AABY) | 17191 | 623 | 17814
3.8 | No of SHG member Linked with RSBY - Health insurance | 5989 | 0 | 5989
3.9 | No of groups to complete Micro Planing exercise within 3 months of Group formation | 4130 | 154 | 4284
3.10 | No of Groups LCM done | 3976 | 382 | 4358
3.11 | Total No. of Groups received ICF through VO/BPIU | 3923 | 104 | 4027
3.12 | No of Group Revisited for Micro plan | 12 | 10 | 22
3.13 | No of trained CM/CRP generating Micro Plan | 56 | 5 | 61
Result-4 | Social Development & Health Nutrition
4.1 | No of SHG members made signature literate | 33177 | 1729 | 34906
4.2 | No of SHG made financial literate | 31 | 55 | 86
4.3 | Sanitation Programme initiated with number of SHGs | 60 | 20 | 80
4.4 | No. of SHG HHs linked with Social Security Programme | 0 | 0 | 0
4.5 | No of Social Security Resource Person working | 0 | 0 | 0
4.6 | NO of Social Security community professional working | 0 | 0 | 0
4.7 | Number of VO participating in HRF | 192 | 0 | 192
4.8 | No. of members benefitted in HRF | 827 | 4 | 831
4.9 | Number of VO participating in FSF | 186 | 0 | 186
4.10 | No of HH linked with FS Intervention | 9017 | 92 | 9109
4.11 | No of VO involved in PDS | 0 | 0 | 0
4.12 | No of VO involved in CNCC | 0 | 0 | 0
4.13 | No. VO Completed 1st Cycle of FS Member | 65 | 0 | 65
4.14 | No. VO Completed 2nd Cycle of FS Member | 11 | 1 | 12
4.15 | No. VO Completed 3rd Cycle of FS Member | 5 | 0 | 5
Result-5 | Livelihoods Activities
5.1 | No of SHG members registered in VO for SRI | 10642 | 0 | 10642
5.2 | No of SHG members registered in VO for SWI | 1778 | 4342 | 6120
5.3 | No of SHG members registered in VO for Vegetable cultivation | 3262 | 1794 | 5056
5.4 | No of Acres of land under Agriculture Intervention-SRI | 6286 | 61 | 6347
5.5 | No of Acres of land under Agriculture Intervention- SWI | 2820 | 2339 | 5159
5.6 | No of Acres of land under Vegetable Intervention- | 2629 | 197 | 2826
5.7 | No of vermi-compost pit will be prepared | 3 | 3 | 6
5.8 | No of SHG members is registered in existing DCS | 0 | 0 | 0
5.9 | No of agri culture PG formed | 5 | 1 | 6
5.10 | No of PG having Bank A/C opened | 3 | 0 | 3
5.11 | No of Vegetable PG formed | 0 | 2 | 2
5.12 | No of Poultry Mother Unit opened | 1 | 1 | 2
5.13 | No of Non-farm PG formed | 0 | 0 | 0
5.14 | No of DCS formed (Dairy Cooperative Society) | 0 | 0 | 0
5.15 | No of SHG members registered in DCS | 0 | 0 | 0
5.16 | No of DCS promoted as resource DCS | 0 | 0 | 0
5.17 | No of Kishan days organized | 0 | 0 | 0
5.18 | No of Cluster Adhibesan organized | 0 | 0 | 0
5.19 | No of VO having efficient equipment management system | 44 | 0 | 44
5.20 | No of MP for Moong Cultivation completed | 1405 | 0 | 1405
5.21 | No of Acres of land under Moong Cultivation | 7317 | 0 | 7317
Result- 6 | Skills Development (JOBs)
6.1 | No of youth identified - data base prepared | 11470 | 440 | 11910
6.2 | No of Youth Placed | 65 | 0 | 65
6.3 | No of Youth Placed by service sector agency | 0 | 0 | 0
6.4 | No. of Youth Trained | 0 | 0 | 0
Result- 7 | Project Monitoring and Learning System established, including RLMIS, learning and experience sharing forums at different levels of Project management
7.1 | % of Cluster generating reports through MIS | 95 | 0 | 95
7.2 | % of VO submitting Receipt & payment on monthly basis | 285 | 0 | 285
7.3 | No of SHG graded | 3808 | 71 | 3879
7.4 | No of VO rated | 135 | 1 | 136
7.5 | No of Case study generated (Best Practice - Institution Program,Procurement, Financial) | 6 | 0 | 6
Result- 8 | Project implementation procedures and agreed business standards are followed for at least 80% of project interventions at any point in time
8.1 | No of MOU signed between BPIU and CBOs | 228 | 9 | 237
8.2 | No of VO received establishment materials | 84 | 0 | 84
8.3 | No of CLF received establishment materials | 3 | 1 | 4
Result- 9 | Status of Utilization Certificate (UC)
9.1 | No of UC received for ICF (SHG) | 1634 | 79 | 1713
9.2 | No of UC received for HRF (VO) | 32 | 9 | 41
9.3 | No of UC received for FSF (VO) | 38 | 7 | 45
9.4 | No of UC received for VO Establishment Materials | 0 | 0 | 0
9.5 | No of CBOs trained on Community Procurement | 122 | 1 | 123
9.6 | % of Community Cadre payment made till month | 130 | 278 | 408