## Triveniganj
MPPR OF -Triveniganj, Month -October . 2014
Sl. | DESCRIPTION OF PROGRAM | Cummalitive achievement Previous month | Cummalitive achievement in current month | Cummalative achievement
1 | No. of Panchayats | 18 | 0 | 18
2 | No of revenue villages to be covered | 36 | 0 | 36
3 | No of Village to be saturated (geographically) - certification from the VO | 22 | 0 | 22
Result-1 | Formation of self reliant and inclusive community institutions including SHGs, Village Organizations and Federations.
In-1.2 | Self managed self help groups (SHGs) established, covering at least 80% of the target households, 60% of formed SHGs into VO; and 40% of the formed VOs into BLF.
| Total SGSY groups in JEEViKA fold | 0 | 0 | 0
1.2.1 | Total No of SHG formed (C1- ……... , C2- ………., C3-……….) *** | 1412 | 46 | 1458
| TOTAL NO OF POOR MOBILISED | 16776 | 527 | 17303
| No. of SC | 4271 | 60 | 4331
| No. ST | 152 | 0 | 152
| No.EBC | 3023 | 241 | 3264
| No. OBC | 7308 | 211 | 7519
| No. Minority | 1928 | 15 | 1943
| General | 94 | 0 | 94
1.2.2 | No. of Village Organisation Formed (C1- …., C2-….., C3- ……..) *** | 82 | 2 | 84
1.2.3 | No. of 4 months old SHGs Part of Village Organisation | 860 | 20 | 880
| No. of CLF Formed | 1 | 0 | 1
| No. of one year old VO part of CLF | 15 | 0 | 15
| No. of VO Registered under Cooperative Society Act-1999 | 5 | 0 | 5
COMMUNITY CADRES - IB & CB
1.2.6 | Number of CM working | 139 | 3 | 142
1.2.7 | Number of VO Book Keepers working | 17 | 0 | 17
1.2.8 | Number of Internal CRPs - SHG Formation working | 62 | 0 | 62
1.2.9 | Number of Internal CRPs-VO formation working | 0 | 0 | 0
1.2.10 | Number of Internal CRPs -Master Trainer working | 0 | 0 | 0
| No. of TSC CRP identified/Trained | 0 | 0 | 0
In-1.3 | At least 75% of formed VOs accessed and managed project funds as per project processes at any point of time
1.3.1 | No of VOs having Bank Account | 79 | 0 | 79
1.3.2 | No of VO to manage Baalwaadi | 0 | 0 | 0
1.3.3 | No of VO to be promoted as Health & Nutrition center | 0 | 0 | 0
1.3.4 | Number of VO participating in HRF | 61 | 0 | 61
1.3.5 | No. of members benefitted in HRF | 178 | 0 | 178
1.3.6 | No of VO received funding for its Action Plan | 0 | 0 | 0
In-1.4
1.4.2 | No. of SHGs having Bank A/C | 1231 | 17 | 1248
1.4.3 | No of Bank Mitra working | 4 | 5 | 9
1.4.4 | No of eligible SHGs ( six month old SHG + following PANCHSUTRA ) financed by Banks | 850 | 0 | 850
1.4.5 | Amount Loaned by Banks to SHG | 42500000 | 0 | 42500000
1.4.6 | No of Groups repeat financed by Banks | 31 | 0 | 31
1.4.7 | Repeat financed Amount by Banks | 3100000 | 0 | 3100000
1.4.10 | No. of SHG members received bond under insurance programme. | 3495 | 0 | 3495
Result-2 | Establishment and use of Community Investment Fund for food security, social services, assets and income generation and service sector investment
2.1.1 | No of Group visited for Social plan | 0 | 0 | 0
2.1.2 | No of SHG members made signature literate | 7154 | 41 | 7195
2.1.3 | No of SHG made financial literate | 0 | 0 | 0
5 | No of SHG Member linked with RSBY - Health insurance | 1139 | 0 | 1139
2.1.5 | Sanitation Programme initiated with number of SHGs | 0 | 0 | 0
2.1.6 | No. of SHG HHs linked with Social Security Programme | 0 | 0 | 0
2.1.7 | No of Social Security Resource Person working | 0 | 0 | 0
2.1.8 | NO of Social Security community professional working | 0 | 0 | 0
2.1.9 | No of groups to complete Micro Planing exercise within 3 months of Group formation | 1031 | 0 | 1031
2.1.10 | No of Group Recd ICF through BPIU | 1023 | 0 | 1023
2.1.11 | No of Group Recd ICF through VO | 0 | 0 | 0
2.1.12 | Total No. of Groups received ICF through Vo/BPIU | 908 | 0 | 908
2.1.13 | No of groups/Farmers to complete Livelihoods Micro Planing exercise(SWI) | 0 | 0 | 0
2.1.14 | No of Group Revisited for Micro plan | 0 | 0 | 0
2.1.15 | No of trained CM generating Micro Plan | 0 | 0 | 0
Food security increased for 80% of target households as compared to the baseline
2.1.16 | Number of VO participating in FSF | 60 | 0 | 60
2.1.17 | No of HH linked with FS Intervention | 1563 | 0 | 1563
Result - 3 | Establishment and operationalization of Technical Assistance Fund.
In- 3.1 | At least 5 major business linkages established through public/private partnership by CBOs
3.1.1 | No of SHG members registered in VO for SRI | 2540 | 0 | 2540
3.1.2 | No of SHG members registered in VO for SWI | 460 | 0 | 460
3.1.3 | No of Acres of land will be under Agriculture Intervention-SRI | 117 | 0 | 117
3.1.4 | No of Acres of land will be under Agriculture Intervention- SWI | 0 | 0 | 0
3.1.5 | No of vermi-compost pit will be prepared | 0 | 0 | 0
3.1.6 | No of VRP will work in the Agriculture Intervention | 41 | 0 | 41
3.1.7 | No of Skilled Extension Worker will be created in Agriculture Intervention | 0 | 0 | 0
3.1.8 | No of SHG members will be registered in existing DCS | 0 | 0 | 0
3.1.9 | No of New DCS formed | 0 | 0 | 0
3.1.10 | No of SHG members will be registered in new DCS | 0 | 0 | 0
3.1.11 | No of DCS promoted as resource DCS | 0 | 0 | 0
3.1.13 | No of Kishan days will be organized | 0 | 0 | 0
3.1.14 | No of Cluster Adhibesan will be organized | 0 | 0 | 0
3.1.15 | No of VO have efficient equipment management system in place | 0 | 0 | 0
| Moong MP | 0 | 0 | 0
| No. of Katta for moong cultivation0 | 0 | 0 | 0
Atleast 5,000 Direct jobs created through Project facilitation and atleast 75% of them are getting sustained income
3.1.16 | No of youth identified - data base prepared | 2644 | 200 | 2844
3.1.17 | No of Youth Placed by direct placement | 10 | 0 | 10
3.1.18 | No of Youth Placed by service sector agency | 0 | 0 | 0
3.1.19 | No of JRP working | 3 | 0 | 3
Project Monitoring and Learning System established, including RLMIS, learning and experience sharing forums at different levels of Project management
3.1.20 | % of Cluster generating reports through MIS | 0 | 0 | 0
3.1.21 | No of SHG graded | 885 | 0 | 885
3.1.22 | No of VO rated | 74 | 0 | 74
3.1.23 | No of Case study generated ( Best Practice - Institution Program,Procurement, Financial Mgmt.) | 0 | 0 | 0
Result 4 | Project implementation procedures and agreed business standards are followed for at least 80% of project interventions at any point in time
4.2.1 | No of MOU signed between BPIU and Community Based Organisation | 70 | 0 | 70
4.2.2 | No of UC received within One month time of CIF release from CBOs | 46 | 0 | 46
4.2.3 | No of CBOs trained on Community Procurement | 2 | 0 | 2
4.2.4 | % of Community Cadre payment made in the Ist week of the month | 68 | 0 | 68
4.2.5 | No of VO submitting Receipt & payment on monthly basis | 35 | 0 | 35
4.2.6 | No of VO two months old procured establishment materials | 28 | 0 | 28
Note on B9: Anurag Kumar (MIS Exeucutive) Please mention in this field cluster wise no. of SHG.
Note on B17: Anurag Kumar (MIS Exeucutive) Please mention in this field cluster wise no. of VO.

## Basantpur
MPPR OF - Basantpur. Month - October 2014
Sl. | DESCRIPTION OF PROGRAM | Cummalitive achievement Previous month | Cummalitive achievement in current month | Cummalative achievement
1 | No. of Panchayats | 9 | 0 | 9
2 | No of revenue villages to be covered | 45 | 0 | 45
3 | No of Village to be saturated (geographically) - certification from the VO | 27 | 0 | 27
Result-1 | Formation of self reliant and inclusive community institutions including SHGs, Village Organizations and Federations.
In-1.2 | Self managed self help groups (SHGs) established, covering at least 80% of the target households, 60% of formed SHGs into VO; and 40% of the formed VOs into BLF.
| Total SGSY groups in JEEViKA fold | 31 | 49 | 80 | Only Validate
1.2.1 | Total No of SHG formed (C1- …... , C2-…..., C3-………….) *** | 845 | 13 | 858
| TOTAL NO OF POOR MOBILISED | 10202 | 141 | 10343
| No. of SC | 3331 | 26 | 3357
| No. ST | 0 | 20 | 20
| No.EBC | 2323 | 6 | 2329
| No. OBC | 2491 | 69 | 2560
| No. Minority | 3508 | 0 | 3508
| General | 206 | 20 | 226
1.2.2 | No. of Village Organisation Formed (C1-25, C2- 22, C3- 14) *** | 60 | 0 | 60
1.2.3 | No. of 6 months old SHGs Part of Village Organisation | 590 | 0 | 590
| No. of CLF Formed | 1 | 0 | 1
| No. of one year old VO part of CLF | 20 | 0 | 20
| No. of VO Registered under Cooperative Society Act-1999 | 5 | 0 | 5
COMMUNITY CADRES - IB & CB
1.2.6 | Number of CM working | 100 | 0 | 100
1.2.7 | Number of VO Book Keepers working | 13 | 0 | 13
1.2.8 | Number of Internal CRPs - SHG Formation working | 64 | 0 | 64
1.2.9 | Number of Internal CRPs-VO formation working | 0 | 0 | 0
1.2.10 | Number of Internal CRPs -Master Trainer working | 0 | 0 | 0
| No. of TSC CRP identified/Trained | 0 | 0 | 0
In-1.3 | At least 75% of formed VOs accessed and managed project funds as per project processes at any point of time
1.3.1 | No of VOs having Bank Account | 51 | 0 | 51
1.3.2 | No of VO to manage Baalwaadi | 0 | 0 | 0
1.3.3 | No of VO to be promoted as Health & Nutrition center | 0 | 0 | 0
1.3.4 | Number of VO participating in HRF | 33 | 0 | 33
1.3.5 | No. of members benefitted in HRF | 142 | 3 | 145
1.3.6 | No of VO received funding for its Action Plan | 0 | 0 | 0
In-1.4
1.4.2 | No. of SHGs having Bank A/C | 727 | 15 | 742
1.4.3 | No of Bank Mitra working | 4 | 0 | 4
1.4.4 | No of eligible SHGs ( six month old SHG + following PANCHSUTRA ) financed by Banks | 563 | 0 | 563
1.4.5 | Amount Loaned by Banks to SHG | 28150000 | 0 | 28150000
1.4.6 | No of Groups repeat financed by Banks | 0 | 0 | 0
1.4.7 | Repeat financed Amount by Banks | 0 | 0 | 0
1.4.10 | No. of SHG members received bond under insurance programme. | 733 | 0 | 733
Result-2 | Establishment and use of Community Investment Fund for food security, social services, assets and income generation and service sector investment
2.1.1 | No of Group visited for Social plan | 0 | 0 | 0
2.1.2 | No of SHG members made signature literate | 4102 | 350 | 4452
2.1.3 | No of SHG made financial literate | 0 | 0 | 0
5 | No of SHG Member linked with RSBY - Health insurance | 2000 | 0 | 2000
2.1.5 | Sanitation Programme initiated with number of SHGs | 0 | 0 | 0
2.1.6 | No. of SHG HHs linked with Social Security Programme | 0 | 0 | 0
2.1.7 | No of Social Security Resource Person working | 0 | 0 | 0
2.1.8 | NO of Social Security community professional working | 0 | 0 | 0
2.1.9 | No of groups to complete Micro Planing exercise within 3 months of Group formation | 707 | 5 | 712
2.1.10 | No of Group Recd ICF through BPIU | 0 | 0 | 0
2.1.11 | No of Group Recd ICF through VO | 0 | 0 | 0
2.1.12 | Total No. of Groups received ICF through Vo/BPIU | 597 | 0 | 597
2.1.13 | No of groups/Farmers to complete Livelihoods Micro Planing exercise(SWI) | 100 | 100 | 200
2.1.14 | No of Group Revisited for Micro plan | 0 | 0 | 0
2.1.15 | No of trained CM generating Micro Plan | 11 | 0 | 11
Food security increased for 80% of target households as compared to the baseline
2.1.16 | Number of VO participating in FSF | 41 | 0 | 41
2.1.17 | No of HH linked with FS Intervention | 1458 | 110 | 1568
Result - 3 | Establishment and operationalization of Technical Assistance Fund.
In- 3.1 | At least 5 major business linkages established through public/private partnership by CBOs
3.1.1 | No of SHG members registered in VO for SRI | 946 | 0 | 946
3.1.2 | No of SHG members registered in VO for SWI | 0 | 0 | 0
3.1.3 | No of Acres of land will be under Agriculture Intervention-SRI | 61 | 0 | 61
3.1.4 | No of Acres of land will be under Agriculture Intervention- SWI | 0 | 0 | 0
3.1.5 | No of vermi-compost pit will be prepared | 0 | 0 | 0
3.1.6 | No of VRP will work in the Agriculture Intervention | 26 | 4 | 30
3.1.7 | No of Skilled Extension Worker will be created in Agriculture Intervention | 0 | 0 | 0
3.1.8 | No of SHG members will be registered in existing DCS | 0 | 0 | 0
3.1.9 | No of New DCS formed | 0 | 0 | 0
3.1.10 | No of SHG members will be registered in new DCS | 0 | 0 | 0
3.1.11 | No of DCS promoted as resource DCS | 0 | 0 | 0
3.1.13 | No of Kishan days will be organized | 0 | 0 | 0
3.1.14 | No of Cluster Adhibesan will be organized | 0 | 0 | 0
3.1.15 | No of VO have efficient equipment management system in place | 0 | 0 | 0
| Moong MP | 0 | 0 | 0
| No. of Katta for moong cultivation0 | 0 | 0 | 0
Atleast 5,000 Direct jobs created through Project facilitation and atleast 75% of them are getting sustained income
3.1.16 | No of youth identified - data base prepared | 3136 | 100 | 3236
3.1.17 | No of Youth Placed by direct placement | 0 | 0 | 0
3.1.18 | No of Youth Placed by service sector agency | 0 | 0 | 0
3.1.19 | No of JRP working | 3 | 0 | 3
Project Monitoring and Learning System established, including RLMIS, learning and experience sharing forums at different levels of Project management
3.1.20 | % of Cluster generating reports through MIS | 95 | 0 | 95
3.1.21 | No of SHG graded | 707 | 5 | 712
3.1.22 | No of VO rated | 2 | 0 | 2
3.1.23 | No of Case study generated ( Best Practice - Institution Program,Procurement, Financial Mgmt.) | 6 | 0 | 6
Result 4 | Project implementation procedures and agreed business standards are followed for at least 80% of project interventions at any point in time
4.2.1 | No of MOU signed between BPIU and Community Based Organisation | 41 | 0 | 41
4.2.2 | No of UC received within One month time of CIF release from CBOs | 413 | 0 | 413
4.2.3 | No of CBOs trained on Community Procurement | 0 | 0 | 0
4.2.4 | % of Community Cadre payment made in the Ist week of the month | 0 | 0 | 0
4.2.5 | No of VO submitting Receipt & payment on monthly basis | 46 | 0 | 46
4.2.6 | No of VO two months old procured establishment materials | 23 | 0 | 23
Note on B9: Anurag Kumar (MIS Exeucutive) Please mention in this field cluster wise no. of SHG.
Note on B17: Anurag Kumar (MIS Exeucutive) Please mention in this field cluster wise no. of VO.

## Pratapganj
MPPR OF - Pratapganj . Month - October . 2014
Sl. | DESCRIPTION OF PROGRAM | Cummalitive achievement Previous month | Cummalitive achievement in current month | Cummalative achievement
1 | No. of Panchayats | 8 | 0 | 8
2 | No of revenue villages to be covered | 10 | 0 | 10
3 | No of Village to be saturated (geographically) - certification from the VO | 10 | 0 | 10
Result-1 | Formation of self reliant and inclusive community institutions including SHGs, Village Organizations and Federations.
In-1.2 | Self managed self help groups (SHGs) established, covering at least 80% of the target households, 60% of formed SHGs into VO; and 40% of the formed VOs into BLF.
| Total SGSY groups in JEEViKA fold | 47 | 0 | 47 | Only Validate
1.2.1 | Total No of SHG formed (C1- . . . . . . . . . . , C2- . . . . . . . . . . , C3- . . . . . . . . . . .) *** | 771 | 10 | 781
| TOTAL NO OF POOR MOBILISED | 9334 | 110 | 9444
| No. of SC | 1807 | 0 | 1807
| No. ST | 187 | 0 | 187
| No.EBC | 2951 | 58 | 3009
| No. OBC | 2886 | 12 | 2898
| No. Minority | 1223 | 40 | 1263
| General | 280 | 0 | 280
1.2.2 | No. of Village Organisation Formed (C1- . . . . . . . . . . , C2- . . . . . . . . . . , C3- . . . . . . . . . . .) | 54 | 0 | 54
1.2.3 | No. of 6 months old SHGs Part of Village Organisation | 638 | 0 | 638
| No. of CLF Formed | 2 | 0 | 2
| No. of one year old VO part of CLF | 33 | 0 | 33
| No. of VO Registered under Cooperative Society Act-1999 | 4 | 0 | 4
COMMUNITY CADRES - IB & CB
1.2.6 | Number of CM working | 84 | 0 | 84
1.2.7 | Number of VO Book Keepers working | 11 | 0 | 11
1.2.8 | Number of Internal CRPs - SHG Formation working | 128 | 0 | 128
1.2.9 | Number of Internal CRPs-VO formation working | 0 | 0 | 0
1.2.10 | Number of Internal CRPs -Master Trainer working | 0 | 0 | 0
| No. of TSC CRP identified/Trained | 0 | 0 | 0
In-1.3 | At least 75% of formed VOs accessed and managed project funds as per project processes at any point of time
1.3.1 | No of VOs having Bank Account | 51 | 1 | 52
1.3.2 | No of VO to manage Baalwaadi | 0 | 0 | 0
1.3.3 | No of VO to be promoted as Health & Nutrition center | 0 | 0 | 0
1.3.4 | Number of VO participating in HRF | 44 | 0 | 44
1.3.5 | No. of members benefitted in HRF | 78 | 5 | 83
1.3.6 | No of VO received funding for its Action Plan | 0 | 0 | 0
In-1.4
1.4.2 | No. of SHGs having Bank A/C | 624 | 3 | 627
1.4.3 | No of Bank Mitra working | 4 | 0 | 4
1.4.4 | No of eligible SHGs ( six month old SHG + following PANCHSUTRA ) financed by Banks | 530 | 0 | 530
1.4.5 | Amount Loaned by Banks to SHG | 26500000 | 0 | 26500000
1.4.6 | No of Groups repeat financed by Banks | 0 | 0 | 0
1.4.7 | Repeat financed Amount by Banks | 0 | 0 | 0
1.4.10 | No. of SHG members received bond under insurance programme. | 2754 | 0 | 2754
Result-2 | Establishment and use of Community Investment Fund for food security, social services, assets and income generation and service sector investment
2.1.1 | No of Group visited for Social plan | 36 | 0 | 36
2.1.2 | No of SHG members made signature literate | 5860 | 49 | 5909
2.1.3 | No of SHG made financial literate | 0 | 0 | 0
5 | No of SHG Member linked with RSBY - Health insurance | 1200 | 0 | 1200
2.1.5 | Sanitation Programme initiated with number of SHGs | 0 | 0 | 0
2.1.6 | No. of SHG HHs linked with Social Security Programme | 0 | 0 | 0
2.1.7 | No of Social Security Resource Person working | 0 | 0 | 0
2.1.8 | NO of Social Security community professional working | 0 | 0 | 0
2.1.9 | No of groups to complete Micro Planing exercise within 3 months of Group formation | 600 | 14 | 614
2.1.10 | No of Group Recd ICF through BPIU | 0 | 0 | 0
2.1.11 | No of Group Recd ICF through VO | 0 | 0 | 0
2.1.12 | Total No. of Groups received ICF through Vo/BPIU | 564 | 0 | 564
2.1.13 | No of groups/Farmers to complete Livelihoods Micro Planing exercise(SWI) | 0 | 0 | 0
2.1.14 | No of Group Revisited for Micro plan | 0 | 0 | 0
2.1.15 | No of trained CM generating Micro Plan | 0 | 0 | 0
Food security increased for 80% of target households as compared to the baseline
2.1.16 | Number of VO participating in FSF | 46 | 0 | 46
2.1.17 | No of HH linked with FS Intervention | 2923 | 153 | 3076
Result - 3 | Establishment and operationalization of Technical Assistance Fund.
In- 3.1 | At least 5 major business linkages established through public/private partnership by CBOs
3.1.1 | No of SHG members registered in VO for SRI | 4166 | 0 | 4166
3.1.2 | No of SHG members registered in VO for SWI | 718 | 0 | 718
3.1.3 | No of Acres of land will be under Agriculture Intervention-SRI | 5788 | 0 | 5788
3.1.4 | No of Acres of land will be under Agriculture Intervention- SWI | 2765 | 0 | 2765
3.1.5 | No of vermi-compost pit will be prepared | 1 | 0 | 1
3.1.6 | No of VRP will work in the Agriculture Intervention | 50 | 0 | 50
3.1.7 | No of Skilled Extension Worker will be created in Agriculture Intervention | 0 | 0 | 0
3.1.8 | No of SHG members will be registered in existing DCS | 0 | 0 | 0
3.1.9 | No of New DCS formed | 0 | 0 | 0
3.1.10 | No of SHG members will be registered in new DCS | 0 | 0 | 0
3.1.11 | No of DCS promoted as resource DCS | 0 | 0 | 0
3.1.13 | No of Kishan days will be organized | 0 | 0 | 0
3.1.14 | No of Cluster Adhibesan will be organized | 0 | 0 | 0
3.1.15 | No of VO have efficient equipment management system in place | 44 | 0 | 44
| Moong MP | 925 | 0 | 925
| No. of Katta for moong cultivation0 | 2593 | 0 | 2593
Atleast 5,000 Direct jobs created through Project facilitation and atleast 75% of them are getting sustained income
3.1.16 | No of youth identified - data base prepared | 3769 | 300 | 4069
3.1.17 | No of Youth Placed by direct placement | 15 | 0 | 15
3.1.18 | No of Youth Placed by service sector agency | 0 | 0 | 0
3.1.19 | No of JRP working | 3 | 0 | 3
Project Monitoring and Learning System established, including RLMIS, learning and experience sharing forums at different levels of Project management
3.1.20 | % of Cluster generating reports through MIS | 0 | 0 | 0
3.1.21 | No of SHG graded | 600 | 14 | 614
3.1.22 | No of VO rated | 0 | 0 | 0
3.1.23 | No of Case study generated ( Best Practice - Institution Program,Procurement, Financial Mgmt.) | 0 | 0 | 0
Result 4 | Project implementation procedures and agreed business standards are followed for at least 80% of project interventions at any point in time
4.2.1 | No of MOU signed between BPIU and Community Based Organisation | 46 | 0 | 46
4.2.2 | No of UC received within One month time of CIF release from CBOs | 473 | 6 | 479
4.2.3 | No of CBOs trained on Community Procurement | 44 | 0 | 44
4.2.4 | % of Community Cadre payment made in the Ist week of the month | 0 | 0 | 0
4.2.5 | No of VO submitting Receipt & payment on monthly basis | 45 | 0 | 45
4.2.6 | No of VO two months old procured establishment materials | 10 | 0 | 10
Note on B9: Anurag Kumar (MIS Exeucutive) Please mention in this field cluster wise no. of SHG.
Note on B17: Anurag Kumar (MIS Exeucutive) Please mention in this field cluster wise no. of VO.

## Chhatapur
MPPR OF - Chhatapur. Month - October -2014
Sl. | DESCRIPTION OF PROGRAM | Cummalitive achievement Previous month | Cummalitive achievement in current month | Cummalative achievement
1 | No. of Panchayats | 23 | 0 | 23
2 | No of revenue villages to be covered | 56 | 0 | 56
3 | No of Village to be saturated (geographically) - certification from the VO | 27 | 0 | 27
Result-1 | Formation of self reliant and inclusive community institutions including SHGs, Village Organizations and Federations.
In-1.2 | Self managed self help groups (SHGs) established, covering at least 80% of the target households, 60% of formed SHGs into VO; and 40% of the formed VOs into BLF.
| Total SGSY groups in JEEViKA fold | 0 | 0 | 0
1.2.1 | Total No of SHG formed (C1- . . . . . . . . , C2- . . . . . . . , C3- . . . . . . ) *** | 2046 | 29 | 2075
| TOTAL NO OF POOR MOBILISED | 24560 | 345 | 24905
| No. of SC | 6158 | 24 | 6182
| No. ST | 716 | 25 | 741
| No.EBC | 6987 | 104 | 7091
| No. OBC | 5866 | 259 | 6125
| No. Minority | 3152 | 36 | 3188
| General | 1513 | 52 | 1565
1.2.2 | No. of Village Organisation Formed (C1-54,C2-38,C3-54) *** | 154 | 2 | 156
1.2.3 | No. of 6 months old SHGs Part of Village Organisation | 1518 | 13 | 1531
| No. of CLF Formed | 3 | 0 | 3
| No. of one year old VO part of CLF | 52 | 0 | 52
| No. of VO Registered under Cooperative Society Act-1999 | 8 | 0 | 8
COMMUNITY CADRES - IB & CB
1.2.6 | Number of CM working | 207 | 7 | 214
1.2.7 | Number of VO Book Keepers working | 26 | 1 | 27
1.2.8 | Number of Internal CRPs - SHG Formation working | 122 | 1 | 123
1.2.9 | Number of Internal CRPs-VO formation working | 28 | 0 | 28
1.2.10 | Number of Internal CRPs -Master Trainer working | 37 | 0 | 37
| No. of TSC CRP identified/Trained | 0 | 0 | 0
In-1.3 | At least 75% of formed VOs accessed and managed project funds as per project processes at any point of time
1.3.1 | No of VOs having Bank Account | 142 | 1 | 143
1.3.2 | No of VO to manage Baalwaadi | 0 | 0 | 0
1.3.3 | No of VO to be promoted as Health & Nutrition center | 0 | 0 | 0
1.3.4 | Number of VO participating in HRF | 52 | 0 | 52
1.3.5 | No. of members benefitted in HRF | 414 | 0 | 414
1.3.6 | No of VO received funding for its Action Plan | 0 | 0 | 0
In-1.4
1.4.2 | No. of SHGs having Bank A/C | 1692 | 113 | 1805
1.4.3 | No of Bank Mitra working | 7 | 1 | 8
1.4.4 | No of eligible SHGs ( six month old SHG + following PANCHSUTRA ) financed by Banks | 1418 | 0 | 1418
1.4.5 | Amount Loaned by Banks to SHG | 70900000 | 0 | 70900000
1.4.6 | No of Groups repeat financed by Banks | 0 | 0 | 0
1.4.7 | Repeat financed Amount by Banks | 0 | 0 | 0
1.4.10 | No. of SHG members received bond under insurance programme. | 5378 | 0 | 5378
Result-2 | Establishment and use of Community Investment Fund for food security, social services, assets and income generation and service sector investment
2.1.1 | No of Group visited for Social plan | 0 | 0 | 0
2.1.2 | No of SHG members made signature literate | 13123 | 97 | 13220
2.1.3 | No of SHG made financial literate | 30 | 1 | 31
5 | No of SHG Member linked with RSBY - Health insurance | 1650 | 0 | 1650
2.1.5 | Sanitation Programme initiated with number of SHGs | 60 | 0 | 60
2.1.6 | No. of SHG HHs linked with Social Security Programme | 0 | 0 | 0
2.1.7 | No of Social Security Resource Person working | 0 | 0 | 0
2.1.8 | NO of Social Security community professional working | 0 | 0 | 0
2.1.9 | No of groups to complete Micro Planing exercise within 3 months of Group formation | 1538 | 32 | 1570
2.1.10 | No of Group Recd ICF through BPIU | 1365 | 97 | 1462
2.1.11 | No of Group Recd ICF through VO | 0 | 0 | 0
2.1.12 | Total No. of Groups received ICF through Vo/BPIU | 1365 | 97 | 1462
2.1.13 | No of groups/Farmers to complete Livelihoods Micro Planing exercise(SWI) | 1100 | 0 | 1100
2.1.14 | No of Group Revisited for Micro plan | 0 | 0 | 0
2.1.15 | No of trained CM generating Micro Plan | 40 | 0 | 40
Food security increased for 80% of target households as compared to the baseline
2.1.16 | Number of VO participating in FSF | 39 | 0 | 39
2.1.17 | No of HH linked with FS Intervention | 1796 | 0 | 1796
Result - 3 | Establishment and operationalization of Technical Assistance Fund.
In- 3.1 | At least 5 major business linkages established through public/private partnership by CBOs
3.1.1 | No of SHG members registered in VO for SRI | 2792 | 198 | 2990
3.1.2 | No of SHG members registered in VO for SWI | 0 | 0 | 0
3.1.3 | No of Acres of land will be under Agriculture Intervention-SRI | 371 | 10 | 381
3.1.4 | No of Acres of land will be under Agriculture Intervention- SWI | 0 | 0 | 0
3.1.5 | No of vermi-compost pit will be prepared | 2 | 0 | 2
3.1.6 | No of VRP will work in the Agriculture Intervention | 53 | 2 | 55
3.1.7 | No of Skilled Extension Worker will be created in Agriculture Intervention | 0 | 0 | 0
3.1.8 | No of SHG members will be registered in existing DCS | 0 | 0 | 0
3.1.9 | No of New DCS formed | 0 | 0 | 0
3.1.10 | No of SHG members will be registered in new DCS | 0 | 0 | 0
3.1.11 | No of DCS promoted as resource DCS | 0 | 0 | 0
3.1.13 | No of Kishan days will be organized | 0 | 0 | 0
3.1.14 | No of Cluster Adhibesan will be organized | 0 | 0 | 0
3.1.15 | No of VO have efficient equipment management system in place | 0 | 0 | 0
| Moong MP | 480 | 0 | 480
| No. of Katta for moong cultivation0 | 4705 | 0 | 4705
Atleast 5,000 Direct jobs created through Project facilitation and atleast 75% of them are getting sustained income
3.1.16 | No of youth identified - data base prepared | 600 | 100 | 700
3.1.17 | No of Youth Placed by direct placement | 40 | 0 | 40
3.1.18 | No of Youth Placed by service sector agency | 0 | 0 | 0
3.1.19 | No of JRP working | 1 | 1 | 2
Project Monitoring and Learning System established, including RLMIS, learning and experience sharing forums at different levels of Project management
3.1.20 | % of Cluster generating reports through MIS | 0 | 0 | 0
3.1.21 | No of SHG graded | 1508 | 0 | 1508
3.1.22 | No of VO rated | 59 | 0 | 59
3.1.23 | No of Case study generated ( Best Practice - Institution Program,Procurement, Financial Mgmt.) | 0 | 0 | 0
Result 4 | Project implementation procedures and agreed business standards are followed for at least 80% of project interventions at any point in time
4.2.1 | No of MOU signed between BPIU and Community Based Organisation | 71 | 0 | 71
4.2.2 | No of UC received within One month time of CIF release from CBOs | 514 | 0 | 514
4.2.3 | No of CBOs trained on Community Procurement | 45 | 0 | 45
4.2.4 | % of Community Cadre payment made in the Ist week of the month | 0 | 0 | 0
4.2.5 | No of VO submitting Receipt & payment on monthly basis | 132 | 0 | 132
4.2.6 | No of VO two months old procured establishment materials | 23 | 0 | 23
Note on B9: Anurag Kumar (MIS Exeucutive) Please mention in this field cluster wise no. of SHG.
Note on B17: Anurag Kumar (MIS Exeucutive) Please mention in this field cluster wise no. of VO.

## Supaul Sadar
MPPR OF -Supaul Sadar. Month - October 2014
Sl. | DESCRIPTION OF PROGRAM | Cummalitive achievement Previous month | Cummalitive achievement in current month | Cummalative achievement
1 | No. of Panchayats | 5 | 3 | 8
2 | No of revenue villages to be covered | 8 | 3 | 11
3 | No of Village to be saturated (geographically) - certification from the VO | 0 | 0 | 0
Result-1 | Formation of self reliant and inclusive community institutions including SHGs, Village Organizations and Federations.
In-1.2 | Self managed self help groups (SHGs) established, covering at least 80% of the target households, 60% of formed SHGs into VO; and 40% of the formed VOs into BLF.
| Total SGSY groups in JEEViKA fold | 25 | 0 | 25
1.2.1 | Total No of SHG formed (C1- . . . . . . . . . . , C2- . . . . . . . . . . , C3- . . . . . . . . . . .) *** | 102 | 10 | 112
| TOTAL NO OF POOR MOBILISED | 1048 | 116 | 1164
| No. of SC | 378 | 18 | 396
| No. ST | 0 | 0 | 0
| No.EBC | 521 | 66 | 587
| No. OBC | 103 | 8 | 111
| No. Minority | 32 | 24 | 56
| General | 14 | 0 | 14
1.2.2 | No. of Village Organisation Formed (C1- . . . . . . . . . . , C2- . . . . . . . . . . , C3- . . . . . . . . . . .) | 0 | 0 | 0
1.2.3 | No. of 6 months old SHGs Part of Village Organisation | 0 | 0 | 0
| No. of CLF Formed | 0 | 0 | 0
| No. of one year old VO part of CLF | 0 | 0 | 0
| No. of VO Registered under Cooperative Society Act-1999 | 0 | 0 | 0
COMMUNITY CADRES - IB & CB
1.2.6 | Number of CM working | 14 | 4 | 18
1.2.7 | Number of VO Book Keepers working | 0 | 0 | 0
1.2.8 | Number of Internal CRPs - SHG Formation working | 0 | 0 | 0
1.2.9 | Number of Internal CRPs-VO formation working | 0 | 0 | 0
1.2.10 | Number of Internal CRPs -Master Trainer working | 0 | 0 | 0
| No. of TSC CRP identified/Trained | 0 | 0 | 0
In-1.3 | At least 75% of formed VOs accessed and managed project funds as per project processes at any point of time
1.3.1 | No of VOs having Bank Account | 0 | 0 | 0
1.3.2 | No of VO to manage Baalwaadi | 0 | 0 | 0
1.3.3 | No of VO to be promoted as Health & Nutrition center | 0 | 0 | 0
1.3.4 | Number of VO participating in HRF | 0 | 0 | 0
1.3.5 | No. of members benefitted in HRF | 0 | 0 | 0
1.3.6 | No of VO received funding for its Action Plan | 0 | 0 | 0
In-1.4
1.4.2 | No. of SHGs having Bank A/C | 16 | 2 | 18
1.4.3 | No of Bank Mitra working | 0 | 0 | 0
1.4.4 | No of eligible SHGs ( six month old SHG + following PANCHSUTRA ) financed by Banks | 0 | 0 | 0
1.4.5 | Amount Loaned by Banks to SHG | 0 | 0 | 0
1.4.6 | No of Groups repeat financed by Banks | 0 | 0 | 0
1.4.7 | Repeat financed Amount by Banks | 0 | 0 | 0
1.4.10 | No. of SHG members received bond under insurance programme. | 0 | 0 | 0
Result-2 | Establishment and use of Community Investment Fund for food security, social services, assets and income generation and service sector investment
2.1.1 | No of Group visited for Social plan | 0 | 0 | 0
2.1.2 | No of SHG members made signature literate | 0 | 0 | 0
2.1.3 | No of SHG made financial literate | 0 | 0 | 0
5 | No of SHG Member linked with RSBY - Health insurance | 0 | 0 | 0
2.1.5 | Sanitation Programme initiated with number of SHGs | 0 | 0 | 0
2.1.6 | No. of SHG HHs linked with Social Security Programme | 0 | 0 | 0
2.1.7 | No of Social Security Resource Person working | 0 | 0 | 0
2.1.8 | NO of Social Security community professional working | 0 | 0 | 0
2.1.9 | No of groups to complete Micro Planing exercise within 3 months of Group formation | 0 | 0 | 0
2.1.10 | No of Group Recd ICF through BPIU | 0 | 0 | 0
2.1.11 | No of Group Recd ICF through VO | 0 | 0 | 0
2.1.12 | Total No. of Groups received ICF through Vo/BPIU | 0 | 0 | 0
2.1.13 | No of groups/Farmers to complete Livelihoods Micro Planing exercise(SWI) | 0 | 0 | 0
2.1.14 | No of Group Revisited for Micro plan | 0 | 0 | 0
2.1.15 | No of trained CM generating Micro Plan | 0 | 0 | 0
Food security increased for 80% of target households as compared to the baseline
2.1.16 | Number of VO participating in FSF | 0 | 0 | 0
2.1.17 | No of HH linked with FS Intervention | 0 | 0 | 0
Result - 3 | Establishment and operationalization of Technical Assistance Fund.
In- 3.1 | At least 5 major business linkages established through public/private partnership by CBOs
3.1.1 | No of SHG members registered in VO for SRI | 0 | 0 | 0
3.1.2 | No of SHG members registered in VO for SWI | 0 | 0 | 0
3.1.3 | No of Acres of land will be under Agriculture Intervention-SRI | 0 | 0 | 0
3.1.4 | No of Acres of land will be under Agriculture Intervention- SWI | 0 | 0 | 0
3.1.5 | No of vermi-compost pit will be prepared | 0 | 0 | 0
3.1.6 | No of VRP will work in the Agriculture Intervention | 0 | 0 | 0
3.1.7 | No of Skilled Extension Worker will be created in Agriculture Intervention | 0 | 0 | 0
3.1.8 | No of SHG members will be registered in existing DCS | 0 | 0 | 0
3.1.9 | No of New DCS formed | 0 | 0 | 0
3.1.10 | No of SHG members will be registered in new DCS | 0 | 0 | 0
3.1.11 | No of DCS promoted as resource DCS | 0 | 0 | 0
3.1.13 | No of Kishan days will be organized | 0 | 0 | 0
3.1.14 | No of Cluster Adhibesan will be organized | 0 | 0 | 0
3.1.15 | No of VO have efficient equipment management system in place | 0 | 0 | 0
| Moong MP | 0 | 0 | 0
| No. of Katta for moong cultivation0 | 0 | 0 | 0
Atleast 5,000 Direct jobs created through Project facilitation and atleast 75% of them are getting sustained income
3.1.16 | No of youth identified - data base prepared | 0 | 0 | 0
3.1.17 | No of Youth Placed by direct placement | 0 | 0 | 0
3.1.18 | No of Youth Placed by service sector agency | 0 | 0 | 0
3.1.19 | No of JRP working | 0 | 0 | 0
Project Monitoring and Learning System established, including RLMIS, learning and experience sharing forums at different levels of Project management
3.1.20 | % of Cluster generating reports through MIS | 0 | 0 | 0
3.1.21 | No of SHG graded | 0 | 32 | 32
3.1.22 | No of VO rated | 0 | 0 | 0
3.1.23 | No of Case study generated ( Best Practice - Institution Program,Procurement, Financial Mgmt.) | 0 | 0 | 0
Result 4 | Project implementation procedures and agreed business standards are followed for at least 80% of project interventions at any point in time
4.2.1 | No of MOU signed between BPIU and Community Based Organisation | 0 | 0 | 0
4.2.2 | No of UC received within One month time of CIF release from CBOs | 0 | 0 | 0
4.2.3 | No of CBOs trained on Community Procurement | 0 | 0 | 0
4.2.4 | % of Community Cadre payment made in the Ist week of the month | 0 | 80 | 80
4.2.5 | No of VO submitting Receipt & payment on monthly basis | 0 | 0 | 0
4.2.6 | No of VO two months old procured establishment materials | 0 | 0 | 0
Note on B9: Anurag Kumar (MIS Exeucutive) Please mention in this field cluster wise no. of SHG.
Note on B17: Anurag Kumar (MIS Exeucutive) Please mention in this field cluster wise no. of VO.

## Pipra
MPPR OF - Pipra Month - October 2014
Sl. | DESCRIPTION OF PROGRAM | Cummalitive achievement Previous month | Cummalitive achievement in current month | Cummalative achievement
1 | No. of Panchayats | 4 | 0 | 4
2 | No of revenue villages to be covered | 3 | 0 | 3
3 | No of Village to be saturated (geographically) - certification from the VO | 0 | 0 | 0
Result-1 | Formation of self reliant and inclusive community institutions including SHGs, Village Organizations and Federations.
In-1.2 | Self managed self help groups (SHGs) established, covering at least 80% of the target households, 60% of formed SHGs into VO; and 40% of the formed VOs into BLF.
| Total SGSY groups in JEEViKA fold | 0 | 0 | 0
1.2.1 | Total No of SHG formed (C1- . . . . . . . . . . , C2- . . . . . . . . . . , C3- . . . . . . . . . . .) *** | 154 | 13 | 167
| TOTAL NO OF POOR MOBILISED | 1865 | 165 | 2030
| No. of SC | 168 | 0 | 168
| No. ST | 0 | 0 | 0
| No.EBC | 50 | 0 | 50
| No. OBC | 370 | 0 | 370
| No. Minority | 12 | 0 | 12
| General | 0 | 0 | 0
1.2.2 | No. of Village Organisation Formed (C1- . . . . . . . . . . , C2- . . . . . . . . . . , C3- . . . . . . . . . . .) | 0 | 0 | 0
1.2.3 | No. of 6 months old SHGs Part of Village Organisation | 0 | 0 | 0
| No. of CLF Formed | 0 | 0 | 0
| No. of one year old VO part of CLF | 0 | 0 | 0
| No. of VO Registered under Cooperative Society Act-1999 | 0 | 0 | 0
COMMUNITY CADRES - IB & CB
1.2.6 | Number of CM working | 20 | 3 | 23
1.2.7 | Number of VO Book Keepers working | 0 | 0 | 0
1.2.8 | Number of Internal CRPs - SHG Formation working | 0 | 0 | 0
1.2.9 | Number of Internal CRPs-VO formation working | 0 | 0 | 0
1.2.10 | Number of Internal CRPs -Master Trainer working | 0 | 0 | 0
| No. of TSC CRP identified/Trained | 0 | 0 | 0
In-1.3 | At least 75% of formed VOs accessed and managed project funds as per project processes at any point of time
1.3.1 | No of VOs having Bank Account | 0 | 0 | 0
1.3.2 | No of VO to manage Baalwaadi | 0 | 0 | 0
1.3.3 | No of VO to be promoted as Health & Nutrition center | 0 | 0 | 0
1.3.4 | Number of VO participating in HRF | 0 | 0 | 0
1.3.5 | No. of members benefitted in HRF | 0 | 0 | 0
1.3.6 | No of VO received funding for its Action Plan | 0 | 0 | 0
In-1.4
1.4.2 | No. of SHGs having Bank A/C | 43 | 15 | 58
1.4.3 | No of Bank Mitra working | 1 | 0 | 1
1.4.4 | No of eligible SHGs ( six month old SHG + following PANCHSUTRA ) financed by Banks | 0 | 0 | 0
1.4.5 | Amount Loaned by Banks to SHG | 0 | 0 | 0
1.4.6 | No of Groups repeat financed by Banks | 0 | 0 | 0
1.4.7 | Repeat financed Amount by Banks | 0 | 0 | 0
1.4.10 | No. of SHG members received bond under insurance programme. | 0 | 0 | 0
Result-2 | Establishment and use of Community Investment Fund for food security, social services, assets and income generation and service sector investment
2.1.1 | No of Group visited for Social plan | 0 | 0 | 0
2.1.2 | No of SHG members made signature literate | 0 | 652 | 652
2.1.3 | No of SHG made financial literate | 0 | 0 | 0
5 | No of SHG Member linked with RSBY - Health insurance | 0 | 0 | 0
2.1.5 | Sanitation Programme initiated with number of SHGs | 0 | 0 | 0
2.1.6 | No. of SHG HHs linked with Social Security Programme | 0 | 0 | 0
2.1.7 | No of Social Security Resource Person working | 0 | 0 | 0
2.1.8 | NO of Social Security community professional working | 0 | 0 | 0
2.1.9 | No of groups to complete Micro Planing exercise within 3 months of Group formation | 0 | 0 | 0
2.1.10 | No of Group Recd ICF through BPIU | 19 | 0 | 19
2.1.11 | No of Group Recd ICF through VO | 0 | 0 | 0
2.1.12 | Total No. of Groups received ICF through Vo/BPIU | 0 | 0 | 0
2.1.13 | No of groups/Farmers to complete Livelihoods Micro Planing exercise(SWI) | 0 | 0 | 0
2.1.14 | No of Group Revisited for Micro plan | 0 | 0 | 0
2.1.15 | No of trained CM generating Micro Plan | 4 | 1 | 5
Food security increased for 80% of target households as compared to the baseline
2.1.16 | Number of VO participating in FSF | 0 | 0 | 0
2.1.17 | No of HH linked with FS Intervention | 0 | 0 | 0
Result - 3 | Establishment and operationalization of Technical Assistance Fund.
In- 3.1 | At least 5 major business linkages established through public/private partnership by CBOs
3.1.1 | No of SHG members registered in VO for SRI | 0 | 0 | 0
3.1.2 | No of SHG members registered in VO for SWI | 0 | 0 | 0
3.1.3 | No of Acres of land will be under Agriculture Intervention-SRI | 0 | 0 | 0
3.1.4 | No of Acres of land will be under Agriculture Intervention- SWI | 0 | 0 | 0
3.1.5 | No of vermi-compost pit will be prepared | 0 | 0 | 0
3.1.6 | No of VRP will work in the Agriculture Intervention | 0 | 0 | 0
3.1.7 | No of Skilled Extension Worker will be created in Agriculture Intervention | 0 | 0 | 0
3.1.8 | No of SHG members will be registered in existing DCS | 0 | 0 | 0
3.1.9 | No of New DCS formed | 0 | 0 | 0
3.1.10 | No of SHG members will be registered in new DCS | 0 | 0 | 0
3.1.11 | No of DCS promoted as resource DCS | 0 | 0 | 0
3.1.13 | No of Kishan days will be organized | 0 | 0 | 0
3.1.14 | No of Cluster Adhibesan will be organized | 0 | 0 | 0
3.1.15 | No of VO have efficient equipment management system in place | 0 | 0 | 0
| Moong MP | 0 | 0 | 0
| No. of Katta for moong cultivation0 | 0 | 0 | 0
Atleast 5,000 Direct jobs created through Project facilitation and atleast 75% of them are getting sustained income
3.1.16 | No of youth identified - data base prepared | 0 | 0 | 0
3.1.17 | No of Youth Placed by direct placement | 0 | 0 | 0
3.1.18 | No of Youth Placed by service sector agency | 0 | 0 | 0
3.1.19 | No of JRP working | 0 | 0 | 0
Project Monitoring and Learning System established, including RLMIS, learning and experience sharing forums at different levels of Project management
3.1.20 | % of Cluster generating reports through MIS | 0 | 0 | 0
3.1.21 | No of SHG graded | 0 | 0 | 0
3.1.22 | No of VO rated | 0 | 0 | 0
3.1.23 | No of Case study generated ( Best Practice - Institution Program,Procurement, Financial Mgmt.) | 0 | 0 | 0
Result 4 | Project implementation procedures and agreed business standards are followed for at least 80% of project interventions at any point in time
4.2.1 | No of MOU signed between BPIU and Community Based Organisation | 0 | 0 | 0
4.2.2 | No of UC received within One month time of CIF release from CBOs | 0 | 0 | 0
4.2.3 | No of CBOs trained on Community Procurement | 0 | 0 | 0
4.2.4 | % of Community Cadre payment made in the Ist week of the month | 0 | 31 | 31
4.2.5 | No of VO submitting Receipt & payment on monthly basis | 0 | 0 | 0
4.2.6 | No of VO two months old procured establishment materials | 0 | 0 | 0
Note on B9: Anurag Kumar (MIS Exeucutive) Please mention in this field cluster wise no. of SHG.
Note on B17: Anurag Kumar (MIS Exeucutive) Please mention in this field cluster wise no. of VO.

## Kisanpur
MPPR OF - Kisanpur, Month - October 2014
Sl. | DESCRIPTION OF PROGRAM | Cummalitive achievement Previous month | Cummalitive achievement in current month | Cummalative achievement
1 | No. of Panchayats | 4 | 1 | 5
2 | No of revenue villages to be covered | 10 | 1 | 11
3 | No of Village to be saturated (geographically) - certification from the VO | 0 | 0 | 0
Result-1 | Formation of self reliant and inclusive community institutions including SHGs, Village Organizations and Federations.
In-1.2 | Self managed self help groups (SHGs) established, covering at least 80% of the target households, 60% of formed SHGs into VO; and 40% of the formed VOs into BLF.
| Total SGSY groups in JEEViKA fold | 0 | 0 | 0
1.2.1 | Total No of SHG formed (C1- ……., C2- ………..., C3- . . . . .. . .) *** | 112 | 4 | 116
| TOTAL NO OF POOR MOBILISED | 1469 | 13 | 1482
| No. of SC | 0 | 0 | 0
| No. ST | 0 | 0 | 0
| No.EBC | 0 | 0 | 0
| No. OBC | 0 | 0 | 0
| No. Minority | 0 | 0 | 0
| General | 0 | 0 | 0
1.2.2 | No. of Village Organisation Formed (C1- . . . . . . . . . . , C2- . . . . . . . . . . , C3- . . . . . . . . . . .) | 0 | 0 | 0
1.2.3 | No. of 6 months old SHGs Part of Village Organisation | 0 | 0 | 0
| No. of CLF Formed | 0 | 0 | 0
| No. of one year old VO part of CLF | 0 | 0 | 0
| No. of VO Registered under Cooperative Society Act-1999 | 0 | 0 | 0
COMMUNITY CADRES - IB & CB
1.2.6 | Number of CM working | 11 | 4 | 15
1.2.7 | Number of VO Book Keepers working | 0 | 0 | 0
1.2.8 | Number of Internal CRPs - SHG Formation working | 0 | 0 | 0
1.2.9 | Number of Internal CRPs-VO formation working | 0 | 0 | 0
1.2.10 | Number of Internal CRPs -Master Trainer working | 0 | 0 | 0
| No. of TSC CRP identified/Trained | 11 | 0 | 11
In-1.3 | At least 75% of formed VOs accessed and managed project funds as per project processes at any point of time
1.3.1 | No of VOs having Bank Account | 0 | 0 | 0
1.3.2 | No of VO to manage Baalwaadi | 0 | 0 | 0
1.3.3 | No of VO to be promoted as Health & Nutrition center | 0 | 0 | 0
1.3.4 | Number of VO participating in HRF | 0 | 0 | 0
1.3.5 | No. of members benefitted in HRF | 0 | 0 | 0
1.3.6 | No of VO received funding for its Action Plan | 0 | 0 | 0
In-1.4
1.4.2 | No. of SHGs having Bank A/C | 0 | 10 | 10
1.4.3 | No of Bank Mitra working | 0 | 0 | 0
1.4.4 | No of eligible SHGs ( six month old SHG + following PANCHSUTRA ) financed by Banks | 0 | 55 | 55
1.4.5 | Amount Loaned by Banks to SHG | 0 | 0 | 0
1.4.6 | No of Groups repeat financed by Banks | 0 | 0 | 0
1.4.7 | Repeat financed Amount by Banks | 0 | 0 | 0
1.4.10 | No. of SHG members received bond under insurance programme. | 0 | 0 | 0
Result-2 | Establishment and use of Community Investment Fund for food security, social services, assets and income generation and service sector investment
2.1.1 | No of Group visited for Social plan | 5 | 0 | 5
2.1.2 | No of SHG members made signature literate | 40 | 200 | 240
2.1.3 | No of SHG made financial literate | 0 | 0 | 0
5 | No of SHG Member linked with RSBY - Health insurance | 0 | 0 | 0
2.1.5 | Sanitation Programme initiated with number of SHGs | 0 | 0 | 0
2.1.6 | No. of SHG HHs linked with Social Security Programme | 0 | 0 | 0
2.1.7 | No of Social Security Resource Person working | 0 | 0 | 0
2.1.8 | NO of Social Security community professional working | 0 | 0 | 0
2.1.9 | No of groups to complete Micro Planing exercise within 3 months of Group formation | 20 | 15 | 35
2.1.10 | No of Group Recd ICF through BPIU | 0 | 0 | 0
2.1.11 | No of Group Recd ICF through VO | 0 | 0 | 0
2.1.12 | Total No. of Groups received ICF through Vo/BPIU | 0 | 0 | 0
2.1.13 | No of groups/Farmers to complete Livelihoods Micro Planing exercise(SWI) | 0 | 0 | 0
2.1.14 | No of Group Revisited for Micro plan | 0 | 0 | 0
2.1.15 | No of trained CM generating Micro Plan | 0 | 0 | 0
Food security increased for 80% of target households as compared to the baseline
2.1.16 | Number of VO participating in FSF | 0 | 0 | 0
2.1.17 | No of HH linked with FS Intervention | 0 | 0 | 0
Result - 3 | Establishment and operationalization of Technical Assistance Fund.
In- 3.1 | At least 5 major business linkages established through public/private partnership by CBOs
3.1.1 | No of SHG members registered in VO for SRI | 0 | 0 | 0
3.1.2 | No of SHG members registered in VO for SWI | 0 | 0 | 0
3.1.3 | No of Acres of land will be under Agriculture Intervention-SRI | 0 | 0 | 0
3.1.4 | No of Acres of land will be under Agriculture Intervention- SWI | 0 | 0 | 0
3.1.5 | No of vermi-compost pit will be prepared | 0 | 0 | 0
3.1.6 | No of VRP will work in the Agriculture Intervention | 0 | 0 | 0
3.1.7 | No of Skilled Extension Worker will be created in Agriculture Intervention | 0 | 0 | 0
3.1.8 | No of SHG members will be registered in existing DCS | 0 | 0 | 0
3.1.9 | No of New DCS formed | 0 | 0 | 0
3.1.10 | No of SHG members will be registered in new DCS | 0 | 0 | 0
3.1.11 | No of DCS promoted as resource DCS | 0 | 0 | 0
3.1.13 | No of Kishan days will be organized | 0 | 0 | 0
3.1.14 | No of Cluster Adhibesan will be organized | 0 | 0 | 0
3.1.15 | No of VO have efficient equipment management system in place | 0 | 0 | 0
| Moong MP | 0 | 0 | 0
| No. of Katta for moong cultivation0 | 0 | 0 | 0
Atleast 5,000 Direct jobs created through Project facilitation and atleast 75% of them are getting sustained income
3.1.16 | No of youth identified - data base prepared | 0 | 0 | 0
3.1.17 | No of Youth Placed by direct placement | 0 | 0 | 0
3.1.18 | No of Youth Placed by service sector agency | 0 | 0 | 0
3.1.19 | No of JRP working | 0 | 0 | 0
Project Monitoring and Learning System established, including RLMIS, learning and experience sharing forums at different levels of Project management
3.1.20 | % of Cluster generating reports through MIS | 0 | 0 | 0
3.1.21 | No of SHG graded | 0 | 0 | 0
3.1.22 | No of VO rated | 0 | 0 | 0
3.1.23 | No of Case study generated ( Best Practice - Institution Program,Procurement, Financial Mgmt.) | 0 | 0 | 0
Result 4 | Project implementation procedures and agreed business standards are followed for at least 80% of project interventions at any point in time
4.2.1 | No of MOU signed between BPIU and Community Based Organisation | 0 | 0 | 0
4.2.2 | No of UC received within One month time of CIF release from CBOs | 0 | 0 | 0
4.2.3 | No of CBOs trained on Community Procurement | 0 | 0 | 0
4.2.4 | % of Community Cadre payment made in the Ist week of the month | 0 | 0 | 0
4.2.5 | No of VO submitting Receipt & payment on monthly basis | 0 | 0 | 0
4.2.6 | No of VO two months old procured establishment materials | 0 | 0 | 0
Note on B9: Anurag Kumar (MIS Exeucutive) Please mention in this field cluster wise no. of SHG.
Note on B17: Anurag Kumar (MIS Exeucutive) Please mention in this field cluster wise no. of VO.

## Raghopur
MPPR OF - Raghopur, Month -October 2014
Sl. | DESCRIPTION OF PROGRAM | Cummalitive achievement Previous month | Cummalitive achievement in current month | Cummalative achievement
1 | No. of Panchayats | 4 | 0 | 4
2 | No of revenue villages to be covered | 14 | 0 | 14
3 | No of Village to be saturated (geographically) - certification from the VO | 0 | 0 | 0
Result-1 | Formation of self reliant and inclusive community institutions including SHGs, Village Organizations and Federations.
In-1.2 | Self managed self help groups (SHGs) established, covering at least 80% of the target households, 60% of formed SHGs into VO; and 40% of the formed VOs into BLF.
| Total SGSY groups in JEEViKA fold | 33 | 8 | 41
1.2.1 | Total No of SHG formed (C1- . . . . . . . . . . , C2- . . . . . . . . . . , C3- …..) *** | 133 | 10 | 143
| TOTAL NO OF POOR MOBILISED | 1565 | 122 | 1687
| No. of SC | 649 | 44 | 693
| No. ST | 0 | 0 | 0
| No.EBC | 373 | 42 | 415
| No. OBC | 351 | 23 | 374
| No. Minority | 125 | 0 | 125
| General | 67 | 13 | 80
1.2.2 | No. of Village Organisation Formed (C1- . . . . . . . . . . , C2- . . . . . . . . . . , C3- . . . . . . . . . . .) | 0 | 0 | 0
1.2.3 | No. of 6 months old SHGs Part of Village Organisation | 0 | 0 | 0
| No. of CLF Formed | 0 | 0 | 0
| No. of one year old VO part of CLF | 0 | 0 | 0
| No. of VO Registered under Cooperative Society Act-1999 | 0 | 0 | 0
COMMUNITY CADRES - IB & CB
1.2.6 | Number of CM working | 17 | 0 | 17
1.2.7 | Number of VO Book Keepers working | 0 | 0 | 0
1.2.8 | Number of Internal CRPs - SHG Formation working | 0 | 0 | 0
1.2.9 | Number of Internal CRPs-VO formation working | 0 | 0 | 0
1.2.10 | Number of Internal CRPs -Master Trainer working | 0 | 0 | 0
| No. of TSC CRP identified/Trained | 0 | 0 | 0
In-1.3 | At least 75% of formed VOs accessed and managed project funds as per project processes at any point of time
1.3.1 | No of VOs having Bank Account | 0 | 0 | 0
1.3.2 | No of VO to manage Baalwaadi | 0 | 0 | 0
1.3.3 | No of VO to be promoted as Health & Nutrition center | 0 | 0 | 0
1.3.4 | Number of VO participating in HRF | 0 | 0 | 0
1.3.5 | No. of members benefitted in HRF | 0 | 0 | 0
1.3.6 | No of VO received funding for its Action Plan | 0 | 0 | 0
In-1.4
1.4.2 | No. of SHGs having Bank A/C | 31 | 7 | 38
1.4.3 | No of Bank Mitra working | 0 | 0 | 0
1.4.4 | No of eligible SHGs ( six month old SHG + following PANCHSUTRA ) financed by Banks | 0 | 0 | 0
1.4.5 | Amount Loaned by Banks to SHG | 0 | 0 | 0
1.4.6 | No of Groups repeat financed by Banks | 0 | 0 | 0
1.4.7 | Repeat financed Amount by Banks | 0 | 0 | 0
1.4.10 | No. of SHG members received bond under insurance programme. | 0 | 0 | 0
Result-2 | Establishment and use of Community Investment Fund for food security, social services, assets and income generation and service sector investment
2.1.1 | No of Group visited for Social plan | 0 | 0 | 0
2.1.2 | No of SHG members made signature literate | 186 | 93 | 279
2.1.3 | No of SHG made financial literate | 0 | 0 | 0
5 | No of SHG Member linked with RSBY - Health insurance | 0 | 0 | 0
2.1.5 | Sanitation Programme initiated with number of SHGs | 0 | 0 | 0
2.1.6 | No. of SHG HHs linked with Social Security Programme | 0 | 0 | 0
2.1.7 | No of Social Security Resource Person working | 0 | 0 | 0
2.1.8 | NO of Social Security community professional working | 0 | 0 | 0
2.1.9 | No of groups to complete Micro Planing exercise within 3 months of Group formation | 0 | 0 | 0
2.1.10 | No of Group Recd ICF through BPIU | 0 | 0 | 0
2.1.11 | No of Group Recd ICF through VO | 0 | 0 | 0
2.1.12 | Total No. of Groups received ICF through Vo/BPIU | 0 | 0 | 0
2.1.13 | No of groups/Farmers to complete Livelihoods Micro Planing exercise(SWI) | 0 | 0 | 0
2.1.14 | No of Group Revisited for Micro plan | 0 | 0 | 0
2.1.15 | No of trained CM generating Micro Plan | 0 | 0 | 0
Food security increased for 80% of target households as compared to the baseline
2.1.16 | Number of VO participating in FSF | 0 | 0 | 0
2.1.17 | No of HH linked with FS Intervention | 0 | 0 | 0
Result - 3 | Establishment and operationalization of Technical Assistance Fund.
In- 3.1 | At least 5 major business linkages established through public/private partnership by CBOs
3.1.1 | No of SHG members registered in VO for SRI | 0 | 0 | 0
3.1.2 | No of SHG members registered in VO for SWI | 0 | 0 | 0
3.1.3 | No of Acres of land will be under Agriculture Intervention-SRI | 0 | 0 | 0
3.1.4 | No of Acres of land will be under Agriculture Intervention- SWI | 0 | 0 | 0
3.1.5 | No of vermi-compost pit will be prepared | 0 | 0 | 0
3.1.6 | No of VRP will work in the Agriculture Intervention | 0 | 0 | 0
3.1.7 | No of Skilled Extension Worker will be created in Agriculture Intervention | 0 | 0 | 0
3.1.8 | No of SHG members will be registered in existing DCS | 0 | 0 | 0
3.1.9 | No of New DCS formed | 0 | 0 | 0
3.1.10 | No of SHG members will be registered in new DCS | 0 | 0 | 0
3.1.11 | No of DCS promoted as resource DCS | 0 | 0 | 0
3.1.13 | No of Kishan days will be organized | 0 | 0 | 0
3.1.14 | No of Cluster Adhibesan will be organized | 0 | 0 | 0
3.1.15 | No of VO have efficient equipment management system in place | 0 | 0 | 0
| Moong MP | 0 | 0 | 0
| No. of Katta for moong cultivation0 | 0 | 0 | 0
Atleast 5,000 Direct jobs created through Project facilitation and atleast 75% of them are getting sustained income
3.1.16 | No of youth identified - data base prepared | 0 | 0 | 0
3.1.17 | No of Youth Placed by direct placement | 0 | 0 | 0
3.1.18 | No of Youth Placed by service sector agency | 0 | 0 | 0
3.1.19 | No of JRP working | 0 | 0 | 0
Project Monitoring and Learning System established, including RLMIS, learning and experience sharing forums at different levels of Project management
3.1.20 | % of Cluster generating reports through MIS | 0 | 0 | 0
3.1.21 | No of SHG graded | 0 | 0 | 0
3.1.22 | No of VO rated | 0 | 0 | 0
3.1.23 | No of Case study generated ( Best Practice - Institution Program,Procurement, Financial Mgmt.) | 0 | 0 | 0
Result 4 | Project implementation procedures and agreed business standards are followed for at least 80% of project interventions at any point in time
4.2.1 | No of MOU signed between BPIU and Community Based Organisation | 0 | 0 | 0
4.2.2 | No of UC received within One month time of CIF release from CBOs | 0 | 0 | 0
4.2.3 | No of CBOs trained on Community Procurement | 0 | 0 | 0
4.2.4 | % of Community Cadre payment made in the Ist week of the month | 0 | 0 | 0
4.2.5 | No of VO submitting Receipt & payment on monthly basis | 0 | 0 | 0
4.2.6 | No of VO two months old procured establishment materials | 0 | 0 | 0
Note on B9: Anurag Kumar (MIS Exeucutive) Please mention in this field cluster wise no. of SHG.
Note on B17: Anurag Kumar (MIS Exeucutive) Please mention in this field cluster wise no. of VO.

## Nirmali
MPPR OF - Nirmali , Month - October 2014
Sl. | DESCRIPTION OF PROGRAM | Cummalitive achievement Previous month | Cummalitive achievement in current month | Cummalative achievement
1 | No. of Panchayats | 4 | 0 | 4
2 | No of revenue villages to be covered | 7 | 1 | 8
3 | No of Village to be saturated (geographically) - certification from the VO | 0 | 0 | 0
Result-1 | Formation of self reliant and inclusive community institutions including SHGs, Village Organizations and Federations.
In-1.2 | Self managed self help groups (SHGs) established, covering at least 80% of the target households, 60% of formed SHGs into VO; and 40% of the formed VOs into BLF.
| Total SGSY groups in JEEViKA fold | 2 | 0 | 2
1.2.1 | Total No of SHG formed (C1- ……. , C2- . . . . . . . . . . , C3- . . . . . . . . . . .) *** | 111 | 5 | 116
| TOTAL NO OF POOR MOBILISED | 1186 | 60 | 1246
| No. of SC | 30 | 0 | 30
| No. ST | 15 | 15 | 30
| No.EBC | 130 | 0 | 130
| No. OBC | 45 | 19 | 64
| No. Minority | 60 | 12 | 72
| General | 0 | 0 | 0
1.2.2 | No. of Village Organisation Formed (C1- . . . . . . . . . . , C2- . . . . . . . . . . , C3- . . . . . . . . . . .) | 0 | 1 | 1
1.2.3 | No. of 6 months old SHGs Part of Village Organisation | 0 | 7 | 7
| No. of CLF Formed | 0 | 0 | 0
| No. of one year old VO part of CLF | 0 | 0 | 0
| No. of VO Registered under Cooperative Society Act-1999 | 0 | 0 | 0
COMMUNITY CADRES - IB & CB
1.2.6 | Number of CM working | 15 | 0 | 15
1.2.7 | Number of VO Book Keepers working | 0 | 0 | 0
1.2.8 | Number of Internal CRPs - SHG Formation working | 0 | 0 | 0
1.2.9 | Number of Internal CRPs-VO formation working | 0 | 0 | 0
1.2.10 | Number of Internal CRPs -Master Trainer working | 0 | 0 | 0
| No. of TSC CRP identified/Trained | 0 | 0 | 0
In-1.3 | At least 75% of formed VOs accessed and managed project funds as per project processes at any point of time
1.3.1 | No of VOs having Bank Account | 0 | 0 | 0
1.3.2 | No of VO to manage Baalwaadi | 0 | 0 | 0
1.3.3 | No of VO to be promoted as Health & Nutrition center | 0 | 0 | 0
1.3.4 | Number of VO participating in HRF | 0 | 0 | 0
1.3.5 | No. of members benefitted in HRF | 0 | 0 | 0
1.3.6 | No of VO received funding for its Action Plan | 0 | 0 | 0
In-1.4
1.4.2 | No. of SHGs having Bank A/C | 34 | 0 | 34
1.4.3 | No of Bank Mitra working | 0 | 0 | 0
1.4.4 | No of eligible SHGs ( six month old SHG + following PANCHSUTRA ) financed by Banks | 0 | 0 | 0
1.4.5 | Amount Loaned by Banks to SHG | 0 | 0 | 0
1.4.6 | No of Groups repeat financed by Banks | 0 | 0 | 0
1.4.7 | Repeat financed Amount by Banks | 0 | 0 | 0
1.4.10 | No. of SHG members received bond under insurance programme. | 0 | 0 | 0
Result-2 | Establishment and use of Community Investment Fund for food security, social services, assets and income generation and service sector investment
2.1.1 | No of Group visited for Social plan | 0 | 0 | 0
2.1.2 | No of SHG members made signature literate | 0 | 35 | 35
2.1.3 | No of SHG made financial literate | 0 | 0 | 0
5 | No of SHG Member linked with RSBY - Health insurance | 0 | 0 | 0
2.1.5 | Sanitation Programme initiated with number of SHGs | 0 | 0 | 0
2.1.6 | No. of SHG HHs linked with Social Security Programme | 0 | 0 | 0
2.1.7 | No of Social Security Resource Person working | 0 | 0 | 0
2.1.8 | NO of Social Security community professional working | 0 | 0 | 0
2.1.9 | No of groups to complete Micro Planing exercise within 3 months of Group formation | 0 | 10 | 10
2.1.10 | No of Group Recd ICF through BPIU | 0 | 5 | 5
2.1.11 | No of Group Recd ICF through VO | 0 | 0 | 0
2.1.12 | Total No. of Groups received ICF through Vo/BPIU | 0 | 0 | 0
2.1.13 | No of groups/Farmers to complete Livelihoods Micro Planing exercise(SWI) | 0 | 0 | 0
2.1.14 | No of Group Revisited for Micro plan | 0 | 0 | 0
2.1.15 | No of trained CM generating Micro Plan | 0 | 0 | 0
Food security increased for 80% of target households as compared to the baseline
2.1.16 | Number of VO participating in FSF | 0 | 0 | 0
2.1.17 | No of HH linked with FS Intervention | 0 | 0 | 0
Result - 3 | Establishment and operationalization of Technical Assistance Fund.
In- 3.1 | At least 5 major business linkages established through public/private partnership by CBOs
3.1.1 | No of SHG members registered in VO for SRI | 0 | 0 | 0
3.1.2 | No of SHG members registered in VO for SWI | 0 | 0 | 0
3.1.3 | No of Acres of land will be under Agriculture Intervention-SRI | 0 | 0 | 0
3.1.4 | No of Acres of land will be under Agriculture Intervention- SWI | 0 | 0 | 0
3.1.5 | No of vermi-compost pit will be prepared | 0 | 0 | 0
3.1.6 | No of VRP will work in the Agriculture Intervention | 0 | 0 | 0
3.1.7 | No of Skilled Extension Worker will be created in Agriculture Intervention | 0 | 0 | 0
3.1.8 | No of SHG members will be registered in existing DCS | 0 | 0 | 0
3.1.9 | No of New DCS formed | 0 | 0 | 0
3.1.10 | No of SHG members will be registered in new DCS | 0 | 0 | 0
3.1.11 | No of DCS promoted as resource DCS | 0 | 0 | 0
3.1.13 | No of Kishan days will be organized | 0 | 0 | 0
3.1.14 | No of Cluster Adhibesan will be organized | 0 | 0 | 0
3.1.15 | No of VO have efficient equipment management system in place | 0 | 0 | 0
| Moong MP | 0 | 0 | 0
| No. of Katta for moong cultivation0 | 0 | 0 | 0
Atleast 5,000 Direct jobs created through Project facilitation and atleast 75% of them are getting sustained income
3.1.16 | No of youth identified - data base prepared | 0 | 0 | 0
3.1.17 | No of Youth Placed by direct placement | 0 | 0 | 0
3.1.18 | No of Youth Placed by service sector agency | 0 | 0 | 0
3.1.19 | No of JRP working | 0 | 0 | 0
Project Monitoring and Learning System established, including RLMIS, learning and experience sharing forums at different levels of Project management
3.1.20 | % of Cluster generating reports through MIS | 0 | 0 | 0
3.1.21 | No of SHG graded | 0 | 10 | 10
3.1.22 | No of VO rated | 0 | 0 | 0
3.1.23 | No of Case study generated ( Best Practice - Institution Program,Procurement, Financial Mgmt.) | 0 | 0 | 0
Result 4 | Project implementation procedures and agreed business standards are followed for at least 80% of project interventions at any point in time
4.2.1 | No of MOU signed between BPIU and Community Based Organisation | 0 | 0 | 0
4.2.2 | No of UC received within One month time of CIF release from CBOs | 0 | 0 | 0
4.2.3 | No of CBOs trained on Community Procurement | 0 | 0 | 0
4.2.4 | % of Community Cadre payment made in the Ist week of the month | 0 | 0 | 0
4.2.5 | No of VO submitting Receipt & payment on monthly basis | 0 | 0 | 0
4.2.6 | No of VO two months old procured establishment materials | 0 | 0 | 0
Note on B9: Anurag Kumar (MIS Exeucutive) Please mention in this field cluster wise no. of SHG.
Note on B17: Anurag Kumar (MIS Exeucutive) Please mention in this field cluster wise no. of VO.

## Marauna
MPPR OF - Marauna, Month - October 2014
Sl. | DESCRIPTION OF PROGRAM | Cummalitive achievement Previous month | Cummalitive achievement in current month | Cummalative achievement
1 | No. of Panchayats | 4 | 0 | 4
2 | No of revenue villages to be covered | 13 | 0 | 13
3 | No of Village to be saturated (geographically) - certification from the VO | 0 | 0 | 0
Result-1 | Formation of self reliant and inclusive community institutions including SHGs, Village Organizations and Federations.
In-1.2 | Self managed self help groups (SHGs) established, covering at least 80% of the target households, 60% of formed SHGs into VO; and 40% of the formed VOs into BLF.
| Total SGSY groups in JEEViKA fold | 22 | 0 | 22
1.2.1 | Total No of SHG formed (C1- …………….. , C2- . . . . . . . . . . , C3- . . . . . . . . . . .) *** | 146 | 20 | 166
| TOTAL NO OF POOR MOBILISED | 1569 | 240 | 1809
| No. of SC | 370 | 10 | 380
| No. ST | 0 | 5 | 5
| No.EBC | 707 | 15 | 722
| No. OBC | 403 | 30 | 433
| No. Minority | 78 | 10 | 88
| General | 6 | 2 | 8
1.2.2 | No. of Village Organisation Formed (C1- . . . . . . . . . . , C2- . . . . . . . . . . , C3- . . . . . . . . . . .) | 0 | 2 | 2
1.2.3 | No. of 6 months old SHGs Part of Village Organisation | 0 | 20 | 20
| No. of CLF Formed | 0 | 0 | 0
| No. of one year old VO part of CLF | 0 | 0 | 0
| No. of VO Registered under Cooperative Society Act-1999 | 0 | 0 | 0
COMMUNITY CADRES - IB & CB
1.2.6 | Number of CM working | 24 | 0 | 24
1.2.7 | Number of VO Book Keepers working | 0 | 0 | 0
1.2.8 | Number of Internal CRPs - SHG Formation working | 0 | 0 | 0
1.2.9 | Number of Internal CRPs-VO formation working | 0 | 0 | 0
1.2.10 | Number of Internal CRPs -Master Trainer working | 0 | 0 | 0
| No. of TSC CRP identified/Trained | 0 | 0 | 0
In-1.3 | At least 75% of formed VOs accessed and managed project funds as per project processes at any point of time
1.3.1 | No of VOs having Bank Account | 0 | 0 | 0
1.3.2 | No of VO to manage Baalwaadi | 0 | 0 | 0
1.3.3 | No of VO to be promoted as Health & Nutrition center | 0 | 0 | 0
1.3.4 | Number of VO participating in HRF | 0 | 0 | 0
1.3.5 | No. of members benefitted in HRF | 0 | 0 | 0
1.3.6 | No of VO received funding for its Action Plan | 0 | 0 | 0
In-1.4
1.4.2 | No. of SHGs having Bank A/C | 67 | 4 | 71
1.4.3 | No of Bank Mitra working | 0 | 0 | 0
1.4.4 | No of eligible SHGs ( six month old SHG + following PANCHSUTRA ) financed by Banks | 0 | 0 | 0
1.4.5 | Amount Loaned by Banks to SHG | 0 | 0 | 0
1.4.6 | No of Groups repeat financed by Banks | 0 | 0 | 0
1.4.7 | Repeat financed Amount by Banks | 0 | 0 | 0
1.4.10 | No. of SHG members received bond under insurance programme. | 0 | 0 | 0
Result-2 | Establishment and use of Community Investment Fund for food security, social services, assets and income generation and service sector investment
2.1.1 | No of Group visited for Social plan | 0 | 0 | 0
2.1.2 | No of SHG members made signature literate | 309 | 25 | 334
2.1.3 | No of SHG made financial literate | 0 | 5 | 5
5 | No of SHG Member linked with RSBY - Health insurance | 0 | 0 | 0
2.1.5 | Sanitation Programme initiated with number of SHGs | 0 | 0 | 0
2.1.6 | No. of SHG HHs linked with Social Security Programme | 0 | 0 | 0
2.1.7 | No of Social Security Resource Person working | 0 | 0 | 0
2.1.8 | NO of Social Security community professional working | 0 | 0 | 0
2.1.9 | No of groups to complete Micro Planing exercise within 3 months of Group formation | 0 | 0 | 0
2.1.10 | No of Group Recd ICF through BPIU | 0 | 33 | 33
2.1.11 | No of Group Recd ICF through VO | 0 | 0 | 0
2.1.12 | Total No. of Groups received ICF through Vo/BPIU | 0 | 33 | 33
2.1.13 | No of groups/Farmers to complete Livelihoods Micro Planing exercise(SWI) | 0 | 0 | 0
2.1.14 | No of Group Revisited for Micro plan | 0 | 0 | 0
2.1.15 | No of trained CM generating Micro Plan | 0 | 3 | 3
Food security increased for 80% of target households as compared to the baseline
2.1.16 | Number of VO participating in FSF | 0 | 0 | 0
2.1.17 | No of HH linked with FS Intervention | 0 | 0 | 0
Result - 3 | Establishment and operationalization of Technical Assistance Fund.
In- 3.1 | At least 5 major business linkages established through public/private partnership by CBOs
3.1.1 | No of SHG members registered in VO for SRI | 0 | 0 | 0
3.1.2 | No of SHG members registered in VO for SWI | 0 | 0 | 0
3.1.3 | No of Acres of land will be under Agriculture Intervention-SRI | 0 | 0 | 0
3.1.4 | No of Acres of land will be under Agriculture Intervention- SWI | 0 | 0 | 0
3.1.5 | No of vermi-compost pit will be prepared | 0 | 0 | 0
3.1.6 | No of VRP will work in the Agriculture Intervention | 0 | 0 | 0
3.1.7 | No of Skilled Extension Worker will be created in Agriculture Intervention | 0 | 0 | 0
3.1.8 | No of SHG members will be registered in existing DCS | 0 | 0 | 0
3.1.9 | No of New DCS formed | 0 | 0 | 0
3.1.10 | No of SHG members will be registered in new DCS | 0 | 0 | 0
3.1.11 | No of DCS promoted as resource DCS | 0 | 0 | 0
3.1.13 | No of Kishan days will be organized | 0 | 0 | 0
3.1.14 | No of Cluster Adhibesan will be organized | 0 | 0 | 0
3.1.15 | No of VO have efficient equipment management system in place | 0 | 0 | 0
| Moong MP | 0 | 0 | 0
| No. of Katta for moong cultivation0 | 0 | 0 | 0
Atleast 5,000 Direct jobs created through Project facilitation and atleast 75% of them are getting sustained income
3.1.16 | No of youth identified - data base prepared | 0 | 0 | 0
3.1.17 | No of Youth Placed by direct placement | 0 | 0 | 0
3.1.18 | No of Youth Placed by service sector agency | 0 | 0 | 0
3.1.19 | No of JRP working | 0 | 0 | 0
Project Monitoring and Learning System established, including RLMIS, learning and experience sharing forums at different levels of Project management
3.1.20 | % of Cluster generating reports through MIS | 0 | 0 | 0
3.1.21 | No of SHG graded | 0 | 0 | 0
3.1.22 | No of VO rated | 0 | 0 | 0
3.1.23 | No of Case study generated ( Best Practice - Institution Program,Procurement, Financial Mgmt.) | 0 | 0 | 0
Result 4 | Project implementation procedures and agreed business standards are followed for at least 80% of project interventions at any point in time
4.2.1 | No of MOU signed between BPIU and Community Based Organisation | 0 | 0 | 0
4.2.2 | No of UC received within One month time of CIF release from CBOs | 0 | 0 | 0
4.2.3 | No of CBOs trained on Community Procurement | 0 | 0 | 0
4.2.4 | % of Community Cadre payment made in the Ist week of the month | 0 | 0 | 0
4.2.5 | No of VO submitting Receipt & payment on monthly basis | 0 | 0 | 0
4.2.6 | No of VO two months old procured establishment materials | 0 | 0 | 0
Note on B9: Anurag Kumar (MIS Exeucutive) Please mention in this field cluster wise no. of SHG.
Note on B17: Anurag Kumar (MIS Exeucutive) Please mention in this field cluster wise no. of VO.

## Saraigadh Bhaptihai
MPPR OF - Saraigadh, Month - October 2014
Sl. | DESCRIPTION OF PROGRAM | Cummalitive achievement Previous month | Cummalitive achievement in current month | Cummalative achievement
1 | No. of Panchayats | 4 | 1 | 5
2 | No of revenue villages to be covered | 10 | 1 | 11
3 | No of Village to be saturated (geographically) - certification from the VO | 0 | 0 | 0
Result-1 | Formation of self reliant and inclusive community institutions including SHGs, Village Organizations and Federations.
In-1.2 | Self managed self help groups (SHGs) established, covering at least 80% of the target households, 60% of formed SHGs into VO; and 40% of the formed VOs into BLF.
| Total SGSY groups in JEEViKA fold | 21 | 0 | 21
1.2.1 | Total No of SHG formed (C1- . . . . . . . . . . , C2- . . . . . . . . . . , C3- . . . . . . . . . . .) *** | 141 | 22 | 163
| TOTAL NO OF POOR MOBILISED | 1752 | 268 | 2020
| No. of SC | 376 | 52 | 428
| No. ST | 0 | 0 | 0
| No.EBC | 449 | 89 | 538
| No. OBC | 750 | 91 | 841
| No. Minority | 128 | 18 | 146
| General | 49 | 18 | 67
1.2.2 | No. of Village Organisation Formed (C1- . . . . . . . . . . , C2- . . . . . . . . . . , C3- . . . . . . . . . . .) | 1 | 0 | 1
1.2.3 | No. of 6 months old SHGs Part of Village Organisation | 8 | 0 | 8
| No. of CLF Formed | 0 | 0 | 0
| No. of one year old VO part of CLF | 0 | 0 | 0
| No. of VO Registered under Cooperative Society Act-1999 | 0 | 0 | 0
COMMUNITY CADRES - IB & CB
1.2.6 | Number of CM working | 18 | 1 | 19
1.2.7 | Number of VO Book Keepers working | 0 | 0 | 0
1.2.8 | Number of Internal CRPs - SHG Formation working | 0 | 0 | 0
1.2.9 | Number of Internal CRPs-VO formation working | 0 | 0 | 0
1.2.10 | Number of Internal CRPs -Master Trainer working | 0 | 0 | 0
| No. of TSC CRP identified/Trained | 0 | 0 | 0
In-1.3 | At least 75% of formed VOs accessed and managed project funds as per project processes at any point of time
1.3.1 | No of VOs having Bank Account | 0 | 0 | 0
1.3.2 | No of VO to manage Baalwaadi | 0 | 0 | 0
1.3.3 | No of VO to be promoted as Health & Nutrition center | 0 | 0 | 0
1.3.4 | Number of VO participating in HRF | 0 | 0 | 0
1.3.5 | No. of members benefitted in HRF | 0 | 0 | 0
1.3.6 | No of VO received funding for its Action Plan | 0 | 0 | 0
In-1.4
1.4.2 | No. of SHGs having Bank A/C | 33 | 0 | 33
1.4.3 | No of Bank Mitra working | 0 | 0 | 0
1.4.4 | No of eligible SHGs ( six month old SHG + following PANCHSUTRA ) financed by Banks | 0 | 0 | 0
1.4.5 | Amount Loaned by Banks to SHG | 0 | 0 | 0
1.4.6 | No of Groups repeat financed by Banks | 0 | 0 | 0
1.4.7 | Repeat financed Amount by Banks | 0 | 0 | 0
1.4.10 | No. of SHG members received bond under insurance programme. | 0 | 0 | 0
Result-2 | Establishment and use of Community Investment Fund for food security, social services, assets and income generation and service sector investment
2.1.1 | No of Group visited for Social plan | 0 | 0 | 0
2.1.2 | No of SHG members made signature literate | 36 | 0 | 36
2.1.3 | No of SHG made financial literate | 0 | 0 | 0
5 | No of SHG Member linked with RSBY - Health insurance | 0 | 0 | 0
2.1.5 | Sanitation Programme initiated with number of SHGs | 0 | 0 | 0
2.1.6 | No. of SHG HHs linked with Social Security Programme | 0 | 0 | 0
2.1.7 | No of Social Security Resource Person working | 0 | 0 | 0
2.1.8 | NO of Social Security community professional working | 0 | 0 | 0
2.1.9 | No of groups to complete Micro Planing exercise within 3 months of Group formation | 15 | 0 | 15
2.1.10 | No of Group Recd ICF through BPIU | 0 | 0 | 0
2.1.11 | No of Group Recd ICF through VO | 0 | 0 | 0
2.1.12 | Total No. of Groups received ICF through Vo/BPIU | 0 | 0 | 0
2.1.13 | No of groups/Farmers to complete Livelihoods Micro Planing exercise(SWI) | 0 | 0 | 0
2.1.14 | No of Group Revisited for Micro plan | 12 | 0 | 12
2.1.15 | No of trained CM generating Micro Plan | 1 | 0 | 1
Food security increased for 80% of target households as compared to the baseline
2.1.16 | Number of VO participating in FSF | 0 | 0 | 0
2.1.17 | No of HH linked with FS Intervention | 0 | 0 | 0
Result - 3 | Establishment and operationalization of Technical Assistance Fund.
In- 3.1 | At least 5 major business linkages established through public/private partnership by CBOs
3.1.1 | No of SHG members registered in VO for SRI | 0 | 0 | 0
3.1.2 | No of SHG members registered in VO for SWI | 0 | 0 | 0
3.1.3 | No of Acres of land will be under Agriculture Intervention-SRI | 0 | 0 | 0
3.1.4 | No of Acres of land will be under Agriculture Intervention- SWI | 0 | 0 | 0
3.1.5 | No of vermi-compost pit will be prepared | 0 | 0 | 0
3.1.6 | No of VRP will work in the Agriculture Intervention | 0 | 0 | 0
3.1.7 | No of Skilled Extension Worker will be created in Agriculture Intervention | 0 | 0 | 0
3.1.8 | No of SHG members will be registered in existing DCS | 0 | 0 | 0
3.1.9 | No of New DCS formed | 0 | 0 | 0
3.1.10 | No of SHG members will be registered in new DCS | 0 | 0 | 0
3.1.11 | No of DCS promoted as resource DCS | 0 | 0 | 0
3.1.13 | No of Kishan days will be organized | 0 | 0 | 0
3.1.14 | No of Cluster Adhibesan will be organized | 0 | 0 | 0
3.1.15 | No of VO have efficient equipment management system in place | 0 | 0 | 0
| Moong MP | 0 | 0 | 0
| No. of Katta for moong cultivation0 | 0 | 0 | 0
Atleast 5,000 Direct jobs created through Project facilitation and atleast 75% of them are getting sustained income
3.1.16 | No of youth identified - data base prepared | 0 | 16 | 16
3.1.17 | No of Youth Placed by direct placement | 0 | 0 | 0
3.1.18 | No of Youth Placed by service sector agency | 0 | 0 | 0
3.1.19 | No of JRP working | 0 | 0 | 0
Project Monitoring and Learning System established, including RLMIS, learning and experience sharing forums at different levels of Project management
3.1.20 | % of Cluster generating reports through MIS | 0 | 0 | 0
3.1.21 | No of SHG graded | 0 | 0 | 0
3.1.22 | No of VO rated | 0 | 0 | 0
3.1.23 | No of Case study generated ( Best Practice - Institution Program,Procurement, Financial Mgmt.) | 0 | 0 | 0
Result 4 | Project implementation procedures and agreed business standards are followed for at least 80% of project interventions at any point in time
4.2.1 | No of MOU signed between BPIU and Community Based Organisation | 0 | 0 | 0
4.2.2 | No of UC received within One month time of CIF release from CBOs | 0 | 0 | 0
4.2.3 | No of CBOs trained on Community Procurement | 0 | 0 | 0
4.2.4 | % of Community Cadre payment made in the Ist week of the month | 85 | 0 | 85
4.2.5 | No of VO submitting Receipt & payment on monthly basis | 0 | 0 | 0
4.2.6 | No of VO two months old procured establishment materials | 0 | 0 | 0
Note on B9: Anurag Kumar (MIS Exeucutive) Please mention in this field cluster wise no. of SHG.
Note on B17: Anurag Kumar (MIS Exeucutive) Please mention in this field cluster wise no. of VO.

## SUPAUL
MPPR OF DPCU- Supaul , Month -October 2014
Sl. | DESCRIPTION OF PROGRAM | Cummalitive achievement Previous month | Cummalitive achievement in current month | Cummalative achievement
1 | No. of Panchayats | 87 | 5 | 92
2 | No of revenue villages to be covered | 212 | 6 | 218
3 | No of Village to be saturated (geographically) - certification from the VO | 86 | 0 | 86
Result-1 | Formation of self reliant and inclusive community institutions including SHGs, Village Organizations and Federations.
In-1.2 | Self managed self help groups (SHGs) established, covering at least 80% of the target households, 60% of formed SHGs into VO; and 40% of the formed VOs into BLF.
| Total SGSY groups in JEEViKA fold | 181 | 57 | 238 | Only Validate
1.2.1 | Total No of SHG formed | 5973 | 182 | 6155
| TOTAL NO OF POOR MOBILISED | 71326 | 2107 | 73433
| No. of SC | 17538 | 234 | 17772
| No. ST | 1070 | 65 | 1135
| No.EBC | 17514 | 621 | 18135
| No. OBC | 20573 | 722 | 21295
| No. Minority | 10246 | 155 | 10401
| General | 2229 | 105 | 2334
1.2.2 | No. of Village Organisation Formed | 351 | 7 | 358
1.2.3 | No. of 6 months old SHGs Part of Village Organisation | 3614 | 60 | 3674
| No. of CLF Formed | 7 | 0 | 7
| No. of one year old VO part of CLF | 120 | 0 | 120
| No. of VO Registered under Cooperative Society Act-1999 | 22 | 0 | 22
COMMUNITY CADRES - IB & CB
1.2.6 | Number of CM working | 649 | 22 | 671
1.2.7 | Number of VO Book Keepers working | 67 | 1 | 68
1.2.8 | Number of Internal CRPs - SHG Formation working | 376 | 1 | 377
1.2.9 | Number of Internal CRPs-VO formation working | 28 | 0 | 28
1.2.10 | Number of Internal CRPs -Master Trainer working | 37 | 0 | 37
| No. of TSC CRP identified/Trained | 11 | 0 | 11
In-1.3 | At least 75% of formed VOs accessed and managed project funds as per project processes at any point of time
1.3.1 | No of VOs having Bank Account | 323 | 2 | 325
1.3.2 | No of VO to manage Baalwaadi | 0 | 0 | 0
1.3.3 | No of VO to be promoted as Health & Nutrition center | 0 | 0 | 0
1.3.4 | Number of VO participating in HRF | 190 | 0 | 190
1.3.5 | No. of members benefitted in HRF | 812 | 8 | 820
1.3.6 | No of VO received funding for its Action Plan | 0 | 0 | 0
In-1.4
1.4.2 | No. of SHGs having Bank A/C | 4498 | 186 | 4684
1.4.3 | No of Bank Mitra working | 20 | 6 | 26
1.4.4 | No of eligible SHGs ( six month old SHG + following PANCHSUTRA ) financed by Banks | 3361 | 55 | 3416
1.4.5 | Amount Loaned by Banks to SHG | 168050000 | 0 | 168050000
1.4.6 | No of Groups repeat financed by Banks | 31 | 0 | 31
1.4.7 | Repeat financed Amount by Banks | 3100000 | 0 | 3100000
1.4.10 | No. of SHG members received bond under insurance programme. | 12360 | 0 | 12360
Result-2 | Establishment and use of Community Investment Fund for food security, social services, assets and income generation and service sector investment
2.1.1 | No of Group visited for Social plan | 41 | 0 | 41
2.1.2 | No of SHG members made signature literate | 30810 | 1542 | 32352
2.1.3 | No of SHG made financial literate | 30 | 6 | 36
5 | No of SHG Member linked with RSBY - Health insurance | 5989 | 0 | 5989
2.1.5 | Sanitation Programme initiated with number of SHGs | 60 | 0 | 60
2.1.6 | No. of SHG HHs linked with Social Security Programme | 0 | 0 | 0
2.1.7 | No of Social Security Resource Person working | 0 | 0 | 0
2.1.8 | NO of Social Security community professional working | 0 | 0 | 0
2.1.9 | No of groups to complete Micro Planing exercise within 3 months of Group formation | 3911 | 76 | 3987
2.1.10 | No of Group Recd ICF through BPIU | 2407 | 135 | 2542
2.1.11 | No of Group Recd ICF through VO | 0 | 0 | 0
2.1.12 | Total No. of Groups received ICF through Vo/BPIU | 3434 | 130 | 3564
2.1.13 | No of groups/Farmers to complete Livelihoods Micro Planing exercise(SWI) | 1200 | 100 | 1300
2.1.14 | No of Group Revisited for Micro plan | 12 | 0 | 12
2.1.15 | No of trained CM generating Micro Plan | 56 | 4 | 60
Food security increased for 80% of target households as compared to the baseline
2.1.16 | Number of VO participating in FSF | 186 | 0 | 186
2.1.17 | No of HH linked with FS Intervention | 7740 | 263 | 8003
Result - 3 | Establishment and operationalization of Technical Assistance Fund.
In- 3.1 | At least 5 major business linkages established through public/private partnership by CBOs
3.1.1 | No of SHG members registered in VO for SRI | 10444 | 198 | 10642
3.1.2 | No of SHG members registered in VO for SWI | 1178 | 0 | 1178
3.1.3 | No of Acres of land will be under Agriculture Intervention-SRI | 6337 | 10 | 6347
3.1.4 | No of Acres of land will be under Agriculture Intervention- SWI | 2765 | 0 | 2765
3.1.5 | No of vermi-compost pit will be prepared | 3 | 0 | 3
3.1.6 | No of VRP will work in the Agriculture Intervention | 170 | 6 | 176
3.1.7 | No of Skilled Extension Worker will be created in Agriculture Intervention | 0 | 0 | 0
3.1.8 | No of SHG members will be registered in existing DCS | 0 | 0 | 0
3.1.9 | No of New DCS formed | 0 | 0 | 0
3.1.10 | No of SHG members will be registered in new DCS | 0 | 0 | 0
3.1.11 | No of DCS promoted as resource DCS | 0 | 0 | 0
3.1.13 | No of Kishan days will be organized | 0 | 0 | 0
3.1.14 | No of Cluster Adhibesan will be organized | 0 | 0 | 0
3.1.15 | No of VO have efficient equipment management system in place | 44 | 0 | 44
| Moong MP | 1405 | 0 | 1405
| No. of Katta for moong cultivation0 | 7298 | 0 | 7298
Atleast 5,000 Direct jobs created through Project facilitation and atleast 75% of them are getting sustained income
3.1.16 | No of youth identified - data base prepared | 10149 | 716 | 10865
3.1.17 | No of Youth Placed by direct placement | 65 | 0 | 65
3.1.18 | No of Youth Placed by service sector agency | 0 | 0 | 0
3.1.19 | No of JRP working | 10 | 1 | 11
Project Monitoring and Learning System established, including RLMIS, learning and experience sharing forums at different levels of Project management
3.1.20 | % of Cluster generating reports through MIS | 95 | 0 | 95
3.1.21 | No of SHG graded | 3700 | 61 | 3761
3.1.22 | No of VO rated | 135 | 0 | 135
3.1.23 | No of Case study generated ( Best Practice - Institution Program,Procurement, Financial Mgmt.) | 6 | 0 | 6
Result 4 | Project implementation procedures and agreed business standards are followed for at least 80% of project interventions at any point in time
4.2.1 | No of MOU signed between BPIU and Community Based Organisation | 228 | 0 | 228
4.2.2 | No of UC received within One month time of CIF release from CBOs | 1446 | 6 | 1452
4.2.3 | No of CBOs trained on Community Procurement | 91 | 0 | 91
4.2.4 | % of Community Cadre payment made in the Ist week of the month | 153 | 111 | 264
4.2.5 | No of VO submitting Receipt & payment on monthly basis | 258 | 0 | 258
4.2.6 | No of VO two months old procured establishment materials | 84 | 0 | 84